## Sheet1
| cost_multiplier | agent | action | duration | cost | level | time | phase | location | site_depth | hub_height | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels
0 | 0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ArrayCableInstallation
1 | 0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
2 |  | Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
3 | 1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
4 | 0.5 | Heavy Lift Vessel | Mobilize | 72 | 750000 | ACTION | 0 | OffshoreSubstationInstallation
5 | 0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | OffshoreSubstationInstallation
6 | 0.5 | WTIV | Mobilize | 72 | 750000 | ACTION | 0 | TurbineInstallation
7 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
8 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
9 |  | Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
10 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  |  |  | ExportCableInstallation
11 |  | Export Cable Installation Vessel | Tow Plow | 0.2 | 1000 | ACTION | 6.2 | ExportCableInstallation |  |  |  | ExportCableInstallation
12 |  | Export Cable Installation Vessel | Pull Winch | 0.2 | 1000 | ACTION | 6.4 | ExportCableInstallation |  |  |  | ExportCableInstallation
13 |  | Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 7.4 | ExportCableInstallation |  |  |  | ExportCableInstallation
14 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 8 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
15 |  | Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | OffshoreSubstationInstallation |  |  |  | OffshoreSubstationInstallation
16 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 12 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
17 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12.9 | ExportCableInstallation |  |  |  | ExportCableInstallation
18 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 13.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
19 |  | Heavy Lift Vessel | Transit | 14.2857 | 297619.0476 | ACTION | 14.2857 | OffshoreSubstationInstallation
20 |  | Array Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 14.6957 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
21 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 15 | MooringSystemInstallation
22 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 15 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
23 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 16.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
24 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16.6957 | ArrayCableInstallation
25 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 17 | MooringSystemInstallation
26 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17.6957 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
27 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 18.4 | ExportCableInstallation |  |  |  | ExportCableInstallation
28 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 19.4 | ExportCableInstallation |  |  |  | ExportCableInstallation
29 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 20.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
30 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 21 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
31 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 23.1957 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
32 |  | Feeder 0 | Fasten Topside | 12 | 60000 | ACTION | 24 | OffshoreSubstationInstallation |  |  |  | OffshoreSubstationInstallation
33 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 24.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
34 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 28.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
35 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 28.6957 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
36 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 29.6957 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
37 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 30 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
38 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 31.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
39 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 33 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
40 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 36.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
41 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8.0832 | 40415.8972 | ACTION | 37.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
42 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 38.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
43 |  | Feeder 0 | Transit | 16.6667 | 83333.3333 | ACTION | 40.6667 | OffshoreSubstationInstallation
44 |  | Heavy Lift Vessel | Delay | 26.381 | 549603.1746 | ACTION | 40.6667 | OffshoreSubstationInstallation | Site
45 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 41 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
46 |  | Heavy Lift Vessel | Position Onsite | 2 | 41666.6667 | ACTION | 42.6667 | OffshoreSubstationInstallation
47 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 43 | MooringSystemInstallation
48 |  | Heavy Lift Vessel | RovSurvey | 1 | 20833.3333 | ACTION | 43.6667 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
49 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 44.2788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
50 |  | Heavy Lift Vessel | Release Monopile | 3 | 62500 | ACTION | 46.6667 | OffshoreSubstationInstallation
51 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 47 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
52 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 47.2857 | TurbineInstallation
53 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 49.2857 | TurbineInstallation
54 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 49.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
55 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 51.7788 | ArrayCableInstallation
56 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 52.2857 | TurbineInstallation
57 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 52.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
58 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 52.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
59 |  | Heavy Lift Vessel | Upend Monopile | 9.1 | 189583.3333 | ACTION | 55.7667 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
60 |  | Heavy Lift Vessel | Lower Monopile | 0.091 | 1895.8333 | ACTION | 55.8577 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
61 |  | Export Cable Installation Vessel | Lay/Bury Cable | 37 | 185000 | ACTION | 56.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
62 |  | Heavy Lift Vessel | Crane Reequip | 1 | 20833.3333 | ACTION | 56.8577 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
63 |  | Export Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 59.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
64 |  | Array Cable Installation Vessel | Delay | 7 | 35000 | ACTION | 59.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
65 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 62.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
66 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 65.2788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
67 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 67 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
68 |  | Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 69 | MooringSystemInstallation
69 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 70.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
70 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 71 | MooringSystemInstallation
71 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 71.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
72 |  | Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 75 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
73 |  | Export Cable Installation Vessel | Lay/Bury Cable | 16 | 80000 | ACTION | 75.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
74 |  | Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 75.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
75 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 79 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
76 |  | Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 89 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
77 |  | Heavy Lift Vessel | Delay | 35 | 729166.6667 | ACTION | 91.8577 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
78 |  | WTIV | Delay | 39 | 812500 | ACTION | 91.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
79 |  | Heavy Lift Vessel | Drive Monopile | 1.5 | 31250 | ACTION | 93.3577 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
80 |  | Heavy Lift Vessel | Release Topside | 2 | 41666.6667 | ACTION | 95.3577 | OffshoreSubstationInstallation
81 |  | Feeder 0 | ActiveFeeder | 54.691 | 273455 | ACTION | 95.3577 | OffshoreSubstationInstallation | Site
82 |  | Heavy Lift Vessel | Crane Reequip | 1 | 20833.3333 | ACTION | 96.3577 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
83 |  | Heavy Lift Vessel | Lift Topside | 0.05 | 1041.6667 | ACTION | 96.4077 | OffshoreSubstationInstallation
84 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 97.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
85 |  | Export Cable Installation Vessel | Delay | 23 | 115000 | ACTION | 98.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
86 |  | Array Cable Installation Vessel | Delay | 23 | 115000 | ACTION | 98.7788 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
87 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 100.9457 | TurbineInstallation
88 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 102.2657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
89 |  | Heavy Lift Vessel | Attach Topside | 6 | 125000 | ACTION | 102.4077 | OffshoreSubstationInstallation
90 |  | Array Cable Installation Vessel | Lay/Bury Cable | 4.0832 | 20415.8972 | ACTION | 102.862 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
91 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 103.862 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
92 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 104.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
93 |  | Heavy Lift Vessel | Bolt TP | 4 | 83333.3333 | ACTION | 106.4077 | OffshoreSubstationInstallation |  | 900 |  | OffshoreSubstationInstallation
94 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 108.2657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
95 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 109 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
96 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 109.362 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
97 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 111 | MooringSystemInstallation
98 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 111.2657 | TurbineInstallation
99 |  | Feeder 0 | Transit | 16.6667 | 83333.3333 | ACTION | 112.0243 | OffshoreSubstationInstallation
100 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 112.2657 | TurbineInstallation
101 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 113.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
102 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 114.862 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
103 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 115 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
104 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 116.862 | ArrayCableInstallation
105 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 117.862 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
106 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 119.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
107 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 120.5857 | TurbineInstallation
108 |  | Heavy Lift Vessel | Transit | 14.2857 | 297619.0476 | ACTION | 120.6934 | OffshoreSubstationInstallation
109 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 121.5857 | TurbineInstallation
110 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 122.9057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
111 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 123.362 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
112 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 126.4057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
113 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 127.4057 | TurbineInstallation
114 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 128.7257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
115 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 128.862 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
116 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 129.862 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
117 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 130.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
118 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 132.2257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
119 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 133.2257 | TurbineInstallation
120 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 134.5457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
121 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 135 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
122 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8.0832 | 40415.8972 | ACTION | 137.9452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
123 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 138.0457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
124 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 138.9452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
125 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 140.0457 | TurbineInstallation
126 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 143.0457 | TurbineInstallation
127 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 143.7057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
128 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 144.4452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
129 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 145 | MooringSystemInstallation
130 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 149.7057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
131 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 149.9452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
132 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 150 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
133 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 151.9452 | ArrayCableInstallation
134 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 152.7057 | TurbineInstallation
135 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 152.9452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
136 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 154.0257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
137 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 158.4452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
138 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 160 | MooringSystemInstallation
139 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 162 | MooringSystemInstallation
140 |  | Export Cable Installation Vessel | Lay/Bury Cable | 64 | 320000 | ACTION | 162.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
141 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 166 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
142 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 168 | MooredSubInstallation
143 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 168 | MooredSubInstallation
144 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 168 | SemiSubStorageInstallation
145 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 168 | SemiSubStorageInstallation
146 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 176 | MooredSubInstallation
147 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 176 | SemiSubStorageInstallation
148 |  | Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 182 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
149 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 188 | MooredSubInstallation
150 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 188 | SemiSubStorageInstallation
151 |  | WTIV | Delay | 35 | 729166.6667 | ACTION | 189.0257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
152 |  | Export Cable Installation Vessel | Delay | 29 | 145000 | ACTION | 191.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
153 |  | Array Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 191.4452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
154 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 195.0257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
155 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 196.9452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
156 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 197.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
157 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 197.9452 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
158 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 198.0257 | TurbineInstallation
159 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 199.0257 | TurbineInstallation
160 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 200 | MooredSubInstallation
161 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 200 | SemiSubStorageInstallation
162 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 200.3457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
163 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 202 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
164 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 204 | MooringSystemInstallation
165 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8.0832 | 40415.8972 | ACTION | 206.0284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
166 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 206.3457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
167 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 207.0284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
168 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 207.3457 | TurbineInstallation
169 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 208 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
170 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 208.3457 | TurbineInstallation
171 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 209.6657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
172 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 212 | MooredSubInstallation
173 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 212 | SemiSubStorageInstallation
174 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 212.5284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
175 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 213.1657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
176 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 214.1657 | TurbineInstallation
177 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 215.4857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
178 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 218.0284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
179 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 218.9857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
180 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 219 | MooredSubInstallation
181 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 219 | SemiSubStorageInstallation
182 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 219.9857 | TurbineInstallation
183 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 220.0284 | ArrayCableInstallation
184 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 221.0284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
185 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 221.3057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
186 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 222.5 | MooredSubInstallation
187 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 222.5 | SemiSubStorageInstallation
188 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 223.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
189 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 224.8057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
190 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 226 | MooredSubInstallation
191 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 226 | SemiSubStorageInstallation
192 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 226.5284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
193 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 228 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
194 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 230 | MooringSystemInstallation
195 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 232.0284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
196 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 233.0284 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
197 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 234 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
198 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 239.0914 | TurbineInstallation
199 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8.0832 | 40415.8972 | ACTION | 241.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
200 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 242.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
201 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 243.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
202 |  | Export Cable Installation Vessel | Lay/Bury Cable | 53 | 265000 | ACTION | 244.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
203 |  | Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 247 | MooredSubInstallation
204 |  | Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 247 | SemiSubStorageInstallation
205 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 247.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
206 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 249.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
207 |  | Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 250.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
208 |  | Export Cable Installation Vessel | Delay | 6 | 30000 | ACTION | 250.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
209 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 250.5 | MooredSubInstallation
210 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 250.5 | SemiSubStorageInstallation
211 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 251.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
212 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 252.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
213 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 254 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
214 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 254.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
215 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 255.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
216 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 255.6115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
217 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 256 | MooringSystemInstallation
218 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 259.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
219 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 260 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
220 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 261.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
221 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 263.1115 | ArrayCableInstallation
222 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 263.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
223 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 264.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
224 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 267.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
225 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 269.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
226 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 269.6115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
227 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 270.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
228 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 272.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
229 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 274.5 | MooredSubInstallation
230 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 274.5 | 343125 | ACTION | 274.5 | MooredSubInstallation
231 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 274.5 | SemiSubStorageInstallation
232 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 274.5 | 343125 | ACTION | 274.5 | SemiSubStorageInstallation
233 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 275.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
234 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 275.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
235 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 276.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
236 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 280 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
237 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 280.5 | MooredSubInstallation | [7 empty] | 3
238 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 280.5 | SemiSubStorageInstallation | [7 empty] | 3
239 |  | Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 283.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
240 |  | Export Cable Installation Vessel | Lay/Bury Cable | 33 | 165000 | ACTION | 283.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
241 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 286.3771 | TurbineInstallation
242 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 288.3771 | TurbineInstallation
243 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 290 | MooringSystemInstallation
244 |  | Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 291.1115 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
245 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 291.3771 | TurbineInstallation
246 |  | Export Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 291.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
247 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 292.0371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
248 |  | Array Cable Installation Vessel | Lay/Bury Cable | 1.0832 | 5415.8972 | ACTION | 292.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
249 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 293.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
250 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 295 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
251 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 297.1667 | MooredSubInstallation | [7 empty] | 3
252 | 1 | Multi-Purpose Support Vessel | Mobilize | 168 | 700000 | ACTION | 297.1667 | MooredSubInstallation
253 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 297.1667 | SemiSubStorageInstallation | [7 empty] | 3
254 | 1 | Multi-Purpose Support Vessel | Mobilize | 168 | 700000 | ACTION | 297.1667 | SemiSubStorageInstallation
255 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 298.0371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
256 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 298.6947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
257 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 301.0371 | TurbineInstallation
258 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 302.3571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
259 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 304.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
260 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 305 | MooringSystemInstallation
261 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 306.1947 | ArrayCableInstallation
262 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 307 | MooringSystemInstallation
263 |  | Multi-Purpose Support Vessel | Transit | 10 | 41666.6667 | ACTION | 307.1667 | MooredSubInstallation
264 |  | Multi-Purpose Support Vessel | Transit | 10 | 41666.6667 | ACTION | 307.1667 | SemiSubStorageInstallation
265 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 307.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
266 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 308.3571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
267 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 309.1667 | MooredSubInstallation
268 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 309.1667 | SemiSubStorageInstallation
269 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 311 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
270 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 311.3571 | TurbineInstallation
271 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 312.3571 | TurbineInstallation
272 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 312.6947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
273 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 313.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
274 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 315.1667 | MooredSubInstallation
275 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 315.1667 | SemiSubStorageInstallation
276 |  | WTIV | Delay | 2 | 41666.6667 | ACTION | 315.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
277 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 318.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
278 |  | Export Cable Installation Vessel | Lay/Bury Cable | 27 | 135000 | ACTION | 318.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
279 |  | Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 319.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
280 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 319.4 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
281 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 320.1947 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
282 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 321.1667 | MooredSubInstallation
283 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 321.1667 | SemiSubStorageInstallation
284 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 321.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
285 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 322.6771 | TurbineInstallation
286 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 323.6771 | TurbineInstallation
287 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 324.9971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
288 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 326.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
289 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8.0832 | 40415.8972 | ACTION | 328.2779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
290 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 328.4971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
291 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 329.2779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
292 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 329.4971 | TurbineInstallation
293 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 330.8171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
294 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 331 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
295 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 333 | MooringSystemInstallation
296 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 334.3171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
297 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 334.7779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
298 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 335.3171 | TurbineInstallation
299 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 336 | MooredSubInstallation
300 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 61.5 | 0 | ACTION | 336 | MooredSubInstallation
301 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 336 | SemiSubStorageInstallation
302 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 61.5 | 0 | ACTION | 336 | SemiSubStorageInstallation
303 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 336.6371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
304 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 337 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
305 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 340.1371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
306 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 340.2779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
307 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 342.1371 | TurbineInstallation
308 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 342.2779 | ArrayCableInstallation
309 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 343.1667 | MooredSubInstallation
310 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 343.1667 | SemiSubStorageInstallation
311 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 343.2779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
312 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 344 | MooredSubInstallation
313 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 344 | SemiSubStorageInstallation
314 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 345.1371 | TurbineInstallation
315 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 345.7971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
316 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 348.7779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
317 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 351.7971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
318 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 352.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
319 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 354.2779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
320 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 354.7971 | TurbineInstallation
321 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 355.1667 | MooredSubInstallation
322 |  | Towing Group 1 | Positioning Support | 58 | 145000 | ACTION | 355.1667 | MooredSubInstallation | site | [6 empty] | 2
323 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 355.1667 | SemiSubStorageInstallation
324 |  | Towing Group 1 | Positioning Support | 58 | 145000 | ACTION | 355.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
325 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 355.2779 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
326 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 356 | MooredSubInstallation
327 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 356 | SemiSubStorageInstallation
328 |  | Export Cable Installation Vessel | Lay/Bury Cable | 36.6667 | 183333.3333 | ACTION | 356.0667 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
329 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 356.1171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
330 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 357 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
331 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 359 | MooringSystemInstallation
332 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 362.1171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
333 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 363 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
334 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8.0832 | 40415.8972 | ACTION | 363.3611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
335 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 364.3611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
336 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 364.7623 | ExportCableInstallation
337 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 365.1171 | TurbineInstallation
338 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 366.1171 | TurbineInstallation
339 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 367.4371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
340 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 368 | MooredSubInstallation
341 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 368 | SemiSubStorageInstallation
342 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 369.8611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
343 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 370.7623 | ExportCableInstallation |  |  |  | ExportCableInstallation
344 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 371.8333 | MooredSubInstallation | [7 empty] | 3
345 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 371.8333 | SemiSubStorageInstallation | [7 empty] | 3
346 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 373.4371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
347 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 374.4371 | TurbineInstallation
348 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 375.3611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
349 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 375.4371 | TurbineInstallation
350 |  | Export Cable Installation Vessel | Transit | 5 | 25000 | ACTION | 375.7623 | ExportCableInstallation
351 |  | Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 376.3611 | ArrayCableInstallation
352 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 376.7571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
353 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 376.7623 | ExportCableInstallation
354 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 378.3611 | ArrayCableInstallation
355 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 378.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
356 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 379.3611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
357 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 380 | MooredSubInstallation
358 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 380 | SemiSubStorageInstallation
359 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 380.2571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
360 |  | Export Cable Installation Vessel | Transit | 3.6957 | 18478.2609 | ACTION | 380.458 | ExportCableInstallation
361 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 381.2571 | TurbineInstallation
362 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 382.458 | ExportCableInstallation
363 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 382.5771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
364 |  | Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 382.958 | ExportCableInstallation |  |  |  | ExportCableInstallation
365 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 383 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
366 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 384.8611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
367 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 385 | MooringSystemInstallation
368 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 386.0771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
369 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 387 | MooredSubInstallation
370 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 387 | SemiSubStorageInstallation
371 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 387.0771 | TurbineInstallation
372 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 388.3971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
373 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 389 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
374 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 390.3611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
375 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 390.5 | MooredSubInstallation
376 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 390.5 | SemiSubStorageInstallation
377 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 391.3611 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
378 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 391.8971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
379 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 394 | MooredSubInstallation
380 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 394 | SemiSubStorageInstallation
381 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 397.5 | MooredSubInstallation
382 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 397.5 | SemiSubStorageInstallation
383 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 401.1276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
384 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 402.1276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
385 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 404.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
386 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 406.1829 | TurbineInstallation
387 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 407.6276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
388 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 409 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
389 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 410.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
390 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 413.1276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
391 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 414.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
392 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 415.1276 | ArrayCableInstallation
393 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 416.1276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
394 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 418.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
395 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 419 | MooringSystemInstallation
396 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 419.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
397 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 421.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
398 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 421.5 | MooredSubInstallation
399 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 49.6667 | 62083.3333 | ACTION | 421.5 | MooredSubInstallation
400 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 421.5 | SemiSubStorageInstallation
401 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 49.6667 | 62083.3333 | ACTION | 421.5 | SemiSubStorageInstallation
402 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 421.6276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
403 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 422.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
404 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 424 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
405 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 426.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
406 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 427.1276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
407 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 427.5 | MooredSubInstallation | [7 empty] | 3
408 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 427.5 | SemiSubStorageInstallation | [7 empty] | 3
409 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 428.1276 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
410 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 430.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
411 |  | Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 430.958 | ExportCableInstallation |  |  |  | ExportCableInstallation
412 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 431.958 | ExportCableInstallation |  |  |  | ExportCableInstallation
413 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 434 | MooringSystemInstallation
414 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 434.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
415 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 436 | MooringSystemInstallation
416 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 436.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
417 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 437.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
418 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 437.8941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
419 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 438.8941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
420 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 439.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
421 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 440 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
422 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 444.1667 | MooredSubInstallation | [7 empty] | 3
423 |  | Multi-Purpose Support Vessel | Delay | 89 | 370833.3333 | ACTION | 444.1667 | MooredSubInstallation | Site
424 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 444.1667 | SemiSubStorageInstallation | [7 empty] | 3
425 |  | Multi-Purpose Support Vessel | Delay | 89 | 370833.3333 | ACTION | 444.1667 | SemiSubStorageInstallation | Site
426 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 444.3941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
427 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 446.1667 | MooredSubInstallation
428 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 446.1667 | SemiSubStorageInstallation
429 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 449.8941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
430 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 451.8941 | ArrayCableInstallation
431 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 452.1667 | MooredSubInstallation
432 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 452.1667 | SemiSubStorageInstallation
433 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 452.8941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
434 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 453.4686 | TurbineInstallation
435 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 455.4686 | TurbineInstallation
436 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 455.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
437 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 458.3941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
438 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 458.4686 | TurbineInstallation
439 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 459.1286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
440 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 460 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
441 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 462 | MooringSystemInstallation
442 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 463.8941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
443 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 464.8941 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
444 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 465.1286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
445 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 466 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
446 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 468.1286 | TurbineInstallation
447 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 469.4486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
448 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 474.1667 | MooredSubInstallation
449 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 474.1667 | SemiSubStorageInstallation
450 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 474.6606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
451 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 475.4486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
452 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 475.6606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
453 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 478.4486 | TurbineInstallation
454 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 479.4486 | TurbineInstallation
455 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 480.7686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
456 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 481.1606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
457 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 481.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
458 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 486 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
459 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 486.1667 | MooredSubInstallation
460 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 486.1667 | MooredSubInstallation | site | [6 empty] | 2
461 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 486.1667 | SemiSubStorageInstallation
462 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 486.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
463 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 486.6606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
464 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 486.7686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
465 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 487.7686 | TurbineInstallation
466 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 488 | MooringSystemInstallation
467 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 488.6606 | ArrayCableInstallation
468 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 488.7686 | TurbineInstallation
469 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 489.6606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
470 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 490.0886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
471 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 492 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
472 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 493.5886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
473 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 494.5886 | TurbineInstallation
474 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 495.1606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
475 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 495.9086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
476 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 499.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
477 |  | Export Cable Installation Vessel | Lay/Bury Cable | 68 | 340000 | ACTION | 499.958 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
478 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 500.4086 | TurbineInstallation
479 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 500.958 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
480 |  | WTIV | Delay | 1 | 20833.3333 | ACTION | 501.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
481 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 502.7286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
482 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 502.8333 | MooredSubInstallation | [7 empty] | 3
483 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 502.8333 | SemiSubStorageInstallation | [7 empty] | 3
484 |  | Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 503.958 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
485 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 504 | MooredSubInstallation
486 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 504 | MooredSubInstallation
487 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 504 | SemiSubStorageInstallation
488 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 504 | SemiSubStorageInstallation
489 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 507.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
490 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 512 | MooredSubInstallation
491 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 512 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
492 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 512 | SemiSubStorageInstallation
493 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 514 | MooringSystemInstallation
494 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 518 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
495 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 524 | MooredSubInstallation
496 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 524 | SemiSubStorageInstallation
497 |  | Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 577 | MooredSubInstallation
498 |  | Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 577 | SemiSubStorageInstallation
499 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 589 | MooredSubInstallation
500 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 589 | SemiSubStorageInstallation
501 |  | Mooring System Installation Vessel | Delay | 74 | 308333.3333 | ACTION | 592 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
502 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 601 | MooredSubInstallation
503 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 601 | SemiSubStorageInstallation
504 |  | WTIV | Delay | 99 | 2062500 | ACTION | 601.7286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
505 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 605.2286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
506 |  | Array Cable Installation Vessel | Delay | 112 | 560000 | ACTION | 607.1606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
507 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 607.2286 | TurbineInstallation
508 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 607.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
509 |  | Export Cable Installation Vessel | Delay | 104 | 520000 | ACTION | 607.958 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
510 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 608 | MooredSubInstallation
511 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 608 | SemiSubStorageInstallation
512 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 610.2286 | TurbineInstallation
513 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 610.8886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
514 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 611.5 | MooredSubInstallation
515 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 611.5 | SemiSubStorageInstallation
516 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 612 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
517 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 612.6606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
518 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 613.6606 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
519 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 615 | MooredSubInstallation
520 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 615 | SemiSubStorageInstallation
521 |  | Export Cable Installation Vessel | Lay/Bury Cable | 8.0416 | 40207.9486 | ACTION | 615.9996 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
522 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 616.8886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
523 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 617.9996 | ExportCableInstallation
524 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 618.5 | MooredSubInstallation
525 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 618.5 | SemiSubStorageInstallation
526 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 619.8886 | TurbineInstallation
527 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 621.2086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
528 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 622 | MooringSystemInstallation
529 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 623.4271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
530 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 623.4996 | ExportCableInstallation |  |  |  | ExportCableInstallation
531 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 624.4271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
532 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 627 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
533 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 627.2086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
534 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 628.9996 | ExportCableInstallation |  |  |  | ExportCableInstallation
535 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 629.9271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
536 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 630.2086 | TurbineInstallation
537 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 631.2086 | TurbineInstallation
538 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 632.5286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
539 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 635.4271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
540 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 637 | MooringSystemInstallation
541 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 637.4271 | ArrayCableInstallation
542 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 637.6952 | ExportCableInstallation
543 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 638.4271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
544 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 638.5286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
545 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 639 | MooringSystemInstallation
546 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 639.5286 | TurbineInstallation
547 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 640.5286 | TurbineInstallation
548 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 641.8486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
549 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 642.5 | MooredSubInstallation
550 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 139.6667 | 174583.3333 | ACTION | 642.5 | MooredSubInstallation
551 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 642.5 | SemiSubStorageInstallation
552 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 139.6667 | 174583.3333 | ACTION | 642.5 | SemiSubStorageInstallation
553 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 643 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
554 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 643.6952 | ExportCableInstallation |  |  |  | ExportCableInstallation
555 |  | Export Cable Installation Vessel | Tow Plow | 0.2 | 1000 | ACTION | 643.8952 | ExportCableInstallation |  |  |  | ExportCableInstallation
556 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 643.9271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
557 |  | Export Cable Installation Vessel | Pull Winch | 0.2 | 1000 | ACTION | 644.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation
558 |  | Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 645.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation
559 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 645.3486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
560 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 646.3486 | TurbineInstallation
561 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 647.6686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
562 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 648.5 | MooredSubInstallation | [7 empty] | 3
563 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 648.5 | SemiSubStorageInstallation | [7 empty] | 3
564 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 649.4271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
565 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 650.4271 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
566 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 650.5952 | ExportCableInstallation |  |  |  | ExportCableInstallation
567 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 651.1686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
568 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 652.1686 | TurbineInstallation
569 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 653.4886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
570 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 656.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation
571 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 656.9886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
572 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 657.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation
573 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 658.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
574 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 660.1937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
575 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 661.1937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
576 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 663 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
577 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 665 | MooringSystemInstallation
578 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 665.1667 | MooredSubInstallation | [7 empty] | 3
579 |  | Multi-Purpose Support Vessel | Delay | 179 | 745833.3333 | ACTION | 665.1667 | MooredSubInstallation | Site
580 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 665.1667 | SemiSubStorageInstallation | [7 empty] | 3
581 |  | Multi-Purpose Support Vessel | Delay | 179 | 745833.3333 | ACTION | 665.1667 | SemiSubStorageInstallation | Site
582 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 666.6937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
583 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 667.1667 | MooredSubInstallation
584 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 667.1667 | SemiSubStorageInstallation
585 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 669 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
586 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 671.2743 | TurbineInstallation
587 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 672 | MooredSubInstallation
588 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 29.5 | 0 | ACTION | 672 | MooredSubInstallation
589 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 672 | SemiSubStorageInstallation
590 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 29.5 | 0 | ACTION | 672 | SemiSubStorageInstallation
591 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 672.1937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
592 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 673.1667 | MooredSubInstallation
593 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 673.1667 | SemiSubStorageInstallation
594 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 674.1937 | ArrayCableInstallation
595 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 675.1937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
596 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 675.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
597 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 679.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
598 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 680 | MooredSubInstallation
599 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 680 | SemiSubStorageInstallation
600 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 680.6937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
601 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 683.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
602 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 684.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
603 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 684.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
604 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 686.1937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
605 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 686.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
606 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 687.1937 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
607 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 687.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
608 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 689 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
609 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 691 | MooringSystemInstallation
610 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 691.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
611 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 692 | MooredSubInstallation
612 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 692 | SemiSubStorageInstallation
613 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 695 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
614 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 695.1667 | MooredSubInstallation
615 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 695.1667 | SemiSubStorageInstallation
616 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 695.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
617 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 696.9602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
618 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 697.9602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
619 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 699.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
620 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 701.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
621 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 702.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
622 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 703.4602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
623 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 704 | MooredSubInstallation
624 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 704 | SemiSubStorageInstallation
625 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 704.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
626 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 707.1667 | MooredSubInstallation
627 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 707.1667 | MooredSubInstallation | site | [6 empty] | 2
628 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 707.1667 | SemiSubStorageInstallation
629 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 707.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
630 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 708.9602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
631 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 710.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
632 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 710.9602 | ArrayCableInstallation
633 |  | Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 711 | MooredSubInstallation
634 |  | Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 711 | SemiSubStorageInstallation
635 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 711.9602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
636 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 715 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
637 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 717 | MooringSystemInstallation
638 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 717.4602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
639 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 718.56 | TurbineInstallation
640 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 720.56 | TurbineInstallation
641 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 721 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
642 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 722.9602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
643 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 723 | MooredSubInstallation
644 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 723 | SemiSubStorageInstallation
645 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 723.56 | TurbineInstallation
646 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 723.8333 | MooredSubInstallation | [7 empty] | 3
647 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 723.8333 | SemiSubStorageInstallation | [7 empty] | 3
648 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 723.9602 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
649 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 724.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
650 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 730 | MooredSubInstallation
651 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 730 | SemiSubStorageInstallation
652 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 730.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
653 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 733.22 | TurbineInstallation
654 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 733.5 | MooredSubInstallation
655 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 733.5 | SemiSubStorageInstallation
656 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 733.7267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
657 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 734.54 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
658 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 734.7267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
659 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 736.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
660 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 737 | MooredSubInstallation
661 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 737 | SemiSubStorageInstallation
662 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 740.2267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
663 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 740.5 | MooredSubInstallation
664 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 740.5 | SemiSubStorageInstallation
665 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 740.54 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
666 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 741 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
667 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 743.54 | TurbineInstallation
668 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 744.54 | TurbineInstallation
669 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 745.7267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
670 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 745.86 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
671 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 747.7267 | ArrayCableInstallation
672 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 748.7267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
673 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 751 | MooringSystemInstallation
674 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 751.86 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
675 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 752.86 | TurbineInstallation
676 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 753.86 | TurbineInstallation
677 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 754.2267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
678 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 755.18 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
679 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 756 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
680 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 758.68 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
681 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 759.68 | TurbineInstallation
682 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 759.7267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
683 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 760.7267 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
684 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 761 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
685 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 764.5 | MooredSubInstallation
686 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 40.6667 | 50833.3333 | ACTION | 764.5 | MooredSubInstallation
687 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 764.5 | SemiSubStorageInstallation
688 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 40.6667 | 50833.3333 | ACTION | 764.5 | SemiSubStorageInstallation
689 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 764.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
690 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 765.5 | TurbineInstallation
691 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 766 | MooringSystemInstallation
692 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 766.82 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
693 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 768 | MooringSystemInstallation
694 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 770.32 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
695 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 770.4932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
696 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 770.5 | MooredSubInstallation | [7 empty] | 3
697 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 770.5 | SemiSubStorageInstallation | [7 empty] | 3
698 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 771.4932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
699 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 772 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
700 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 772.32 | TurbineInstallation
701 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 775.32 | TurbineInstallation
702 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 775.98 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
703 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 776.9932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
704 |  | Export Cable Installation Vessel | Lay/Bury Cable | 124 | 620000 | ACTION | 781.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
705 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 781.98 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
706 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 784.98 | TurbineInstallation
707 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 787.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
708 |  | WTIV | Delay | 6 | 125000 | ACTION | 790.98 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
709 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 792 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
710 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 792.3 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
711 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 794 | MooringSystemInstallation
712 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 798 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
713 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 798.3 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
714 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 813.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
715 |  | WTIV | Delay | 17 | 354166.6667 | ACTION | 815.3 | TurbineInstallation
716 |  | Towing Group 1 | Delay | 45 | 168750 | ACTION | 815.5 | MooredSubInstallation | [7 empty] | 3
717 |  | Towing Group 1 | Delay | 45 | 168750 | ACTION | 815.5 | SemiSubStorageInstallation | [7 empty] | 3
718 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 818 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
719 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 818.3 | TurbineInstallation
720 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 819.3 | TurbineInstallation
721 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 820 | MooringSystemInstallation
722 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 820.62 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
723 |  | Export Cable Installation Vessel | Delay | 40 | 200000 | ACTION | 821.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
724 |  | Array Cable Installation Vessel | Delay | 45 | 225000 | ACTION | 821.9932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
725 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 824 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
726 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 826.62 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
727 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 827.4932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
728 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 827.62 | TurbineInstallation
729 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 828.62 | TurbineInstallation
730 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 829.4932 | ArrayCableInstallation
731 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 829.94 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
732 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 830.4932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
733 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 832.1667 | MooredSubInstallation | [7 empty] | 3
734 |  | Multi-Purpose Support Vessel | Delay | 125 | 520833.3333 | ACTION | 832.1667 | MooredSubInstallation | Site
735 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 832.1667 | SemiSubStorageInstallation | [7 empty] | 3
736 |  | Multi-Purpose Support Vessel | Delay | 125 | 520833.3333 | ACTION | 832.1667 | SemiSubStorageInstallation | Site
737 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 833.44 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
738 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 834.1667 | MooredSubInstallation
739 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 834.1667 | SemiSubStorageInstallation
740 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 834.44 | TurbineInstallation
741 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 835.76 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
742 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 835.9932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
743 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 839.26 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
744 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 839.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
745 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 840 | MooredSubInstallation
746 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 75.5 | 0 | ACTION | 840 | MooredSubInstallation
747 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 840 | SemiSubStorageInstallation
748 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 75.5 | 0 | ACTION | 840 | SemiSubStorageInstallation
749 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 840.1667 | MooredSubInstallation
750 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 840.1667 | SemiSubStorageInstallation
751 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 840.26 | TurbineInstallation
752 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 841.4932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
753 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 841.58 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
754 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 842.4932 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
755 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 844 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
756 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 845.08 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
757 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 846 | MooringSystemInstallation
758 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 848 | MooredSubInstallation
759 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 848 | SemiSubStorageInstallation
760 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 850 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
761 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 852.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
762 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 853.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
763 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 858.7597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
764 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 859.3657 | TurbineInstallation
765 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 860 | MooredSubInstallation
766 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 860 | SemiSubStorageInstallation
767 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 862.1667 | MooredSubInstallation
768 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 862.1667 | SemiSubStorageInstallation
769 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 863.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
770 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 864.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
771 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 865.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
772 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 866.2597 | ArrayCableInstallation
773 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 867.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
774 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 867.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
775 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 870 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
776 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 871.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
777 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 872 | MooredSubInstallation
778 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 872 | SemiSubStorageInstallation
779 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 872.7597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
780 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 872.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
781 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 874.1667 | MooredSubInstallation
782 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 874.1667 | MooredSubInstallation | site | [6 empty] | 2
783 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 874.1667 | SemiSubStorageInstallation
784 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 874.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
785 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 874.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
786 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 875.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
787 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 878.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
788 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 879.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
789 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 879.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
790 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 880 | MooringSystemInstallation
791 |  | Export Cable Installation Vessel | Lay/Bury Cable | 61 | 305000 | ACTION | 882.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
792 |  | Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 882.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
793 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 883.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
794 |  | Export Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 884.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
795 |  | Array Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 884.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
796 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 885 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
797 |  | Export Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 886.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
798 |  | Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 886.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
799 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 887.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
800 |  | Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 890 | MooringSystemInstallation
801 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 890.8333 | MooredSubInstallation | [7 empty] | 3
802 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 890.8333 | SemiSubStorageInstallation | [7 empty] | 3
803 |  | Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 914 | MooringSystemInstallation
804 |  | WTIV | Delay | 30 | 625000 | ACTION | 917.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
805 |  | Turbine Assembly Line 1 | Delay | 46 | 0 | ACTION | 918 | MooredSubInstallation
806 |  | Turbine Assembly Line 1 | Delay | 46 | 0 | ACTION | 918 | SemiSubStorageInstallation
807 |  | Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 919 | MooringSystemInstallation
808 |  | Export Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 919.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
809 |  | Array Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 919.2597 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
810 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 919.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
811 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 920.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
812 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 921 | MooringSystemInstallation
813 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 922.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
814 |  | Array Cable Installation Vessel | Lay/Bury Cable | 4.7665 | 23832.5638 | ACTION | 924.0262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
815 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 925 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
816 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 925.0262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
817 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 930 | MooredSubInstallation
818 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 930 | SemiSubStorageInstallation
819 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 930.5262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
820 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 936.0262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
821 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 936.6514 | TurbineInstallation
822 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 937 | MooredSubInstallation
823 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 937 | SemiSubStorageInstallation
824 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 938.0262 | ArrayCableInstallation
825 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 938.6514 | TurbineInstallation
826 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 939.0262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
827 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 940.5 | MooredSubInstallation
828 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 940.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
829 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 940.5 | SemiSubStorageInstallation
830 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 941.6514 | TurbineInstallation
831 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 942.3114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
832 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 944.5262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
833 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 945 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
834 |  | Export Cable Installation Vessel | Lay/Bury Cable | 27 | 135000 | ACTION | 946.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
835 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 947 | MooringSystemInstallation
836 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 948.3114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
837 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 951 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
838 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 951.3114 | TurbineInstallation
839 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 952.6314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
840 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 953.5 | MooredSubInstallation
841 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 953.5 | SemiSubStorageInstallation
842 |  | WTIV | Delay | 2 | 41666.6667 | ACTION | 954.6314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
843 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 957 | MooredSubInstallation
844 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 957 | SemiSubStorageInstallation
845 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 960.5 | MooredSubInstallation
846 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 960.5 | SemiSubStorageInstallation
847 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 960.6314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
848 |  | Export Cable Installation Vessel | Delay | 15 | 75000 | ACTION | 961.0952 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
849 |  | Array Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 961.5262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
850 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 963.6314 | TurbineInstallation
851 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 964.6314 | TurbineInstallation
852 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 965.9514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
853 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 966.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
854 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 967.0262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
855 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 968.0262 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
856 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 971 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
857 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 971.9514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
858 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 972.9514 | TurbineInstallation
859 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 973 | MooringSystemInstallation
860 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 973.9514 | TurbineInstallation
861 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 975.2714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
862 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 977 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
863 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 977.7927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
864 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 978.7714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
865 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 978.7927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
866 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 979.7714 | TurbineInstallation
867 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 981.0914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
868 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 984.2927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
869 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 984.5 | MooredSubInstallation
870 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 93.6667 | 117083.3333 | ACTION | 984.5 | MooredSubInstallation
871 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 984.5 | SemiSubStorageInstallation
872 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 93.6667 | 117083.3333 | ACTION | 984.5 | SemiSubStorageInstallation
873 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 984.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
874 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 985.5914 | TurbineInstallation
875 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 986.9114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
876 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 989.7927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
877 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 990.4114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
878 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 990.5 | MooredSubInstallation | [7 empty] | 3
879 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 990.5 | SemiSubStorageInstallation | [7 empty] | 3
880 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 991.7927 | ArrayCableInstallation
881 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 992.4114 | TurbineInstallation
882 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 992.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
883 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 992.7927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
884 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 995.4114 | TurbineInstallation
885 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 996.0714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
886 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 997 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
887 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 998.2927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
888 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 999 | MooringSystemInstallation
889 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1002.0714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
890 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1003 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
891 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1003.7927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
892 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1004.7927 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
893 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1005.0714 | TurbineInstallation
894 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1006.3914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
895 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1007.1667 | MooredSubInstallation | [7 empty] | 3
896 |  | Multi-Purpose Support Vessel | Delay | 133 | 554166.6667 | ACTION | 1007.1667 | MooredSubInstallation | Site
897 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1007.1667 | SemiSubStorageInstallation | [7 empty] | 3
898 |  | Multi-Purpose Support Vessel | Delay | 133 | 554166.6667 | ACTION | 1007.1667 | SemiSubStorageInstallation | Site
899 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1008 | MooredSubInstallation
900 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 23.5 | 0 | ACTION | 1008 | MooredSubInstallation
901 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1008 | SemiSubStorageInstallation
902 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 23.5 | 0 | ACTION | 1008 | SemiSubStorageInstallation
903 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1009.1667 | MooredSubInstallation
904 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1009.1667 | SemiSubStorageInstallation
905 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1012.3914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
906 |  | Export Cable Installation Vessel | Lay/Bury Cable | 52.6667 | 263333.3333 | ACTION | 1013.7619 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
907 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1014.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
908 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1015.3914 | TurbineInstallation
909 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1015.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
910 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1016 | MooredSubInstallation
911 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1016 | SemiSubStorageInstallation
912 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1016.3914 | TurbineInstallation
913 |  | Export Cable Installation Vessel | Transit | 3 | 15000 | ACTION | 1016.7619 | ExportCableInstallation
914 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1028 | MooredSubInstallation
915 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1028 | SemiSubStorageInstallation
916 |  | Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 1034 | MooredSubInstallation
917 |  | Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 1034 | SemiSubStorageInstallation
918 |  | Mooring System Installation Vessel | Delay | 41 | 170833.3333 | ACTION | 1044 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
919 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1046 | MooredSubInstallation
920 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1046 | SemiSubStorageInstallation
921 |  | Multi-Purpose Support Vessel | Delay | 37 | 154166.6667 | ACTION | 1046.1667 | MooredSubInstallation
922 |  | Multi-Purpose Support Vessel | Delay | 37 | 154166.6667 | ACTION | 1046.1667 | SemiSubStorageInstallation
923 |  | WTIV | Delay | 30 | 625000 | ACTION | 1046.3914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
924 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1047.7114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
925 |  | Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 1051.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
926 |  | Export Cable Installation Vessel | Delay | 35 | 175000 | ACTION | 1051.7619 | ExportCableInstallation
927 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1052.1667 | MooredSubInstallation
928 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1052.1667 | SemiSubStorageInstallation
929 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1053.7114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
930 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1054.7114 | TurbineInstallation
931 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1055.7114 | TurbineInstallation
932 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1057.0314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
933 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1057.0592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
934 |  | Export Cable Installation Vessel | Transit | 5.6957 | 28478.2609 | ACTION | 1057.4575 | ExportCableInstallation
935 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1058 | MooredSubInstallation
936 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1058 | SemiSubStorageInstallation
937 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1059.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
938 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1060.5314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
939 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1061.5314 | TurbineInstallation
940 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1062.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
941 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1062.8514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
942 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1063.4575 | ExportCableInstallation |  |  |  | ExportCableInstallation
943 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1064 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
944 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1064.5592 | ArrayCableInstallation
945 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1065 | MooredSubInstallation
946 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1065 | SemiSubStorageInstallation
947 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1065.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
948 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1066.3514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
949 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1067.3514 | TurbineInstallation
950 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1068.5 | MooredSubInstallation
951 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1068.5 | SemiSubStorageInstallation
952 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1068.6714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
953 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1071.0592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
954 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1072 | MooredSubInstallation
955 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1072 | SemiSubStorageInstallation
956 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 1072.1532 | ExportCableInstallation
957 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1072.1714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
958 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1074 | MooringSystemInstallation
959 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1074.1532 | ExportCableInstallation
960 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1074.1667 | MooredSubInstallation
961 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1074.1667 | SemiSubStorageInstallation
962 |  | Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 1074.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation
963 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1075.5 | MooredSubInstallation
964 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1075.5 | SemiSubStorageInstallation
965 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 1076.1667 | MooredSubInstallation
966 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 1076.1667 | SemiSubStorageInstallation
967 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1076.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
968 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1077.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
969 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1079 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
970 |  | Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 1079.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
971 |  | WTIV | Transit | 8 | 166666.6667 | ACTION | 1080.1714 | TurbineInstallation
972 |  | Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 1081 | MooringSystemInstallation
973 |  | Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 1082 | MooringSystemInstallation
974 |  | Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 1086 | MooringSystemInstallation
975 |  | Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 1089 | MooringSystemInstallation
976 |  | Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 1089.5 | MooredSubInstallation
977 |  | Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 1089.5 | SemiSubStorageInstallation
978 |  | WTIV | Delay | 10 | 208333.3333 | ACTION | 1090.1714 | TurbineInstallation
979 |  | Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 1093 | MooringSystemInstallation
980 |  | WTIV | Transit | 3 | 62500 | ACTION | 1093.1714 | TurbineInstallation
981 |  | WTIV | Delay | 1 | 20833.3333 | ACTION | 1094.1714 | TurbineInstallation
982 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1095 | MooringSystemInstallation
983 |  | Multi-Purpose Support Vessel | Delay | 19 | 79166.6667 | ACTION | 1095.1667 | MooredSubInstallation
984 |  | Multi-Purpose Support Vessel | Delay | 19 | 79166.6667 | ACTION | 1095.1667 | SemiSubStorageInstallation
985 |  | WTIV | Transit | 3.2857 | 68452.381 | ACTION | 1097.4571 | TurbineInstallation
986 |  | Array Cable Installation Vessel | Delay | 18 | 90000 | ACTION | 1097.5592 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
987 |  | Export Cable Installation Vessel | Delay | 23 | 115000 | ACTION | 1097.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation
988 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1099 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
989 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1101.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
990 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 10 | 41666.6667 | ACTION | 1105.1667 | MooredSubInstallation
991 |  | Towing Group 1 | Positioning Support | 98 | 245000 | ACTION | 1105.1667 | MooredSubInstallation | site | [6 empty] | 2
992 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 10 | 41666.6667 | ACTION | 1105.1667 | SemiSubStorageInstallation
993 |  | Towing Group 1 | Positioning Support | 98 | 245000 | ACTION | 1105.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
994 |  | Array Cable Installation Vessel | Lay/Bury Cable | 7.7665 | 38832.5638 | ACTION | 1105.3258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
995 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1105.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
996 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1106.3258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
997 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1109.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
998 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1110.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
999 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1111.8258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1000 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1112.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1001 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1113.5 | MooredSubInstallation
1002 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1113.5 | SemiSubStorageInstallation
1003 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1113.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1004 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1114.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1005 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1117.3258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1006 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1117.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1007 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1119 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1008 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1119.3258 | ArrayCableInstallation
1009 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1120.3258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1010 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1121 | MooringSystemInstallation
1011 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1121.8333 | MooredSubInstallation | [7 empty] | 3
1012 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1121.8333 | SemiSubStorageInstallation | [7 empty] | 3
1013 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1121.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1014 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1125 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1015 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1125.8258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1016 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1125.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1017 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1127.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1018 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1127.8333 | MooredSubInstallation | [7 empty] | 3
1019 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1127.8333 | SemiSubStorageInstallation | [7 empty] | 3
1020 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1128.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1021 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1130.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1022 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1131.3258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1023 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1132.3258 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1024 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1140.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1025 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1142.0923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1026 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1143.0923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1027 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1144.5 | MooredSubInstallation | [7 empty] | 3
1028 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 1144.5 | MooredSubInstallation | Site
1029 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1144.5 | SemiSubStorageInstallation | [7 empty] | 3
1030 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 1144.5 | SemiSubStorageInstallation | Site
1031 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 1144.7429 | TurbineInstallation
1032 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1145 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1033 |  | Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 1145.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation
1034 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1146.5 | MooredSubInstallation
1035 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1146.5 | SemiSubStorageInstallation
1036 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1146.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation
1037 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1146.7429 | TurbineInstallation
1038 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1147 | MooringSystemInstallation
1039 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1148.5923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1040 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1149.7429 | TurbineInstallation
1041 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1150.4029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1042 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1151 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1043 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1152.5 | MooredSubInstallation
1044 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1152.5 | SemiSubStorageInstallation
1045 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1154.0923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1046 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1156.0923 | ArrayCableInstallation
1047 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1156.4029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1048 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1157.0923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1049 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1159.4029 | TurbineInstallation
1050 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1160.7229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1051 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1162.5923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1052 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 1163.5 | MooredSubInstallation
1053 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 1163.5 | SemiSubStorageInstallation
1054 |  | Export Cable Installation Vessel | Lay/Bury Cable | 18 | 90000 | ACTION | 1164.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1055 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1166.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1056 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1176 | MooredSubInstallation
1057 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 62.5 | 0 | ACTION | 1176 | MooredSubInstallation
1058 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1176 | SemiSubStorageInstallation
1059 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 62.5 | 0 | ACTION | 1176 | SemiSubStorageInstallation
1060 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1184 | MooredSubInstallation
1061 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1184 | SemiSubStorageInstallation
1062 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1196 | MooredSubInstallation
1063 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1196 | SemiSubStorageInstallation
1064 |  | Mooring System Installation Vessel | Delay | 66 | 275000 | ACTION | 1232.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1065 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1237 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1066 |  | Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 1238 | MooredSubInstallation
1067 |  | Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 1238 | SemiSubStorageInstallation
1068 |  | Multi-Purpose Support Vessel | Delay | 75 | 312500 | ACTION | 1238.5 | MooredSubInstallation
1069 |  | Multi-Purpose Support Vessel | Delay | 75 | 312500 | ACTION | 1238.5 | SemiSubStorageInstallation
1070 |  | WTIV | Delay | 78 | 1625000 | ACTION | 1238.7229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1071 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1239 | MooringSystemInstallation
1072 |  | Export Cable Installation Vessel | Delay | 76 | 380000 | ACTION | 1240.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1073 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1241.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1074 |  | Array Cable Installation Vessel | Delay | 80 | 400000 | ACTION | 1242.5923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1075 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1242.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1076 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1243 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1077 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1244.7229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1078 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1247.7229 | TurbineInstallation
1079 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1248.0923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1080 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1248.7229 | TurbineInstallation
1081 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1249.0923 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1082 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 1249.5 | MooredSubInstallation
1083 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 1249.5 | SemiSubStorageInstallation
1084 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1250 | MooredSubInstallation
1085 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1250 | SemiSubStorageInstallation
1086 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1250.0429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1087 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1256.0429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1088 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1257.0429 | TurbineInstallation
1089 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1258.0429 | TurbineInstallation
1090 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1258.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1091 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1258.8588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1092 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1259.3629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1093 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1259.8588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1094 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1261.5 | MooredSubInstallation
1095 |  | Towing Group 1 | Positioning Support | 117 | 292500 | ACTION | 1261.5 | MooredSubInstallation | site | [6 empty] | 2
1096 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1261.5 | SemiSubStorageInstallation
1097 |  | Towing Group 1 | Positioning Support | 117 | 292500 | ACTION | 1261.5 | SemiSubStorageInstallation | site | [6 empty] | 2
1098 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1262 | MooredSubInstallation
1099 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1262 | SemiSubStorageInstallation
1100 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1262.8629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1101 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1263 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1102 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1263.8629 | TurbineInstallation
1103 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1265.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1104 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1265.3588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1105 |  | Export Cable Installation Vessel | Lay/Bury Cable | 26 | 130000 | ACTION | 1268.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1106 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1269 | MooredSubInstallation
1107 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1269 | SemiSubStorageInstallation
1108 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1273 | MooringSystemInstallation
1109 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1278.1667 | MooredSubInstallation | [7 empty] | 3
1110 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1278.1667 | SemiSubStorageInstallation | [7 empty] | 3
1111 |  | Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 1281 | MooredSubInstallation
1112 |  | Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 1281 | SemiSubStorageInstallation
1113 |  | Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 1284 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1114 |  | WTIV | Delay | 19 | 395833.3333 | ACTION | 1284.1829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1115 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1284.5 | MooredSubInstallation
1116 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1284.5 | SemiSubStorageInstallation
1117 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1287.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1118 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1288 | MooredSubInstallation
1119 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1288 | SemiSubStorageInstallation
1120 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1288.6829 | TurbineInstallation
1121 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1289 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1122 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1290.0029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1123 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1291.5 | MooredSubInstallation
1124 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1291.5 | SemiSubStorageInstallation
1125 |  | WTIV | Delay | 3 | 62500 | ACTION | 1293.0029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1126 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1296.5029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1127 |  | Export Cable Installation Vessel | Delay | 28 | 140000 | ACTION | 1296.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1128 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1297.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1129 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1298.5029 | TurbineInstallation
1130 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1298.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1131 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1299 | MooringSystemInstallation
1132 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1299.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1133 |  | Array Cable Installation Vessel | Delay | 35 | 175000 | ACTION | 1300.3588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1134 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1300.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1135 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1301 | MooringSystemInstallation
1136 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1301.5029 | TurbineInstallation
1137 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1302.1629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1138 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1305 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1139 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1305.8588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1140 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1307.8588 | ArrayCableInstallation
1141 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1308.1629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1142 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1308.8588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1143 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1311.1629 | TurbineInstallation
1144 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1312.4829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1145 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1314.3588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1146 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1315.5 | MooredSubInstallation
1147 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 37.3333 | 46666.6667 | ACTION | 1315.5 | MooredSubInstallation
1148 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1315.5 | SemiSubStorageInstallation
1149 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 37.3333 | 46666.6667 | ACTION | 1315.5 | SemiSubStorageInstallation
1150 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1318.4829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1151 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1319.8588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1152 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1320.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1153 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1320.8588 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1154 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1321.4829 | TurbineInstallation
1155 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1321.5 | MooredSubInstallation | [7 empty] | 3
1156 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1321.5 | SemiSubStorageInstallation | [7 empty] | 3
1157 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1322.4829 | TurbineInstallation
1158 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1323.8029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1159 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1325 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1160 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1327 | MooringSystemInstallation
1161 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1329.8029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1162 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1330.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1163 |  | Export Cable Installation Vessel | Lay/Bury Cable | 30 | 150000 | ACTION | 1330.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1164 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1330.8029 | TurbineInstallation
1165 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1331 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1166 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1331.8029 | TurbineInstallation
1167 |  | WTIV | Delay | 3 | 62500 | ACTION | 1334.8029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1168 |  | Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 1335.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1169 |  | Export Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 1335.6532 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1170 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1336.1229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1171 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1336.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1172 |  | Export Cable Installation Vessel | Lay/Bury Cable | 2.0416 | 10207.9486 | ACTION | 1337.6948 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1173 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1339.6229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1174 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1339.6948 | ExportCableInstallation
1175 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1340.6229 | TurbineInstallation
1176 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1341.9429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1177 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1342.1253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1178 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1344 | MooredSubInstallation
1179 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 28.5 | 0 | ACTION | 1344 | MooredSubInstallation
1180 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1344 | SemiSubStorageInstallation
1181 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 28.5 | 0 | ACTION | 1344 | SemiSubStorageInstallation
1182 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1345.1948 | ExportCableInstallation |  |  |  | ExportCableInstallation
1183 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1345.4429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1184 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1346.4429 | TurbineInstallation
1185 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1346.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1186 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1347.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1187 |  | WTIV | Delay | 4 | 83333.3333 | ACTION | 1350.4429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1188 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1351 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1189 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1351.7629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1190 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1352 | MooredSubInstallation
1191 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1352 | SemiSubStorageInstallation
1192 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1353 | MooringSystemInstallation
1193 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1355.2629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1194 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1357 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1195 |  | WTIV | Transit | 2 | 41666.6667 | ACTION | 1357.2629 | TurbineInstallation
1196 |  | WTIV | Delay | 1 | 20833.3333 | ACTION | 1358.2629 | TurbineInstallation
1197 |  | Array Cable Installation Vessel | Delay | 16 | 80000 | ACTION | 1363.6253 | ArrayCableInstallation
1198 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1364 | MooredSubInstallation
1199 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1364 | SemiSubStorageInstallation
1200 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1365.6253 | ArrayCableInstallation
1201 |  | Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1366.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1202 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1367.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1203 |  | Export Cable Installation Vessel | Delay | 25 | 125000 | ACTION | 1370.1948 | ExportCableInstallation |  |  |  | ExportCableInstallation
1204 |  | WTIV | Transit | 12.2857 | 255952.381 | ACTION | 1370.5486 | TurbineInstallation
1205 |  | Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 1370.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1206 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1372.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1207 |  | Towing Group 1 | Delay | 53 | 198750 | ACTION | 1374.5 | MooredSubInstallation | [7 empty] | 3
1208 |  | Towing Group 1 | Delay | 53 | 198750 | ACTION | 1374.5 | SemiSubStorageInstallation | [7 empty] | 3
1209 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1374.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1210 |  | Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 1375 | MooredSubInstallation
1211 |  | Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 1375 | SemiSubStorageInstallation
1212 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1375.6948 | ExportCableInstallation |  |  |  | ExportCableInstallation
1213 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1376.1253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1214 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1377 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1215 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1378.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1216 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1379 | MooringSystemInstallation
1217 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1381.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1218 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1382.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1219 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1382.6253 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1220 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1383 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1221 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1384.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1222 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 1384.3904 | ExportCableInstallation
1223 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1385.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1224 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1387 | MooredSubInstallation
1225 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1387 | SemiSubStorageInstallation
1226 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1387.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1227 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1390.3904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1228 |  | Export Cable Installation Vessel | Tow Plow | 0.2 | 1000 | ACTION | 1390.5904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1229 |  | Export Cable Installation Vessel | Pull Winch | 0.2 | 1000 | ACTION | 1390.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1230 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1391.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1231 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1391.1667 | MooredSubInstallation | [7 empty] | 3
1232 |  | Multi-Purpose Support Vessel | Delay | 129.6667 | 540277.7778 | ACTION | 1391.1667 | MooredSubInstallation | Site
1233 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1391.1667 | SemiSubStorageInstallation | [7 empty] | 3
1234 |  | Multi-Purpose Support Vessel | Delay | 129.6667 | 540277.7778 | ACTION | 1391.1667 | SemiSubStorageInstallation | Site
1235 |  | Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1391.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1236 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1392.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1237 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1393.1667 | MooredSubInstallation
1238 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1393.1667 | SemiSubStorageInstallation
1239 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1393.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1240 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1395.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1241 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1397.2904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1242 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1398.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1243 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1398.8918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1244 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1399 | MooredSubInstallation
1245 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1399 | SemiSubStorageInstallation
1246 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1399.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1247 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1399.1667 | MooredSubInstallation
1248 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1399.1667 | SemiSubStorageInstallation
1249 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1400.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1250 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1402.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1251 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1402.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1252 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1403 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1253 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1403.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1254 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1403.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation
1255 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1404.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1256 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1406 | MooredSubInstallation
1257 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1406 | SemiSubStorageInstallation
1258 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1406.3918 | ArrayCableInstallation
1259 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1407.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1260 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 10 | 41666.6667 | ACTION | 1409.1667 | MooredSubInstallation
1261 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 10 | 41666.6667 | ACTION | 1409.1667 | SemiSubStorageInstallation
1262 |  | Export Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 1411.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1263 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1413 | MooringSystemInstallation
1264 |  | WTIV | Transit | 11 | 229166.6667 | ACTION | 1414.5486 | TurbineInstallation
1265 |  | Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 1435 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1266 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1440 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1267 |  | Mooring System Installation Vessel | Transit | 7 | 29166.6667 | ACTION | 1447 | MooringSystemInstallation
1268 |  | Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 1448 | MooringSystemInstallation
1269 |  | WTIV | Delay | 36 | 750000 | ACTION | 1450.5486 | TurbineInstallation
1270 |  | Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 1451 | MooringSystemInstallation
1271 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1453 | MooringSystemInstallation
1272 |  | WTIV | Transit | 3.2857 | 68452.381 | ACTION | 1453.8343 | TurbineInstallation
1273 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1455.8343 | TurbineInstallation
1274 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1457 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1275 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1472.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1276 |  | WTIV | Delay | 19 | 395833.3333 | ACTION | 1474.8343 | TurbineInstallation
1277 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1477 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1278 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1477.8343 | TurbineInstallation
1279 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1479 | MooringSystemInstallation
1280 |  | Multi-Purpose Support Vessel | Delay | 70 | 291666.6667 | ACTION | 1479.1667 | MooredSubInstallation
1281 |  | Multi-Purpose Support Vessel | Delay | 70 | 291666.6667 | ACTION | 1479.1667 | SemiSubStorageInstallation
1282 |  | WTIV | Delay | 2 | 41666.6667 | ACTION | 1479.8343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1283 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1480.4943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1284 |  | Export Cable Installation Vessel | Delay | 70 | 350000 | ACTION | 1481.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1285 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1482.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1286 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1483 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1287 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1483.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1288 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1484.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1289 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 7 | 29166.6667 | ACTION | 1486.1667 | MooredSubInstallation
1290 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 7 | 29166.6667 | ACTION | 1486.1667 | SemiSubStorageInstallation
1291 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1486.4943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1292 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1489.4943 | TurbineInstallation
1293 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 1492.1667 | MooredSubInstallation
1294 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 1492.1667 | SemiSubStorageInstallation
1295 |  | WTIV | Delay | 3 | 62500 | ACTION | 1492.4943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1296 |  | Export Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 1492.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1297 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1493.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1298 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1493.8143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1299 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1494.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1300 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 1496.1667 | MooredSubInstallation
1301 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 1496.1667 | SemiSubStorageInstallation
1302 |  | Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 1497.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1303 |  | Array Cable Installation Vessel | Delay | 91 | 455000 | ACTION | 1498.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1304 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1498.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1305 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1498.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1306 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1503 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1307 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1503.8918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1308 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1505 | MooringSystemInstallation
1309 |  | Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 1505.1667 | MooredSubInstallation
1310 |  | Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 1505.1667 | SemiSubStorageInstallation
1311 |  | WTIV | Delay | 12 | 250000 | ACTION | 1505.8143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1312 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 1506.1667 | MooredSubInstallation
1313 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 1506.1667 | SemiSubStorageInstallation
1314 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1509 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1315 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1509.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1316 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1510.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1317 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1511.8143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1318 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1512 | MooredSubInstallation
1319 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1512 | SemiSubStorageInstallation
1320 |  | Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 1513.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1321 |  | Export Cable Installation Vessel | Lay/Bury Cable | 15 | 75000 | ACTION | 1513.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1322 |  | Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1514.3918 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1323 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1514.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1324 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1514.8143 | TurbineInstallation
1325 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1515.8143 | TurbineInstallation
1326 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1517.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1327 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1518.1667 | MooredSubInstallation
1328 |  | Towing Group 1 | Positioning Support | 127 | 317500 | ACTION | 1518.1667 | MooredSubInstallation | site | [6 empty] | 2
1329 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1518.1667 | SemiSubStorageInstallation
1330 |  | Towing Group 1 | Positioning Support | 127 | 317500 | ACTION | 1518.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
1331 |  | Array Cable Installation Vessel | Lay/Bury Cable | 6.7665 | 33832.5638 | ACTION | 1521.1583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1332 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1522.1583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1333 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1523.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1334 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1524.1343 | TurbineInstallation
1335 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1524.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1336 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1525.1343 | TurbineInstallation
1337 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1526.4543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1338 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1527.6583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1339 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1529 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1340 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1529.9543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1341 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1530.9543 | TurbineInstallation
1342 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1531 | MooringSystemInstallation
1343 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1532.2743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1344 |  | Turbine Assembly Line 1 | Delay | 127 | 0 | ACTION | 1533 | MooredSubInstallation
1345 |  | Turbine Assembly Line 1 | Delay | 127 | 0 | ACTION | 1533 | SemiSubStorageInstallation
1346 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1533.1583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1347 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1534.8333 | MooredSubInstallation | [7 empty] | 3
1348 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1534.8333 | SemiSubStorageInstallation | [7 empty] | 3
1349 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1535 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1350 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1535.1583 | ArrayCableInstallation
1351 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1535.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1352 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1536.1583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1353 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1536.5 | MooredSubInstallation
1354 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1536.5 | SemiSubStorageInstallation
1355 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1536.7743 | TurbineInstallation
1356 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1538.0943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1357 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1540 | MooredSubInstallation
1358 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1540 | SemiSubStorageInstallation
1359 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1541.5943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1360 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1541.6583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1361 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1543.5 | MooredSubInstallation
1362 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1543.5 | SemiSubStorageInstallation
1363 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1543.5943 | TurbineInstallation
1364 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1546.5943 | TurbineInstallation
1365 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1547.1583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1366 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1547.2543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1367 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1548.1583 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1368 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1550.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1369 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1553.2543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1370 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1555 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1371 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1556.2543 | TurbineInstallation
1372 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1557.5743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1373 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1557.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1374 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1558.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1375 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1563.5743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1376 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1564.4248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1377 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1565 | MooringSystemInstallation
1378 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1566.5743 | TurbineInstallation
1379 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1567.5 | MooredSubInstallation
1380 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 32.6667 | 40833.3333 | ACTION | 1567.5 | MooredSubInstallation
1381 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1567.5 | SemiSubStorageInstallation
1382 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 32.6667 | 40833.3333 | ACTION | 1567.5 | SemiSubStorageInstallation
1383 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1567.5743 | TurbineInstallation
1384 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1568.8943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1385 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1569.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1386 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1570 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1387 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1571.9248 | ArrayCableInstallation
1388 |  | Export Cable Installation Vessel | Lay/Bury Cable | 58 | 290000 | ACTION | 1572.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1389 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1572.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1390 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1573.5 | MooredSubInstallation | [7 empty] | 3
1391 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1573.5 | SemiSubStorageInstallation | [7 empty] | 3
1392 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1574.8943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1393 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1575.5 | MooredSubInstallation
1394 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1575.5 | SemiSubStorageInstallation
1395 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1575.8943 | TurbineInstallation
1396 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1576.8943 | TurbineInstallation
1397 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1580 | MooringSystemInstallation
1398 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1582 | MooringSystemInstallation
1399 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1586 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1400 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1587.5 | MooredSubInstallation
1401 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1587.5 | SemiSubStorageInstallation
1402 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 1600.5 | MooredSubInstallation
1403 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 1600.5 | SemiSubStorageInstallation
1404 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1612.5 | MooredSubInstallation
1405 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1612.5 | SemiSubStorageInstallation
1406 |  | Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 1617 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1407 |  | WTIV | Delay | 43 | 895833.3333 | ACTION | 1619.8943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1408 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1621.2143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1409 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1624.5 | MooredSubInstallation
1410 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1624.5 | SemiSubStorageInstallation
1411 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1624.7143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1412 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1625.7143 | TurbineInstallation
1413 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1627.0343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1414 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1632.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1415 |  | Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 1660.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1416 |  | Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 1664.5 | MooredSubInstallation
1417 |  | Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 1664.5 | SemiSubStorageInstallation
1418 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1665 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1419 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1667 | MooringSystemInstallation
1420 |  | WTIV | Delay | 43 | 895833.3333 | ACTION | 1670.0343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1421 |  | Towing Group 1 | Delay | 97 | 363750 | ACTION | 1670.5 | MooredSubInstallation | [7 empty] | 3
1422 |  | Towing Group 1 | Delay | 97 | 363750 | ACTION | 1670.5 | SemiSubStorageInstallation | [7 empty] | 3
1423 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1671 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1424 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1671.5 | MooredSubInstallation
1425 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1671.5 | SemiSubStorageInstallation
1426 |  | Export Cable Installation Vessel | Delay | 100 | 500000 | ACTION | 1672.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1427 |  | Array Cable Installation Vessel | Delay | 100 | 500000 | ACTION | 1672.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1428 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1673.5343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1429 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1674.5343 | TurbineInstallation
1430 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1675 | MooredSubInstallation
1431 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1675 | SemiSubStorageInstallation
1432 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1675.8543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1433 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1678.4248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1434 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1678.5 | MooredSubInstallation
1435 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1678.5 | SemiSubStorageInstallation
1436 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1679.3543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1437 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1680 | MooredSubInstallation
1438 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1680 | SemiSubStorageInstallation
1439 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1682 | MooredSubInstallation
1440 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1682 | SemiSubStorageInstallation
1441 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1683.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1442 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1684.9248 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1443 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1686.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1444 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1687.1667 | MooredSubInstallation | [7 empty] | 3
1445 |  | Multi-Purpose Support Vessel | Delay | 169 | 704166.6667 | ACTION | 1687.1667 | MooredSubInstallation | Site
1446 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1687.1667 | SemiSubStorageInstallation | [7 empty] | 3
1447 |  | Multi-Purpose Support Vessel | Delay | 169 | 704166.6667 | ACTION | 1687.1667 | SemiSubStorageInstallation | Site
1448 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1689.1667 | MooredSubInstallation
1449 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1689.1667 | SemiSubStorageInstallation
1450 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1691 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1451 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1693 | MooringSystemInstallation
1452 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 1693.64 | TurbineInstallation
1453 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1694.6913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1454 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1695.1667 | MooredSubInstallation
1455 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1695.1667 | SemiSubStorageInstallation
1456 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1695.6913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1457 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1697 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1458 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1697.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1459 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1701.1913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1460 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1701.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1461 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1705.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1462 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1706 | MooredSubInstallation
1463 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1706 | SemiSubStorageInstallation
1464 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1706.6913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1465 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1707.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1466 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1708.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1467 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1708.6913 | ArrayCableInstallation
1468 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1709.6913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1469 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1710.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1470 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1712.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1471 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1714 | MooredSubInstallation
1472 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1714 | SemiSubStorageInstallation
1473 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1714.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1474 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1715.1913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1475 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1717 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1476 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1717.1667 | MooredSubInstallation
1477 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1717.1667 | SemiSubStorageInstallation
1478 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1718.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1479 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1719 | MooringSystemInstallation
1480 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1720.6913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1481 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1721.6913 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1482 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1722.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1483 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1723 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1484 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1723.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1485 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1725.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1486 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1726 | MooredSubInstallation
1487 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1726 | SemiSubStorageInstallation
1488 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1726.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1489 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1729.1667 | MooredSubInstallation
1490 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 1729.1667 | MooredSubInstallation | site | [6 empty] | 2
1491 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1729.1667 | SemiSubStorageInstallation
1492 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 1729.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
1493 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1731.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1494 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1732.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1495 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1737.9579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1496 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1738 | MooredSubInstallation
1497 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1738 | SemiSubStorageInstallation
1498 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1738.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1499 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 1740.9257 | TurbineInstallation
1500 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1742.9257 | TurbineInstallation
1501 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1743 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1502 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1743.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1503 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1745.4579 | ArrayCableInstallation
1504 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1745.8333 | MooredSubInstallation | [7 empty] | 3
1505 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1745.8333 | SemiSubStorageInstallation | [7 empty] | 3
1506 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1745.9257 | TurbineInstallation
1507 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1746.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1508 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1746.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1509 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1750 | MooredSubInstallation
1510 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1750 | SemiSubStorageInstallation
1511 |  | Export Cable Installation Vessel | Lay/Bury Cable | 79 | 395000 | ACTION | 1751.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1512 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1751.8333 | MooredSubInstallation | [7 empty] | 3
1513 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1751.8333 | SemiSubStorageInstallation | [7 empty] | 3
1514 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1753 | MooringSystemInstallation
1515 |  | Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 1780 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1516 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1785 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1517 |  | WTIV | Delay | 40 | 833333.3333 | ACTION | 1786.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1518 |  | Towing Group 1 | Delay | 35 | 131250 | ACTION | 1786.8333 | MooredSubInstallation | [7 empty] | 3
1519 |  | Towing Group 1 | Delay | 35 | 131250 | ACTION | 1786.8333 | SemiSubStorageInstallation | [7 empty] | 3
1520 |  | Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 1787 | MooredSubInstallation
1521 |  | Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 1787 | SemiSubStorageInstallation
1522 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1792.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1523 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1794 | MooredSubInstallation
1524 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1794 | SemiSubStorageInstallation
1525 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1795 | MooringSystemInstallation
1526 |  | Array Cable Installation Vessel | Delay | 49 | 245000 | ACTION | 1795.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1527 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1795.5857 | TurbineInstallation
1528 |  | Export Cable Installation Vessel | Delay | 44 | 220000 | ACTION | 1795.7904 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1529 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1796.9057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1530 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1797 | MooringSystemInstallation
1531 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1797.5 | MooredSubInstallation
1532 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1797.5 | SemiSubStorageInstallation
1533 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1800.9579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1534 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1801 | MooredSubInstallation
1535 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1801 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1536 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1801 | SemiSubStorageInstallation
1537 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1802.9057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1538 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1803.5 | MooredSubInstallation | [7 empty] | 3
1539 |  | Multi-Purpose Support Vessel | Delay | 74.3333 | 309722.2222 | ACTION | 1803.5 | MooredSubInstallation | Site
1540 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1803.5 | SemiSubStorageInstallation | [7 empty] | 3
1541 |  | Multi-Purpose Support Vessel | Delay | 74.3333 | 309722.2222 | ACTION | 1803.5 | SemiSubStorageInstallation | Site
1542 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1804.5 | MooredSubInstallation
1543 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1804.5 | SemiSubStorageInstallation
1544 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1805.5 | MooredSubInstallation
1545 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1805.5 | SemiSubStorageInstallation
1546 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1805.9057 | TurbineInstallation
1547 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1806.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1548 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1806.9057 | TurbineInstallation
1549 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1807.4579 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1550 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1808.2257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1551 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1811.5 | MooredSubInstallation
1552 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1811.5 | SemiSubStorageInstallation
1553 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1814.2257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1554 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1815.2257 | TurbineInstallation
1555 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1816.2257 | TurbineInstallation
1556 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1816.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1557 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1817.2244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1558 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1817.5457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1559 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1818.2244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1560 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1821 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1561 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1821.0457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1562 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1822.0457 | TurbineInstallation
1563 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1823 | MooringSystemInstallation
1564 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1823.3657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1565 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1823.7244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1566 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1826.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1567 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1827 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1568 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1827.8657 | TurbineInstallation
1569 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1828.5 | MooredSubInstallation
1570 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1828.5 | SemiSubStorageInstallation
1571 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1829.1857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1572 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1829.2244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1573 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1831.2244 | ArrayCableInstallation
1574 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1832.2244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1575 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1832.6857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1576 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1833.5 | MooredSubInstallation
1577 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1833.5 | SemiSubStorageInstallation
1578 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1834.6857 | TurbineInstallation
1579 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1837.6857 | TurbineInstallation
1580 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1837.7244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1581 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1838.3457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1582 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1842.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1583 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1843.2244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1584 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1844.2244 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1585 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1844.3457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1586 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1845.5 | MooredSubInstallation
1587 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 1845.5 | MooredSubInstallation | site | [6 empty] | 2
1588 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1845.5 | SemiSubStorageInstallation
1589 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 1845.5 | SemiSubStorageInstallation | site | [6 empty] | 2
1590 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1847 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1591 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1847.3457 | TurbineInstallation
1592 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1848 | MooredSubInstallation
1593 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 19.5 | 0 | ACTION | 1848 | MooredSubInstallation
1594 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 1848 | SemiSubStorageInstallation
1595 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 19.5 | 0 | ACTION | 1848 | SemiSubStorageInstallation
1596 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1848.6657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1597 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1849 | MooringSystemInstallation
1598 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1853 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1599 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1853.9909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1600 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1854.6657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1601 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1854.9909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1602 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1856 | MooredSubInstallation
1603 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 1856 | SemiSubStorageInstallation
1604 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1857.6657 | TurbineInstallation
1605 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1858.6657 | TurbineInstallation
1606 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1859.9857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1607 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1860.4909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1608 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1862.1667 | MooredSubInstallation | [7 empty] | 3
1609 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1862.1667 | SemiSubStorageInstallation | [7 empty] | 3
1610 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1865.9857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1611 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1865.9909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1612 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1866.9857 | TurbineInstallation
1613 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1867.9857 | TurbineInstallation
1614 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1867.9909 | ArrayCableInstallation
1615 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1868 | MooredSubInstallation
1616 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 1868 | SemiSubStorageInstallation
1617 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1868.1667 | MooredSubInstallation | [7 empty] | 3
1618 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1868.1667 | SemiSubStorageInstallation | [7 empty] | 3
1619 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1868.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1620 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1868.9909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1621 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1869.3057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1622 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1872.8057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1623 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1873 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1624 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1873.8057 | TurbineInstallation
1625 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1874.4909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1626 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1875 | MooringSystemInstallation
1627 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1875.1257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1628 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1878.6257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1629 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1879 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1630 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1879.6257 | TurbineInstallation
1631 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1879.9909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1632 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1880 | MooredSubInstallation
1633 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1880 | SemiSubStorageInstallation
1634 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1880.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1635 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1880.9909 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1636 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1884.4457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1637 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1884.8333 | MooredSubInstallation | [7 empty] | 3
1638 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 1884.8333 | MooredSubInstallation | Site
1639 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1884.8333 | SemiSubStorageInstallation | [7 empty] | 3
1640 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 1884.8333 | SemiSubStorageInstallation | Site
1641 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1886.8333 | MooredSubInstallation
1642 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1886.8333 | SemiSubStorageInstallation
1643 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1890.7574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1644 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1891.7574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1645 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1892 | MooredSubInstallation
1646 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 1892 | SemiSubStorageInstallation
1647 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1892.8333 | MooredSubInstallation
1648 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1892.8333 | SemiSubStorageInstallation
1649 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1894.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1650 |  | Export Cable Installation Vessel | Lay/Bury Cable | 100.6667 | 503333.3333 | ACTION | 1896.4571 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1651 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1897.2574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1652 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 1898.7314 | TurbineInstallation
1653 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1899 | MooredSubInstallation
1654 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1899 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1655 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 1899 | SemiSubStorageInstallation
1656 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1902.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1657 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1902.7574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1658 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1904.7574 | ArrayCableInstallation
1659 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 1905.1527 | ExportCableInstallation
1660 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1905.7574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1661 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1906.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1662 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1909 | MooringSystemInstallation
1663 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1910.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1664 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1911.1527 | ExportCableInstallation |  |  |  | ExportCableInstallation
1665 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1911.2574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1666 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1912.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1667 |  | Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 1913 | MooredSubInstallation
1668 |  | Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 1913 | SemiSubStorageInstallation
1669 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1913.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1670 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1914 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1671 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1914.8333 | MooredSubInstallation
1672 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1914.8333 | SemiSubStorageInstallation
1673 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1915.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1674 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1916.5 | MooredSubInstallation
1675 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1916.5 | SemiSubStorageInstallation
1676 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1916.7574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1677 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1917.7574 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1678 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1919.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1679 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 1919.8484 | ExportCableInstallation
1680 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1920 | MooredSubInstallation
1681 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1920 | SemiSubStorageInstallation
1682 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1921.8484 | ExportCableInstallation
1683 |  | Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 1922.3484 | ExportCableInstallation |  |  |  | ExportCableInstallation
1684 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 1923.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1685 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1924 | MooringSystemInstallation
1686 |  | Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 1925 | MooredSubInstallation
1687 |  | Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 1925 | SemiSubStorageInstallation
1688 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1926 | MooringSystemInstallation
1689 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1926.8333 | MooredSubInstallation
1690 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 1926.8333 | MooredSubInstallation | site | [6 empty] | 2
1691 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1926.8333 | SemiSubStorageInstallation
1692 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 1926.8333 | SemiSubStorageInstallation | site | [6 empty] | 2
1693 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 1927.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1694 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1927.5239 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1695 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1928.5 | MooredSubInstallation
1696 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 1928.5 | SemiSubStorageInstallation
1697 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1928.5239 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1698 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1928.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1699 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1930 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1700 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1930.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1701 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 1931.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1702 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1934.0239 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1703 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1939.5239 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1704 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1943.5 | MooredSubInstallation | [7 empty] | 3
1705 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 1943.5 | SemiSubStorageInstallation | [7 empty] | 3
1706 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1945.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1707 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 1946.0171 | TurbineInstallation
1708 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 1948.0171 | TurbineInstallation
1709 |  | Array Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 1948.2196 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1710 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1950 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1711 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1951.0171 | TurbineInstallation
1712 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 1951.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1713 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1952 | MooringSystemInstallation
1714 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1952.5 | MooredSubInstallation
1715 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 9 | 11250 | ACTION | 1952.5 | MooredSubInstallation
1716 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 1952.5 | SemiSubStorageInstallation
1717 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 9 | 11250 | ACTION | 1952.5 | SemiSubStorageInstallation
1718 |  | Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1954.2196 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1719 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1956 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1720 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1957.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1721 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1958.5 | MooredSubInstallation | [7 empty] | 3
1722 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 1958.5 | SemiSubStorageInstallation | [7 empty] | 3
1723 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 1960.6771 | TurbineInstallation
1724 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 1961.9971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1725 |  | Array Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 1962.9152 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1726 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1964.9152 | ArrayCableInstallation
1727 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1965.9152 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1728 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 1967.9971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1729 |  | Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 1970.3484 | ExportCableInstallation |  |  |  | ExportCableInstallation
1730 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 1970.9971 | TurbineInstallation
1731 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1971.3484 | ExportCableInstallation |  |  |  | ExportCableInstallation
1732 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1971.4152 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1733 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1971.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1734 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1971.9971 | TurbineInstallation
1735 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 1973.3171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1736 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 1975.1667 | MooredSubInstallation | [7 empty] | 3
1737 |  | Multi-Purpose Support Vessel | Delay | 48.3333 | 201388.8889 | ACTION | 1975.1667 | MooredSubInstallation | Site
1738 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 1975.1667 | SemiSubStorageInstallation | [7 empty] | 3
1739 |  | Multi-Purpose Support Vessel | Delay | 48.3333 | 201388.8889 | ACTION | 1975.1667 | SemiSubStorageInstallation | Site
1740 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 1976 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1741 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1976.9152 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1742 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 1977.1667 | MooredSubInstallation
1743 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 1977.1667 | SemiSubStorageInstallation
1744 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1977.9152 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1745 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1978 | MooringSystemInstallation
1746 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 1979.3171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1747 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 1980.3171 | TurbineInstallation
1748 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1981.3171 | TurbineInstallation
1749 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1982 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1750 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1982.6371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1751 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1983.1667 | MooredSubInstallation
1752 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1983.1667 | SemiSubStorageInstallation
1753 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1986.1371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1754 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1987.1371 | TurbineInstallation
1755 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 1987.6817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1756 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1988.4571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1757 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 1988.6817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1758 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1991.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1759 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 1992.9571 | TurbineInstallation
1760 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 10 | 41666.6667 | ACTION | 1993.1667 | MooredSubInstallation
1761 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 10 | 41666.6667 | ACTION | 1993.1667 | SemiSubStorageInstallation
1762 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 1994.1667 | MooredSubInstallation
1763 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 1994.1667 | SemiSubStorageInstallation
1764 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1994.1817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1765 |  | WTIV | Delay | 2 | 41666.6667 | ACTION | 1994.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1766 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 1996.2771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1767 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 1997.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1768 |  | Export Cable Installation Vessel | Lay/Bury Cable | 27 | 135000 | ACTION | 1998.3484 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1769 |  | Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 1999.1817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1770 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 1999.3484 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1771 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 1999.7771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1772 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2001.7771 | TurbineInstallation
1773 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2002 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1774 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2004 | MooringSystemInstallation
1775 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2004.6817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1776 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2004.7771 | TurbineInstallation
1777 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2005.4371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1778 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 12 | 50000 | ACTION | 2006.1667 | MooredSubInstallation
1779 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 12 | 50000 | ACTION | 2006.1667 | SemiSubStorageInstallation
1780 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2006.6817 | ArrayCableInstallation
1781 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2007.6817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1782 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2008 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1783 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2011.4371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1784 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2013.1817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1785 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2014.4371 | TurbineInstallation
1786 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2015.7571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1787 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2016 | MooredSubInstallation
1788 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 63.5 | 0 | ACTION | 2016 | MooredSubInstallation
1789 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2016 | SemiSubStorageInstallation
1790 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 63.5 | 0 | ACTION | 2016 | SemiSubStorageInstallation
1791 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2018.1667 | MooredSubInstallation
1792 |  | Towing Group 1 | Positioning Support | 43 | 107500 | ACTION | 2018.1667 | MooredSubInstallation | site | [6 empty] | 2
1793 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2018.1667 | SemiSubStorageInstallation
1794 |  | Towing Group 1 | Positioning Support | 43 | 107500 | ACTION | 2018.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
1795 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2018.6817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1796 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2019.6817 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1797 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2021.7571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1798 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2023.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1799 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2024 | MooredSubInstallation
1800 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2024 | SemiSubStorageInstallation
1801 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2024.7571 | TurbineInstallation
1802 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2025.7571 | TurbineInstallation
1803 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2027.0771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1804 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2028 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1805 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2029.4482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1806 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2030.4482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1807 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2033.0771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1808 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2034.0771 | TurbineInstallation
1809 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2034.8333 | MooredSubInstallation | [7 empty] | 3
1810 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2034.8333 | SemiSubStorageInstallation | [7 empty] | 3
1811 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2035.0771 | TurbineInstallation
1812 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2035.9482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1813 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2036 | MooredSubInstallation
1814 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2036 | SemiSubStorageInstallation
1815 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2036.3971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1816 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2038 | MooringSystemInstallation
1817 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2039.8971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1818 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2040.8971 | TurbineInstallation
1819 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2041.4482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1820 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2042.2171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1821 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2043 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1822 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2043.4482 | ArrayCableInstallation
1823 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2044.4482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1824 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2045.7171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1825 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2046.7171 | TurbineInstallation
1826 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2048 | MooredSubInstallation
1827 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2048 | SemiSubStorageInstallation
1828 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2048.0371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1829 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2049.9482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1830 |  | Export Cable Installation Vessel | Lay/Bury Cable | 52.0416 | 260207.9486 | ACTION | 2051.39 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1831 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2051.5371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1832 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2053 | MooringSystemInstallation
1833 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2053.39 | ExportCableInstallation
1834 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2055 | MooringSystemInstallation
1835 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2055.4482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1836 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2056.4482 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1837 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2058.89 | ExportCableInstallation |  |  |  | ExportCableInstallation
1838 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2059 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1839 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2060 | MooredSubInstallation
1840 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2060 | SemiSubStorageInstallation
1841 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2064.39 | ExportCableInstallation |  |  |  | ExportCableInstallation
1842 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2065.8229 | TurbineInstallation
1843 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2066.2147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1844 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2067 | MooredSubInstallation
1845 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2067 | SemiSubStorageInstallation
1846 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2067.2147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1847 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2069.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1848 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2070.5 | MooredSubInstallation
1849 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2070.5 | SemiSubStorageInstallation
1850 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2072.7147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1851 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 2073.0856 | ExportCableInstallation
1852 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2073.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1853 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2074 | MooredSubInstallation
1854 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2074 | SemiSubStorageInstallation
1855 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2074.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1856 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2077.5 | MooredSubInstallation
1857 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2077.5 | SemiSubStorageInstallation
1858 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2077.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1859 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2078.2147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1860 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2079 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1861 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 2079.0856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1862 |  | Export Cable Installation Vessel | Tow Plow | 0.2 | 1000 | ACTION | 2079.2856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1863 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2079.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1864 |  | Export Cable Installation Vessel | Pull Winch | 0.2 | 1000 | ACTION | 2079.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1865 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2080.2147 | ArrayCableInstallation
1866 |  | Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2080.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1867 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2080.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1868 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2081 | MooringSystemInstallation
1869 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2081.2147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1870 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2082.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1871 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2085 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1872 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2085.9856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1873 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2086.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1874 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2086.7147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1875 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2090.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1876 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2091.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1877 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2092.2147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1878 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2092.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation
1879 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2093.2147 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1880 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2094.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1881 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2095.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1882 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2097.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1883 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2098.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1884 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2100.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1885 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2101.5 | MooredSubInstallation
1886 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 66.6667 | 83333.3333 | ACTION | 2101.5 | MooredSubInstallation
1887 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2101.5 | SemiSubStorageInstallation
1888 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 66.6667 | 83333.3333 | ACTION | 2101.5 | SemiSubStorageInstallation
1889 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2102.9813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1890 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2103.9813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1891 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2105 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1892 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2107 | MooringSystemInstallation
1893 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2107.5 | MooredSubInstallation | [7 empty] | 3
1894 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2107.5 | SemiSubStorageInstallation | [7 empty] | 3
1895 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2109.4813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1896 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2111 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1897 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2113.1086 | TurbineInstallation
1898 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2114.9813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1899 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2115.1086 | TurbineInstallation
1900 |  | Export Cable Installation Vessel | Lay/Bury Cable | 23 | 115000 | ACTION | 2115.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1901 |  | Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 2134 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1902 |  | WTIV | Delay | 22 | 458333.3333 | ACTION | 2137.1086 | TurbineInstallation
1903 |  | Towing Group 1 | Delay | 30 | 112500 | ACTION | 2137.5 | MooredSubInstallation | [7 empty] | 3
1904 |  | Towing Group 1 | Delay | 30 | 112500 | ACTION | 2137.5 | SemiSubStorageInstallation | [7 empty] | 3
1905 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2140.1086 | TurbineInstallation
1906 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2140.7686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1907 |  | Export Cable Installation Vessel | Delay | 27 | 135000 | ACTION | 2142.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1908 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2143.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1909 |  | Export Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 2145.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
1910 |  | Array Cable Installation Vessel | Delay | 31 | 155000 | ACTION | 2145.9813 | ArrayCableInstallation
1911 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2146.7686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1912 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2147.9813 | ArrayCableInstallation
1913 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2148.9813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1914 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2149.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1915 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2149.7686 | TurbineInstallation
1916 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2151.0886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1917 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2154 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1918 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 2154.1667 | MooredSubInstallation | [7 empty] | 3
1919 |  | Multi-Purpose Support Vessel | Delay | 136 | 566666.6667 | ACTION | 2154.1667 | MooredSubInstallation | Site
1920 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 2154.1667 | SemiSubStorageInstallation | [7 empty] | 3
1921 |  | Multi-Purpose Support Vessel | Delay | 136 | 566666.6667 | ACTION | 2154.1667 | SemiSubStorageInstallation | Site
1922 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2154.4813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1923 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2156 | MooringSystemInstallation
1924 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 2156.1667 | MooredSubInstallation
1925 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 2156.1667 | SemiSubStorageInstallation
1926 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2157.0886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1927 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2159.9813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1928 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2160 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1929 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2160.0886 | TurbineInstallation
1930 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2160.9813 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1931 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2161.0886 | TurbineInstallation
1932 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2162.1667 | MooredSubInstallation
1933 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2162.1667 | SemiSubStorageInstallation
1934 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2162.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1935 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2168.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1936 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2169.4086 | TurbineInstallation
1937 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2170.4086 | TurbineInstallation
1938 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2170.7478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1939 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2171.7286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1940 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2171.7478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1941 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2175.2286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1942 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2175.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1943 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2176.2286 | TurbineInstallation
1944 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2177.2478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1945 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2177.5486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1946 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2180 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1947 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2181.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1948 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2182.0486 | TurbineInstallation
1949 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2182.7478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1950 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2183.3686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1951 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2184 | MooredSubInstallation
1952 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 2184 | MooredSubInstallation
1953 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2184 | SemiSubStorageInstallation
1954 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 2184 | SemiSubStorageInstallation
1955 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 2184.1667 | MooredSubInstallation
1956 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 2184.1667 | SemiSubStorageInstallation
1957 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2184.7478 | ArrayCableInstallation
1958 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2185.7478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1959 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2186.8686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1960 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2188.8686 | TurbineInstallation
1961 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2190 | MooringSystemInstallation
1962 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2191.2478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1963 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2191.8686 | TurbineInstallation
1964 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2192 | MooredSubInstallation
1965 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2192 | SemiSubStorageInstallation
1966 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2192.5286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1967 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2195 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1968 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2196.1667 | MooredSubInstallation
1969 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 2196.1667 | MooredSubInstallation | site | [6 empty] | 2
1970 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2196.1667 | SemiSubStorageInstallation
1971 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 2196.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
1972 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2196.7478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1973 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2197.7478 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1974 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2198.5286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1975 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2201.5286 | TurbineInstallation
1976 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2202.8486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1977 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2204 | MooredSubInstallation
1978 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2204 | SemiSubStorageInstallation
1979 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2205 | MooringSystemInstallation
1980 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2207 | MooringSystemInstallation
1981 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2207.5143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
1982 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2208.5143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1983 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2208.8486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1984 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2211 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
1985 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2211.8486 | TurbineInstallation
1986 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2212.8333 | MooredSubInstallation | [7 empty] | 3
1987 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2212.8333 | SemiSubStorageInstallation | [7 empty] | 3
1988 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2212.8486 | TurbineInstallation
1989 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2214.0143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1990 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2214.1686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1991 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2216 | MooredSubInstallation
1992 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2216 | SemiSubStorageInstallation
1993 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2219.5143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1994 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2220.1686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
1995 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2221.1686 | TurbineInstallation
1996 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2221.5143 | ArrayCableInstallation
1997 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2222.1686 | TurbineInstallation
1998 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2222.5143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
1999 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2223.4886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2000 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2226.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2001 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2226.9886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2002 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2227.9886 | TurbineInstallation
2003 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2228 | MooredSubInstallation
2004 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2228 | SemiSubStorageInstallation
2005 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2228.0143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2006 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2229.3086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2007 |  | Export Cable Installation Vessel | Lay/Bury Cable | 85 | 425000 | ACTION | 2230.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2008 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2231 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2009 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2233 | MooringSystemInstallation
2010 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2237 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2011 |  | WTIV | Delay | 11 | 229166.6667 | ACTION | 2240.3086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2012 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 2241 | MooredSubInstallation
2013 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 2241 | SemiSubStorageInstallation
2014 |  | Array Cable Installation Vessel | Delay | 15 | 75000 | ACTION | 2243.0143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2015 |  | Export Cable Installation Vessel | Delay | 13 | 65000 | ACTION | 2243.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2016 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2243.8086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2017 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2244.8086 | TurbineInstallation
2018 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2246.1286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2019 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2248 | MooredSubInstallation
2020 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2248 | SemiSubStorageInstallation
2021 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2248.5143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2022 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2249.5143 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2023 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2249.6286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2024 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2251.5 | MooredSubInstallation
2025 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2251.5 | SemiSubStorageInstallation
2026 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2252.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2027 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2255 | MooredSubInstallation
2028 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2255 | SemiSubStorageInstallation
2029 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2257 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2030 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2258.5 | MooredSubInstallation
2031 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2258.5 | SemiSubStorageInstallation
2032 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2259 | MooringSystemInstallation
2033 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2259.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2034 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2260.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2035 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2263 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2036 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2263.9143 | TurbineInstallation
2037 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2265.7808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2038 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2267.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2039 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2271.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2040 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2271.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2041 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2273.2808 | ArrayCableInstallation
2042 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2274.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2043 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2275.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2044 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2277.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2045 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2278.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2046 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2278.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2047 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2279.7808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2048 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2280.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2049 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2282.5 | MooredSubInstallation
2050 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 69.6667 | 87083.3333 | ACTION | 2282.5 | MooredSubInstallation
2051 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2282.5 | SemiSubStorageInstallation
2052 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 69.6667 | 87083.3333 | ACTION | 2282.5 | SemiSubStorageInstallation
2053 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2283 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2054 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2284.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2055 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2285 | MooringSystemInstallation
2056 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2285.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2057 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2286.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2058 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2288.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2059 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2289 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2060 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2292.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2061 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2293.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2062 |  | Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 2294.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2063 |  | Export Cable Installation Vessel | Lay/Bury Cable | 51 | 255000 | ACTION | 2294.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2064 |  | Array Cable Installation Vessel | Delay | 10 | 50000 | ACTION | 2304.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2065 |  | Export Cable Installation Vessel | Delay | 10 | 50000 | ACTION | 2304.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2066 |  | Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2305.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2067 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2305.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2068 |  | Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 2336 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2069 |  | Towing Group 1 | Delay | 56 | 210000 | ACTION | 2338.5 | MooredSubInstallation | [7 empty] | 3
2070 |  | Towing Group 1 | Delay | 56 | 210000 | ACTION | 2338.5 | SemiSubStorageInstallation | [7 empty] | 3
2071 |  | WTIV | Delay | 45 | 937500 | ACTION | 2338.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2072 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2340.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2073 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2341.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2074 |  | Array Cable Installation Vessel | Delay | 39 | 195000 | ACTION | 2344.2808 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2075 |  | Export Cable Installation Vessel | Delay | 39 | 195000 | ACTION | 2344.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2076 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2344.5 | MooredSubInstallation | [7 empty] | 3
2077 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2344.5 | SemiSubStorageInstallation | [7 empty] | 3
2078 |  | Array Cable Installation Vessel | Lay/Bury Cable | 0.76651 | 3832.5638 | ACTION | 2345.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2079 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2346.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2080 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2351.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2081 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2351.5473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2082 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2352 | MooredSubInstallation
2083 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 69.5 | 0 | ACTION | 2352 | MooredSubInstallation
2084 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2352 | SemiSubStorageInstallation
2085 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 69.5 | 0 | ACTION | 2352 | SemiSubStorageInstallation
2086 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2356 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2087 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2356.2 | TurbineInstallation
2088 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2357.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2089 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2358.2 | TurbineInstallation
2090 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2359.0473 | ArrayCableInstallation
2091 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2360 | MooredSubInstallation
2092 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2360 | SemiSubStorageInstallation
2093 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2360.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2094 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 2361.1667 | MooredSubInstallation | [7 empty] | 3
2095 |  | Multi-Purpose Support Vessel | Delay | 165 | 687500 | ACTION | 2361.1667 | MooredSubInstallation | Site
2096 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 2361.1667 | SemiSubStorageInstallation | [7 empty] | 3
2097 |  | Multi-Purpose Support Vessel | Delay | 165 | 687500 | ACTION | 2361.1667 | SemiSubStorageInstallation | Site
2098 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2361.2 | TurbineInstallation
2099 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2361.86 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2100 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 2363.1667 | MooredSubInstallation
2101 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 2363.1667 | SemiSubStorageInstallation
2102 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2365.5473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2103 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2366 | MooringSystemInstallation
2104 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2367.86 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2105 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2369.1667 | MooredSubInstallation
2106 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2369.1667 | SemiSubStorageInstallation
2107 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2370.86 | TurbineInstallation
2108 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2371 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2109 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2371.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2110 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2372 | MooredSubInstallation
2111 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2372 | SemiSubStorageInstallation
2112 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2372.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2113 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2372.18 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2114 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 6 | 25000 | ACTION | 2375.1667 | MooredSubInstallation
2115 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 6 | 25000 | ACTION | 2375.1667 | SemiSubStorageInstallation
2116 |  | Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 2376.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2117 |  | Export Cable Installation Vessel | Lay/Bury Cable | 32 | 160000 | ACTION | 2376.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2118 |  | Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 2379 | MooringSystemInstallation
2119 |  | Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 2383 | MooringSystemInstallation
2120 |  | Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 2384 | MooringSystemInstallation
2121 |  | Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 2386 | MooringSystemInstallation
2122 |  | Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 2387 | MooringSystemInstallation
2123 |  | Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 2397 | MooringSystemInstallation
2124 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2399 | MooringSystemInstallation
2125 |  | Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 2404 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2126 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2408 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2127 |  | Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 2409 | MooredSubInstallation
2128 |  | Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 2409 | SemiSubStorageInstallation
2129 |  | Multi-Purpose Support Vessel | Delay | 35 | 145833.3333 | ACTION | 2410.1667 | MooredSubInstallation
2130 |  | Multi-Purpose Support Vessel | Delay | 35 | 145833.3333 | ACTION | 2410.1667 | SemiSubStorageInstallation
2131 |  | WTIV | Delay | 38 | 791666.6667 | ACTION | 2410.18 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2132 |  | Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 2412.0473 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2133 |  | Export Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 2412.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2134 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2416.18 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2135 |  | Array Cable Installation Vessel | Lay/Bury Cable | 5.7665 | 28832.5638 | ACTION | 2417.8138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2136 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2418.8138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2137 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2419.18 | TurbineInstallation
2138 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2420.18 | TurbineInstallation
2139 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2421 | MooredSubInstallation
2140 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2421 | SemiSubStorageInstallation
2141 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2421.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2142 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2423.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2143 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2424.3138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2144 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 2426.1667 | MooredSubInstallation
2145 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 2426.1667 | SemiSubStorageInstallation
2146 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2427.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2147 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2428 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2148 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2428.5 | TurbineInstallation
2149 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2429.5 | TurbineInstallation
2150 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2429.8138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2151 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2430 | MooringSystemInstallation
2152 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2430.82 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2153 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2431.8138 | ArrayCableInstallation
2154 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2432.8138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2155 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2433 | MooredSubInstallation
2156 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2433 | SemiSubStorageInstallation
2157 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2434 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2158 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2434.32 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2159 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2435.32 | TurbineInstallation
2160 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2436.64 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2161 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2438.1667 | MooredSubInstallation
2162 |  | Towing Group 1 | Positioning Support | 77 | 192500 | ACTION | 2438.1667 | MooredSubInstallation | site | [6 empty] | 2
2163 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2438.1667 | SemiSubStorageInstallation
2164 |  | Towing Group 1 | Positioning Support | 77 | 192500 | ACTION | 2438.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
2165 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2438.3138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2166 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2440 | MooredSubInstallation
2167 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2440 | SemiSubStorageInstallation
2168 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2440.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2169 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2441.14 | TurbineInstallation
2170 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2442.46 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2171 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2443.5 | MooredSubInstallation
2172 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2443.5 | SemiSubStorageInstallation
2173 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2443.8138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2174 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2444.8138 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2175 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2445.96 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2176 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2447 | MooredSubInstallation
2177 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2447 | SemiSubStorageInstallation
2178 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2447.96 | TurbineInstallation
2179 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2449.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2180 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2450.5 | MooredSubInstallation
2181 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2450.5 | SemiSubStorageInstallation
2182 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2450.96 | TurbineInstallation
2183 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2451.62 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2184 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2454 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2185 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2454.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2186 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2454.8333 | MooredSubInstallation | [7 empty] | 3
2187 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2454.8333 | SemiSubStorageInstallation | [7 empty] | 3
2188 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2455.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2189 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2456 | MooringSystemInstallation
2190 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2457.62 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2191 |  | Export Cable Installation Vessel | Lay/Bury Cable | 47 | 235000 | ACTION | 2459.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2192 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2460 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2193 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2460.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2194 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2460.62 | TurbineInstallation
2195 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2461.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2196 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2461.94 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2197 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2462.4856 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2198 |  | Array Cable Installation Vessel | Delay | 7 | 35000 | ACTION | 2462.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2199 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2467.94 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2200 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2468.0803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2201 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2470.94 | TurbineInstallation
2202 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2471.94 | TurbineInstallation
2203 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2473.26 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2204 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2473.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2205 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2474.5 | MooredSubInstallation
2206 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 19.6667 | 24583.3333 | ACTION | 2474.5 | MooredSubInstallation
2207 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2474.5 | SemiSubStorageInstallation
2208 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 19.6667 | 24583.3333 | ACTION | 2474.5 | SemiSubStorageInstallation
2209 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2475.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2210 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2475.5803 | ArrayCableInstallation
2211 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2476.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2212 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2479.26 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2213 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2480 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2214 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2480.26 | TurbineInstallation
2215 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2480.5 | MooredSubInstallation | [7 empty] | 3
2216 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2480.5 | SemiSubStorageInstallation | [7 empty] | 3
2217 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2481.26 | TurbineInstallation
2218 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2482 | MooringSystemInstallation
2219 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2482.0803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2220 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2482.58 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2221 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2486 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2222 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2486.08 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2223 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2487.08 | TurbineInstallation
2224 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2487.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2225 |  | Export Cable Installation Vessel | Lay/Bury Cable | 25.6667 | 128333.3333 | ACTION | 2488.1523 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2226 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2488.4 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2227 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2488.5803 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2228 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2491.9 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2229 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2492.9 | TurbineInstallation
2230 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2494.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2231 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 2496.848 | ExportCableInstallation
2232 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 2497.1667 | MooredSubInstallation | [7 empty] | 3
2233 |  | Multi-Purpose Support Vessel | Delay | 59 | 245833.3333 | ACTION | 2497.1667 | MooredSubInstallation | Site
2234 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 2497.1667 | SemiSubStorageInstallation | [7 empty] | 3
2235 |  | Multi-Purpose Support Vessel | Delay | 59 | 245833.3333 | ACTION | 2497.1667 | SemiSubStorageInstallation | Site
2236 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2497.72 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2237 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2498.3469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2238 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 2499.1667 | MooredSubInstallation
2239 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 2499.1667 | SemiSubStorageInstallation
2240 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2499.3469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2241 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2501.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2242 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 2502.848 | ExportCableInstallation |  |  |  | ExportCableInstallation
2243 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2504.8469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2244 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2505.1667 | MooredSubInstallation
2245 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2505.1667 | SemiSubStorageInstallation
2246 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2506 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2247 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2510.3469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2248 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 2511.5436 | ExportCableInstallation
2249 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2512.0057 | TurbineInstallation
2250 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2512.3469 | ArrayCableInstallation
2251 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2513.3469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2252 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2513.5436 | ExportCableInstallation
2253 |  | Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 2514.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation
2254 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2516 | MooringSystemInstallation
2255 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2516.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2256 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2518.8469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2257 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2520 | MooredSubInstallation
2258 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 45.5 | 0 | ACTION | 2520 | MooredSubInstallation
2259 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2520 | SemiSubStorageInstallation
2260 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 45.5 | 0 | ACTION | 2520 | SemiSubStorageInstallation
2261 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2520.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2262 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2521 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2263 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2524.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2264 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2524.3469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2265 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2525.3469 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2266 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2525.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2267 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2527.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2268 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 2527.1667 | MooredSubInstallation
2269 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 2527.1667 | SemiSubStorageInstallation
2270 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2528 | MooredSubInstallation
2271 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2528 | SemiSubStorageInstallation
2272 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2528.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2273 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2531 | MooringSystemInstallation
2274 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 2531.1667 | MooredSubInstallation
2275 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 2531.1667 | SemiSubStorageInstallation
2276 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2532.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2277 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2533 | MooringSystemInstallation
2278 |  | Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 2534.1667 | MooredSubInstallation
2279 |  | Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 2534.1667 | SemiSubStorageInstallation
2280 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2535.1134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2281 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2536.1134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2282 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2536.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2283 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2537 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2284 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2540 | MooredSubInstallation
2285 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2540 | SemiSubStorageInstallation
2286 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2540.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2287 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2541.6134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2288 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2542.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2289 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 8 | 33333.3333 | ACTION | 2542.1667 | MooredSubInstallation
2290 |  | Towing Group 1 | Positioning Support | 45 | 112500 | ACTION | 2542.1667 | MooredSubInstallation | site | [6 empty] | 2
2291 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 8 | 33333.3333 | ACTION | 2542.1667 | SemiSubStorageInstallation
2292 |  | Towing Group 1 | Positioning Support | 45 | 112500 | ACTION | 2542.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
2293 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2543.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2294 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2545.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2295 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2547.1134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2296 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2549.1134 | ArrayCableInstallation
2297 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2550.1134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2298 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2552 | MooredSubInstallation
2299 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2552 | SemiSubStorageInstallation
2300 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2552.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2301 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2555.6134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2302 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2557 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2303 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2558.8333 | MooredSubInstallation | [7 empty] | 3
2304 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2558.8333 | SemiSubStorageInstallation | [7 empty] | 3
2305 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2559 | MooringSystemInstallation
2306 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2559.2914 | TurbineInstallation
2307 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2561.1134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2308 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2561.2914 | TurbineInstallation
2309 |  | Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 2562.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation
2310 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2562.1134 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2311 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2563 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2312 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2563.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation
2313 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2564 | MooredSubInstallation
2314 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2564 | SemiSubStorageInstallation
2315 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2564.2914 | TurbineInstallation
2316 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2564.9514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2317 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2570.9514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2318 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2571 | MooredSubInstallation
2319 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2571 | SemiSubStorageInstallation
2320 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2571.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2321 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2572.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2322 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2573.9514 | TurbineInstallation
2323 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2574.5 | MooredSubInstallation
2324 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2574.5 | SemiSubStorageInstallation
2325 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2575.2714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2326 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2578 | MooredSubInstallation
2327 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2578 | SemiSubStorageInstallation
2328 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2578.3799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2329 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2578.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2330 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2581.2714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2331 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2583 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2332 |  | Export Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 2583.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2333 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2584.2714 | TurbineInstallation
2334 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2585 | MooringSystemInstallation
2335 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2585.2714 | TurbineInstallation
2336 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2589 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2337 |  | Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 2595 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2338 |  | WTIV | Delay | 17 | 354166.6667 | ACTION | 2602.2714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2339 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2603.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2340 |  | Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 2607 | MooredSubInstallation
2341 |  | Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 2607 | SemiSubStorageInstallation
2342 |  | Export Cable Installation Vessel | Delay | 24 | 120000 | ACTION | 2607.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2343 |  | Array Cable Installation Vessel | Delay | 29 | 145000 | ACTION | 2607.3799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2344 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2609.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2345 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2610.5 | MooredSubInstallation
2346 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2610.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2347 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2610.5 | SemiSubStorageInstallation
2348 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2610.5914 | TurbineInstallation
2349 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2611.5914 | TurbineInstallation
2350 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2612.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2351 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2612.9114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2352 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2614.8799 | ArrayCableInstallation
2353 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2615 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2354 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2615.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2355 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2616.4114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2356 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2617 | MooringSystemInstallation
2357 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2617.4114 | TurbineInstallation
2358 |  | Export Cable Installation Vessel | Lay/Bury Cable | 11 | 55000 | ACTION | 2618.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2359 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2618.7314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2360 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2619.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2361 |  | Array Cable Installation Vessel | Delay | 4 | 20000 | ACTION | 2619.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2362 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2621 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2363 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2622.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2364 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2623.2314 | TurbineInstallation
2365 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2624.5514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2366 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2625.3799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2367 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2628.0514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2368 |  | Export Cable Installation Vessel | Lay/Bury Cable | 10 | 50000 | ACTION | 2629.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2369 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2630.0514 | TurbineInstallation
2370 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2633.0514 | TurbineInstallation
2371 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2633.7114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2372 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2634.5 | MooredSubInstallation
2373 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 75.6667 | 94583.3333 | ACTION | 2634.5 | MooredSubInstallation
2374 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2634.5 | SemiSubStorageInstallation
2375 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 75.6667 | 94583.3333 | ACTION | 2634.5 | SemiSubStorageInstallation
2376 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2636.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2377 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2641 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2378 |  | Towing Group 1 | Delay | 10 | 37500 | ACTION | 2644.5 | MooredSubInstallation | [7 empty] | 3
2379 |  | Towing Group 1 | Delay | 10 | 37500 | ACTION | 2644.5 | SemiSubStorageInstallation | [7 empty] | 3
2380 |  | WTIV | Delay | 11 | 229166.6667 | ACTION | 2644.7114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2381 |  | Export Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 2646.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2382 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2647.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2383 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2648.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2384 |  | Array Cable Installation Vessel | Delay | 23 | 115000 | ACTION | 2648.3799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2385 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2650.5 | MooredSubInstallation | [7 empty] | 3
2386 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2650.5 | SemiSubStorageInstallation | [7 empty] | 3
2387 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2650.7114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2388 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2651 | MooringSystemInstallation
2389 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2653.7114 | TurbineInstallation
2390 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2653.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2391 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2654.8799 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2392 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2655.0314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2393 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2656 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2394 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2661.0314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2395 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2664.0314 | TurbineInstallation
2396 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2664.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2397 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2665.0314 | TurbineInstallation
2398 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2665.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2399 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2666 | MooringSystemInstallation
2400 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2666.3514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2401 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 2667.1667 | MooredSubInstallation | [7 empty] | 3
2402 |  | Multi-Purpose Support Vessel | Delay | 125 | 520833.3333 | ACTION | 2667.1667 | MooredSubInstallation | Site
2403 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 2667.1667 | SemiSubStorageInstallation | [7 empty] | 3
2404 |  | Multi-Purpose Support Vessel | Delay | 125 | 520833.3333 | ACTION | 2667.1667 | SemiSubStorageInstallation | Site
2405 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2668 | MooringSystemInstallation
2406 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 2669.1667 | MooredSubInstallation
2407 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 2669.1667 | SemiSubStorageInstallation
2408 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2671.1464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2409 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2672 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2410 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2672.3514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2411 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2673.3514 | TurbineInstallation
2412 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2674.3514 | TurbineInstallation
2413 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2675.1667 | MooredSubInstallation
2414 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2675.1667 | SemiSubStorageInstallation
2415 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2675.6714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2416 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2676.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2417 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2678.6464 | ArrayCableInstallation
2418 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2679.1714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2419 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2679.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2420 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 5 | 20833.3333 | ACTION | 2680.1667 | MooredSubInstallation
2421 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 5 | 20833.3333 | ACTION | 2680.1667 | SemiSubStorageInstallation
2422 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2680.1714 | TurbineInstallation
2423 |  | Export Cable Installation Vessel | Lay/Bury Cable | 35 | 175000 | ACTION | 2683.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2424 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2688 | MooredSubInstallation
2425 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 53.5 | 0 | ACTION | 2688 | MooredSubInstallation
2426 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2688 | SemiSubStorageInstallation
2427 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 53.5 | 0 | ACTION | 2688 | SemiSubStorageInstallation
2428 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2696 | MooredSubInstallation
2429 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2696 | SemiSubStorageInstallation
2430 |  | Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 2700 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2431 |  | Multi-Purpose Support Vessel | Delay | 23 | 95833.3333 | ACTION | 2703.1667 | MooredSubInstallation
2432 |  | Multi-Purpose Support Vessel | Delay | 23 | 95833.3333 | ACTION | 2703.1667 | SemiSubStorageInstallation
2433 |  | WTIV | Delay | 23 | 479166.6667 | ACTION | 2703.1714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2434 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2704.4914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2435 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2707.9914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2436 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2708 | MooredSubInstallation
2437 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2708 | SemiSubStorageInstallation
2438 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2708.9914 | TurbineInstallation
2439 |  | Export Cable Installation Vessel | Delay | 26 | 130000 | ACTION | 2709.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2440 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2710.3114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2441 |  | Export Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 2711.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2442 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2712.0436 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2443 |  | Export Cable Installation Vessel | Lay/Bury Cable | 0.04159 | 207.9486 | ACTION | 2712.0852 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2444 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 9 | 37500 | ACTION | 2712.1667 | MooredSubInstallation
2445 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 9 | 37500 | ACTION | 2712.1667 | SemiSubStorageInstallation
2446 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 2713.1667 | MooredSubInstallation
2447 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 2713.1667 | SemiSubStorageInstallation
2448 |  | WTIV | Delay | 3 | 62500 | ACTION | 2713.3114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2449 |  | Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 2714 | MooredSubInstallation
2450 |  | Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 2714 | SemiSubStorageInstallation
2451 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2714.0852 | ExportCableInstallation
2452 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2715.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2453 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2716.8114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2454 |  | Export Cable Installation Vessel | Delay | 4 | 20000 | ACTION | 2718.0852 | ExportCableInstallation |  |  |  | ExportCableInstallation
2455 |  | Array Cable Installation Vessel | Delay | 39 | 195000 | ACTION | 2718.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2456 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2720 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2457 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 2721.1667 | MooredSubInstallation
2458 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 2721.1667 | SemiSubStorageInstallation
2459 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2722 | MooringSystemInstallation
2460 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2723.5852 | ExportCableInstallation |  |  |  | ExportCableInstallation
2461 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2724.1464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2462 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2726 | MooredSubInstallation
2463 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2726 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2464 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2726 | SemiSubStorageInstallation
2465 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2729.0852 | ExportCableInstallation |  |  |  | ExportCableInstallation
2466 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2729.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2467 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2730.6464 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2468 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2731.0971 | TurbineInstallation
2469 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2733.1667 | MooredSubInstallation
2470 |  | Towing Group 1 | Positioning Support | 66 | 165000 | ACTION | 2733.1667 | MooredSubInstallation | site | [6 empty] | 2
2471 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2733.1667 | SemiSubStorageInstallation
2472 |  | Towing Group 1 | Positioning Support | 66 | 165000 | ACTION | 2733.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
2473 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2735.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2474 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 2737.7809 | ExportCableInstallation
2475 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2738 | MooredSubInstallation
2476 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2738 | SemiSubStorageInstallation
2477 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2739.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2478 |  | Array Cable Installation Vessel | Lay/Bury Cable | 9.7665 | 48832.5638 | ACTION | 2740.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2479 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2741.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2480 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2741.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2481 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2743.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2482 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 2743.7809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2483 |  | Export Cable Installation Vessel | Tow Plow | 0.2 | 1000 | ACTION | 2743.9809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2484 |  | Export Cable Installation Vessel | Pull Winch | 0.2 | 1000 | ACTION | 2744.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2485 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2744.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2486 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2745 | MooredSubInstallation
2487 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2745 | SemiSubStorageInstallation
2488 |  | Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2745.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2489 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2746 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2490 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2746.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2491 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2746.9129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2492 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2747.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2493 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2748 | MooringSystemInstallation
2494 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2748.5 | MooredSubInstallation
2495 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2748.5 | SemiSubStorageInstallation
2496 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2749.8333 | MooredSubInstallation | [7 empty] | 3
2497 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2749.8333 | SemiSubStorageInstallation | [7 empty] | 3
2498 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2750.6809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2499 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2751.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2500 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2752 | MooredSubInstallation
2501 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2752 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2502 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2752 | SemiSubStorageInstallation
2503 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2752.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2504 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2754.4129 | ArrayCableInstallation
2505 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2755.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2506 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2755.5 | MooredSubInstallation
2507 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2755.5 | SemiSubStorageInstallation
2508 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2755.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2509 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2756.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2510 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2757.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation
2511 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2759.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2512 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2760.9129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2513 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2761.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2514 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2762.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2515 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2764.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2516 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2766.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2517 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2767.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2518 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2767.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2519 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2772 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2520 |  | Export Cable Installation Vessel | Lay/Bury Cable | 15 | 75000 | ACTION | 2772.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2521 |  | Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 2772.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2522 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2774 | MooringSystemInstallation
2523 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2778 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2524 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2778.3829 | TurbineInstallation
2525 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2779.5 | MooredSubInstallation
2526 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 29.6667 | 37083.3333 | ACTION | 2779.5 | MooredSubInstallation
2527 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2779.5 | SemiSubStorageInstallation
2528 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 29.6667 | 37083.3333 | ACTION | 2779.5 | SemiSubStorageInstallation
2529 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2780.3829 | TurbineInstallation
2530 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2783.3829 | TurbineInstallation
2531 |  | WTIV | Delay | 7 | 145833.3333 | ACTION | 2790.3829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2532 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2791.0429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2533 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2793.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2534 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2798 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2535 |  | WTIV | Delay | 9 | 187500 | ACTION | 2800.0429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2536 |  | Towing Group 1 | Delay | 21 | 78750 | ACTION | 2800.5 | MooredSubInstallation | [7 empty] | 3
2537 |  | Towing Group 1 | Delay | 21 | 78750 | ACTION | 2800.5 | SemiSubStorageInstallation | [7 empty] | 3
2538 |  | Export Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 2805.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2539 |  | Array Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 2805.4129 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2540 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2806.0429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2541 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2806.5 | MooredSubInstallation | [7 empty] | 3
2542 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2806.5 | SemiSubStorageInstallation | [7 empty] | 3
2543 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2808 | MooringSystemInstallation
2544 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2809.0429 | TurbineInstallation
2545 |  | Array Cable Installation Vessel | Lay/Bury Cable | 4.7665 | 23832.5638 | ACTION | 2810.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2546 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2810.3629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2547 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2811.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2548 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2813 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2549 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2816.3629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2550 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2816.6794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2551 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2819.3629 | TurbineInstallation
2552 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2820.3629 | TurbineInstallation
2553 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2821.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2554 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2822.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2555 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2823 | MooringSystemInstallation
2556 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 2823.1667 | MooredSubInstallation | [7 empty] | 3
2557 |  | Multi-Purpose Support Vessel | Delay | 90 | 375000 | ACTION | 2823.1667 | MooredSubInstallation | Site
2558 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 2823.1667 | SemiSubStorageInstallation | [7 empty] | 3
2559 |  | Multi-Purpose Support Vessel | Delay | 90 | 375000 | ACTION | 2823.1667 | SemiSubStorageInstallation | Site
2560 |  | Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2824.1794 | ArrayCableInstallation
2561 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2825 | MooringSystemInstallation
2562 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 2825.1667 | MooredSubInstallation
2563 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 2825.1667 | SemiSubStorageInstallation
2564 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2825.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2565 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2827.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2566 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2828.6829 | TurbineInstallation
2567 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2829 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2568 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2829.6829 | TurbineInstallation
2569 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2830.6794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2570 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2831.0029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2571 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2831.1667 | MooredSubInstallation
2572 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 2831.1667 | SemiSubStorageInstallation
2573 |  | Export Cable Installation Vessel | Lay/Bury Cable | 28 | 140000 | ACTION | 2833.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2574 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2834.5029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2575 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 2835.1667 | MooredSubInstallation
2576 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 2835.1667 | SemiSubStorageInstallation
2577 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2835.5029 | TurbineInstallation
2578 |  | Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 2840 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2579 |  | Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 2843.1667 | MooredSubInstallation
2580 |  | Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 2843.1667 | SemiSubStorageInstallation
2581 |  | WTIV | Delay | 8 | 166666.6667 | ACTION | 2843.5029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2582 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2844.8229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2583 |  | Export Cable Installation Vessel | Delay | 13 | 65000 | ACTION | 2846.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2584 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2848.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2585 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2849.3229 | TurbineInstallation
2586 |  | Export Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 2850.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2587 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2850.6429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2588 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2851.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2589 |  | Array Cable Installation Vessel | Delay | 21 | 105000 | ACTION | 2851.6794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2590 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2854.1429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2591 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2855.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2592 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2856 | MooredSubInstallation
2593 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76.5 | 0 | ACTION | 2856 | MooredSubInstallation
2594 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2856 | SemiSubStorageInstallation
2595 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76.5 | 0 | ACTION | 2856 | SemiSubStorageInstallation
2596 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2856.1429 | TurbineInstallation
2597 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2857.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2598 |  | Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2858.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2599 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2859.1429 | TurbineInstallation
2600 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 2859.8029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2601 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2860 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2602 |  | Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 2860.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2603 |  | Export Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 2860.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2604 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 18 | 75000 | ACTION | 2861.1667 | MooredSubInstallation
2605 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 18 | 75000 | ACTION | 2861.1667 | SemiSubStorageInstallation
2606 |  | Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2861.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2607 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2861.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2608 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2862 | MooringSystemInstallation
2609 |  | Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2862.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2610 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2862.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2611 |  | Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2863.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2612 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 2863.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2613 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2864 | MooredSubInstallation
2614 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2864 | SemiSubStorageInstallation
2615 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2865.8029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2616 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2866 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2617 |  | Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 2867.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2618 |  | Export Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 2867.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2619 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2868.8029 | TurbineInstallation
2620 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 2870.1229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2621 |  | Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 2870.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2622 |  | Export Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 2870.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2623 |  | Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2871.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2624 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2871.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2625 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2873.1667 | MooredSubInstallation
2626 |  | Towing Group 1 | Positioning Support | 50 | 125000 | ACTION | 2873.1667 | MooredSubInstallation | site | [6 empty] | 2
2627 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 2873.1667 | SemiSubStorageInstallation
2628 |  | Towing Group 1 | Positioning Support | 50 | 125000 | ACTION | 2873.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
2629 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2876 | MooredSubInstallation
2630 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2876 | SemiSubStorageInstallation
2631 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 2876.1229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2632 |  | Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 2876.1794 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2633 |  | Export Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 2876.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2634 |  | Array Cable Installation Vessel | Lay/Bury Cable | 1.7665 | 8832.5638 | ACTION | 2877.9459 | ArrayCableInstallation |  |  |  | ArrayCableInstallation | 2 | 25 | 11.5
2635 |  | Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 2878.9459 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2636 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 2879.1229 | TurbineInstallation
2637 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2880.1229 | TurbineInstallation
2638 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2881.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2639 |  | Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2884.4459 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2640 |  | Export Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 2885.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2641 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2886 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2642 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2888 | MooringSystemInstallation
2643 |  | Export Cable Installation Vessel | Delay | 4 | 20000 | ACTION | 2889.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2644 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2889.8333 | MooredSubInstallation | [7 empty] | 3
2645 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 2889.8333 | SemiSubStorageInstallation | [7 empty] | 3
2646 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 2890.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2647 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2892 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2648 |  | WTIV | Delay | 25 | 520833.3333 | ACTION | 2905.1229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2649 |  | Export Cable Installation Vessel | Delay | 15 | 75000 | ACTION | 2905.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2650 |  | Array Cable Installation Vessel | Delay | 21 | 105000 | ACTION | 2905.4459 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2651 |  | Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 2906 | MooredSubInstallation
2652 |  | Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 2906 | SemiSubStorageInstallation
2653 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 2906.4429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2654 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2907.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2655 |  | Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2910.9459 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2656 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2912 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2657 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 2912.4429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2658 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 2913.4429 | TurbineInstallation
2659 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2914 | MooringSystemInstallation
2660 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2914.4429 | TurbineInstallation
2661 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2915.7629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2662 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2918 | MooredSubInstallation
2663 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2918 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2664 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2918 | SemiSubStorageInstallation
2665 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2919.2629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2666 |  | Array Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 2919.6416 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2667 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2920.2629 | TurbineInstallation
2668 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2921.5829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2669 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2925.0829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2670 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 2926.0829 | TurbineInstallation
2671 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 2927.4029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2672 |  | Array Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 2928.3372 | ArrayCableInstallation |  |  |  | ArrayCableInstallation
2673 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2930 | MooredSubInstallation
2674 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 2930 | SemiSubStorageInstallation
2675 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 2930.9029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2676 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2933.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2677 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2937 | MooredSubInstallation
2678 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 2937 | SemiSubStorageInstallation
2679 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2938 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2680 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2945.1886 | TurbineInstallation
2681 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2948 | MooringSystemInstallation
2682 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2949.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2683 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2953 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2684 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2953.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2685 |  | Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 2957 | MooredSubInstallation
2686 |  | Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 2957 | SemiSubStorageInstallation
2687 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2957.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2688 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2958.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2689 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2960.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2690 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2960.5 | MooredSubInstallation
2691 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2960.5 | SemiSubStorageInstallation
2692 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2961.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2693 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2963 | MooringSystemInstallation
2694 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2964 | MooredSubInstallation
2695 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2964 | SemiSubStorageInstallation
2696 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2965 | MooringSystemInstallation
2697 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2965.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2698 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2967.5 | MooredSubInstallation
2699 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2967.5 | SemiSubStorageInstallation
2700 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2969 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2701 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 2969.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2702 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 2973.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2703 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2975.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2704 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2976.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2705 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 2978.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2706 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 2984.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2707 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 2989 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2708 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2991 | MooringSystemInstallation
2709 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2991.5 | MooredSubInstallation
2710 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 101.6667 | 127083.3333 | ACTION | 2991.5 | MooredSubInstallation
2711 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2991.5 | SemiSubStorageInstallation
2712 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 101.6667 | 127083.3333 | ACTION | 2991.5 | SemiSubStorageInstallation
2713 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 2992.4743 | TurbineInstallation
2714 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 2994.4743 | TurbineInstallation
2715 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2995 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2716 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 2997.4743 | TurbineInstallation
2717 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2997.5 | MooredSubInstallation | [7 empty] | 3
2718 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 2997.5 | SemiSubStorageInstallation | [7 empty] | 3
2719 |  | Export Cable Installation Vessel | Lay/Bury Cable | 95 | 475000 | ACTION | 3000.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2720 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3024 | MooredSubInstallation
2721 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 32.5 | 0 | ACTION | 3024 | MooredSubInstallation
2722 |  | Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 3024 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2723 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3024 | SemiSubStorageInstallation
2724 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 32.5 | 0 | ACTION | 3024 | SemiSubStorageInstallation
2725 |  | WTIV | Delay | 28 | 583333.3333 | ACTION | 3025.4743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2726 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3026.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2727 |  | WTIV | Delay | 4 | 83333.3333 | ACTION | 3030.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2728 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3032 | MooredSubInstallation
2729 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3032 | SemiSubStorageInstallation
2730 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3036.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2731 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3039.1343 | TurbineInstallation
2732 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3039.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2733 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3040.4543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2734 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3044 | MooredSubInstallation
2735 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3044 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2736 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3044 | SemiSubStorageInstallation
2737 |  | Export Cable Installation Vessel | Delay | 44 | 220000 | ACTION | 3044.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2738 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 3045.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2739 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3046 | MooringSystemInstallation
2740 |  | Export Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 3047.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2741 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 3048.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2742 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3050 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2743 |  | Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 3060 | MooredSubInstallation
2744 |  | Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 3060 | SemiSubStorageInstallation
2745 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3072 | MooredSubInstallation
2746 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3072 | SemiSubStorageInstallation
2747 |  | Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 3082 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2748 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3084 | MooredSubInstallation
2749 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3084 | SemiSubStorageInstallation
2750 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3091 | MooredSubInstallation
2751 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3091 | SemiSubStorageInstallation
2752 |  | WTIV | Delay | 54 | 1125000 | ACTION | 3094.4543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2753 |  | Towing Group 1 | Delay | 97 | 363750 | ACTION | 3094.5 | MooredSubInstallation | [7 empty] | 3
2754 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3094.5 | MooredSubInstallation
2755 |  | Towing Group 1 | Delay | 97 | 363750 | ACTION | 3094.5 | SemiSubStorageInstallation | [7 empty] | 3
2756 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3094.5 | SemiSubStorageInstallation
2757 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3097.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2758 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3098 | MooredSubInstallation
2759 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3098 | SemiSubStorageInstallation
2760 |  | Export Cable Installation Vessel | Delay | 51 | 255000 | ACTION | 3099.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2761 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 3100.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2762 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3100.4543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2763 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3101.5 | MooredSubInstallation
2764 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3101.5 | SemiSubStorageInstallation
2765 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3102 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2766 |  | Export Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 3103.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2767 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3103.4543 | TurbineInstallation
2768 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3104 | MooringSystemInstallation
2769 |  | Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 3104.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2770 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3104.4543 | TurbineInstallation
2771 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 3105.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2772 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3105.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2773 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3108 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2774 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3111.1667 | MooredSubInstallation | [7 empty] | 3
2775 |  | Multi-Purpose Support Vessel | Delay | 238 | 991666.6667 | ACTION | 3111.1667 | MooredSubInstallation | Site
2776 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3111.1667 | SemiSubStorageInstallation | [7 empty] | 3
2777 |  | Multi-Purpose Support Vessel | Delay | 238 | 991666.6667 | ACTION | 3111.1667 | SemiSubStorageInstallation | Site
2778 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3111.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2779 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3112.7743 | TurbineInstallation
2780 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3113.1667 | MooredSubInstallation
2781 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3113.1667 | SemiSubStorageInstallation
2782 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3113.7743 | TurbineInstallation
2783 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3115.0943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2784 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3118.5943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2785 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3119.1667 | MooredSubInstallation
2786 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3119.1667 | SemiSubStorageInstallation
2787 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3119.5943 | TurbineInstallation
2788 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3120.9143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2789 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3123.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2790 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3124.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2791 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 6 | 25000 | ACTION | 3125.1667 | MooredSubInstallation
2792 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 6 | 25000 | ACTION | 3125.1667 | SemiSubStorageInstallation
2793 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3125.4143 | TurbineInstallation
2794 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3125.5 | MooredSubInstallation
2795 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3125.5 | SemiSubStorageInstallation
2796 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3128 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2797 |  | Export Cable Installation Vessel | Lay/Bury Cable | 25 | 125000 | ACTION | 3130.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2798 |  | Multi-Purpose Support Vessel | Delay | 12 | 50000 | ACTION | 3137.1667 | MooredSubInstallation
2799 |  | Multi-Purpose Support Vessel | Delay | 12 | 50000 | ACTION | 3137.1667 | SemiSubStorageInstallation
2800 |  | WTIV | Delay | 12 | 250000 | ACTION | 3137.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2801 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3138 | MooringSystemInstallation
2802 |  | Export Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 3138.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2803 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3138.7343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2804 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3142.2343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2805 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3143 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2806 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3144.2343 | TurbineInstallation
2807 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3147.2343 | TurbineInstallation
2808 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3147.8943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2809 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3153 | MooringSystemInstallation
2810 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 3153.1667 | MooredSubInstallation
2811 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 3153.1667 | SemiSubStorageInstallation
2812 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3153.8943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2813 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3155 | MooringSystemInstallation
2814 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3156.8943 | TurbineInstallation
2815 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3158.2143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2816 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3159 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2817 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3164.2143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2818 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3165.1667 | MooredSubInstallation
2819 |  | Towing Group 1 | Positioning Support | 54 | 135000 | ACTION | 3165.1667 | MooredSubInstallation | site | [6 empty] | 2
2820 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3165.1667 | SemiSubStorageInstallation
2821 |  | Towing Group 1 | Positioning Support | 54 | 135000 | ACTION | 3165.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
2822 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3167.2143 | TurbineInstallation
2823 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3168.2143 | TurbineInstallation
2824 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3169.5343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2825 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3174.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2826 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3175.5343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2827 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3176.5343 | TurbineInstallation
2828 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3177.5343 | TurbineInstallation
2829 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3178.8543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2830 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3179 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2831 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3181 | MooringSystemInstallation
2832 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3181.8333 | MooredSubInstallation | [7 empty] | 3
2833 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3181.8333 | SemiSubStorageInstallation | [7 empty] | 3
2834 |  | Export Cable Installation Vessel | Lay/Bury Cable | 45 | 225000 | ACTION | 3183.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2835 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3185 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2836 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3192 | MooredSubInstallation
2837 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 66.5 | 0 | ACTION | 3192 | MooredSubInstallation
2838 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3192 | SemiSubStorageInstallation
2839 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 66.5 | 0 | ACTION | 3192 | SemiSubStorageInstallation
2840 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3200 | MooredSubInstallation
2841 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3200 | SemiSubStorageInstallation
2842 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3200.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2843 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3205 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2844 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3207 | MooringSystemInstallation
2845 |  | Towing Group 1 | Delay | 29 | 108750 | ACTION | 3210.8333 | MooredSubInstallation | [7 empty] | 3
2846 |  | Towing Group 1 | Delay | 29 | 108750 | ACTION | 3210.8333 | SemiSubStorageInstallation | [7 empty] | 3
2847 |  | WTIV | Delay | 32 | 666666.6667 | ACTION | 3210.8543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2848 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3211 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2849 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3212 | MooredSubInstallation
2850 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3212 | SemiSubStorageInstallation
2851 |  | Export Cable Installation Vessel | Delay | 31 | 155000 | ACTION | 3214.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2852 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3214.3543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2853 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3215.3543 | TurbineInstallation
2854 |  | Export Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 3216.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2855 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3216.6743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2856 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3216.8333 | MooredSubInstallation | [7 empty] | 3
2857 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3216.8333 | SemiSubStorageInstallation | [7 empty] | 3
2858 |  | Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 3217.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2859 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3220.1743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2860 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3221.1743 | TurbineInstallation
2861 |  | WTIV | Delay | 3 | 62500 | ACTION | 3224.1743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2862 |  | Towing Group 1 | Delay | 8 | 30000 | ACTION | 3224.8333 | MooredSubInstallation | [7 empty] | 3
2863 |  | Towing Group 1 | Delay | 8 | 30000 | ACTION | 3224.8333 | SemiSubStorageInstallation | [7 empty] | 3
2864 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 3225 | MooredSubInstallation
2865 |  | Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 3225 | SemiSubStorageInstallation
2866 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3225.4943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2867 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3226.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2868 |  | Export Cable Installation Vessel | Lay/Bury Cable | 10 | 50000 | ACTION | 3227.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2869 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3228.9943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2870 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3231 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2871 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3233 | MooringSystemInstallation
2872 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3237 | MooredSubInstallation
2873 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3237 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2874 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3237 | SemiSubStorageInstallation
2875 |  | Export Cable Installation Vessel | Delay | 11 | 55000 | ACTION | 3238.1809 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2876 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3241.5 | MooredSubInstallation | [7 empty] | 3
2877 |  | Multi-Purpose Support Vessel | Delay | 76.3333 | 318055.5556 | ACTION | 3241.5 | MooredSubInstallation | Site
2878 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3241.5 | SemiSubStorageInstallation | [7 empty] | 3
2879 |  | Multi-Purpose Support Vessel | Delay | 76.3333 | 318055.5556 | ACTION | 3241.5 | SemiSubStorageInstallation | Site
2880 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3243.28 | TurbineInstallation
2881 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3243.5 | MooredSubInstallation
2882 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3243.5 | SemiSubStorageInstallation
2883 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3247.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2884 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3249 | MooredSubInstallation
2885 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3249 | SemiSubStorageInstallation
2886 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3249.5 | MooredSubInstallation
2887 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3249.5 | SemiSubStorageInstallation
2888 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3251.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2889 |  | Export Cable Installation Vessel | Lay/Bury Cable | 13.6667 | 68333.3333 | ACTION | 3251.8475 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
2890 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3252.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2891 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3255.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2892 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3256 | MooredSubInstallation
2893 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3256 | SemiSubStorageInstallation
2894 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3256.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2895 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3257 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2896 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3258.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2897 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3259.5 | MooredSubInstallation
2898 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3259.5 | SemiSubStorageInstallation
2899 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3259.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2900 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 3260.5432 | ExportCableInstallation
2901 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3263 | MooredSubInstallation
2902 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3263 | SemiSubStorageInstallation
2903 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3263.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2904 |  | Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 3266.5432 | ExportCableInstallation |  |  |  | ExportCableInstallation
2905 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3267 | MooringSystemInstallation
2906 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3267.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2907 |  | Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 3268 | MooredSubInstallation
2908 |  | Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 3268 | SemiSubStorageInstallation
2909 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3271.5 | MooredSubInstallation
2910 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3271.5 | SemiSubStorageInstallation
2911 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3271.5 | MooredSubInstallation
2912 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3271.5 | SemiSubStorageInstallation
2913 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3271.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2914 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3272 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2915 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3273.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2916 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3274.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2917 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 3275.2388 | ExportCableInstallation
2918 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3276.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2919 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 3277.2388 | ExportCableInstallation
2920 |  | Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 3277.7388 | ExportCableInstallation |  |  |  | ExportCableInstallation
2921 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3282 | MooringSystemInstallation
2922 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3283.5 | MooredSubInstallation
2923 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3283.5 | MooredSubInstallation | site | [6 empty] | 2
2924 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3283.5 | SemiSubStorageInstallation
2925 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3283.5 | SemiSubStorageInstallation | site | [6 empty] | 2
2926 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3284 | MooringSystemInstallation
2927 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3288 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2928 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3290.5657 | TurbineInstallation
2929 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3292.5657 | TurbineInstallation
2930 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3295.5 | MooredSubInstallation
2931 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3295.5 | SemiSubStorageInstallation
2932 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3295.5657 | TurbineInstallation
2933 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3296.2257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2934 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3300.1667 | MooredSubInstallation | [7 empty] | 3
2935 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3300.1667 | SemiSubStorageInstallation | [7 empty] | 3
2936 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3302.2257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2937 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3303.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2938 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3305.2257 | TurbineInstallation
2939 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3306.1667 | MooredSubInstallation | [7 empty] | 3
2940 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3306.1667 | SemiSubStorageInstallation | [7 empty] | 3
2941 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3306.5457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2942 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3308 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2943 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3310 | MooringSystemInstallation
2944 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3312.5457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2945 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3314 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2946 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3315.5457 | TurbineInstallation
2947 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3316.5457 | TurbineInstallation
2948 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3317.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2949 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3322.8333 | MooredSubInstallation | [7 empty] | 3
2950 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 3322.8333 | MooredSubInstallation | Site
2951 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3322.8333 | SemiSubStorageInstallation | [7 empty] | 3
2952 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 3322.8333 | SemiSubStorageInstallation | Site
2953 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3323.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2954 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3324.8333 | MooredSubInstallation
2955 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3324.8333 | SemiSubStorageInstallation
2956 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3324.8657 | TurbineInstallation
2957 |  | Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 3325.7388 | ExportCableInstallation |  |  |  | ExportCableInstallation
2958 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3325.8657 | TurbineInstallation
2959 |  | Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 3326.7388 | ExportCableInstallation |  |  |  | ExportCableInstallation
2960 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3327.1857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2961 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3329.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2962 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3330.6857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2963 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3330.8333 | MooredSubInstallation
2964 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3330.8333 | SemiSubStorageInstallation
2965 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3331.6857 | TurbineInstallation
2966 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3333.0057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2967 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3334 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2968 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3336 | MooringSystemInstallation
2969 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3336.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2970 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3337.5057 | TurbineInstallation
2971 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3338.8257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2972 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3340 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2973 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3342.3257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2974 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3344.3257 | TurbineInstallation
2975 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3347.3257 | TurbineInstallation
2976 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3347.9857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2977 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3352.8333 | MooredSubInstallation
2978 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3352.8333 | SemiSubStorageInstallation
2979 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3353.9857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2980 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3355.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2981 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3356.9857 | TurbineInstallation
2982 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3358.3057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2983 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3360 | MooredSubInstallation
2984 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 64.5 | 0 | ACTION | 3360 | MooredSubInstallation
2985 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3360 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2986 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3360 | SemiSubStorageInstallation
2987 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 64.5 | 0 | ACTION | 3360 | SemiSubStorageInstallation
2988 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3362 | MooringSystemInstallation
2989 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3364.3057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
2990 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3364.8333 | MooredSubInstallation
2991 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3364.8333 | MooredSubInstallation | site | [6 empty] | 2
2992 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3364.8333 | SemiSubStorageInstallation
2993 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3364.8333 | SemiSubStorageInstallation | site | [6 empty] | 2
2994 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3366 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
2995 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3367.3057 | TurbineInstallation
2996 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3368 | MooredSubInstallation
2997 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3368 | SemiSubStorageInstallation
2998 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3368.3057 | TurbineInstallation
2999 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3369.6257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3000 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3375.6257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3001 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3376.6257 | TurbineInstallation
3002 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3377.6257 | TurbineInstallation
3003 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3378.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3004 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3380 | MooredSubInstallation
3005 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3380 | SemiSubStorageInstallation
3006 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3381.5 | MooredSubInstallation | [7 empty] | 3
3007 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3381.5 | SemiSubStorageInstallation | [7 empty] | 3
3008 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3381.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3009 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3382.4457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3010 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3383.4457 | TurbineInstallation
3011 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3384.7657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3012 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3386 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3013 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3388.2657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3014 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3389.2657 | TurbineInstallation
3015 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3390.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3016 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3392 | MooredSubInstallation
3017 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3392 | SemiSubStorageInstallation
3018 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3394.0857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3019 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3396 | MooringSystemInstallation
3020 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3401 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3021 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3404 | MooredSubInstallation
3022 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3404 | SemiSubStorageInstallation
3023 |  | Export Cable Installation Vessel | Lay/Bury Cable | 79.0416 | 395207.9486 | ACTION | 3405.7804 | ExportCableInstallation |  |  |  | ExportCableInstallation | 2 | 25 | 11.5
3024 |  | Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 3407.7804 | ExportCableInstallation
3025 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3408.3714 | TurbineInstallation
3026 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3411 | MooringSystemInstallation
3027 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3412.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3028 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3413 | MooringSystemInstallation
3029 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3416.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3030 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3417 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3031 |  | Turbine Assembly Line 1 | Delay | 52 | 0 | ACTION | 3456 | MooredSubInstallation
3032 |  | Turbine Assembly Line 1 | Delay | 52 | 0 | ACTION | 3456 | SemiSubStorageInstallation
3033 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3463 | MooredSubInstallation
3034 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3463 | SemiSubStorageInstallation
3035 |  | Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 3466 | MooredSubInstallation
3036 |  | Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 3466 | SemiSubStorageInstallation
3037 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3469.5 | MooredSubInstallation
3038 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3469.5 | SemiSubStorageInstallation
3039 |  | Mooring System Installation Vessel | Delay | 80 | 333333.3333 | ACTION | 3497 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3040 |  | Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 3503.5 | MooredSubInstallation
3041 |  | Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 3503.5 | SemiSubStorageInstallation
3042 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3507 | MooredSubInstallation
3043 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3507 | SemiSubStorageInstallation
3044 |  | WTIV | Delay | 91 | 1895833.3333 | ACTION | 3507.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3045 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3510.5 | MooredSubInstallation
3046 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3510.5 | SemiSubStorageInstallation
3047 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3511.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3048 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3512.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3049 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3512.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3050 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3514.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3051 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3515.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3052 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3517 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3053 |  | Export Cable Installation Vessel | Delay | 111 | 555000 | ACTION | 3518.7804 | ExportCableInstallation |  |  |  | ExportCableInstallation
3054 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3519 | MooringSystemInstallation
3055 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3519.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3056 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3523 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3057 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3523.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3058 |  | Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 3524.2804 | ExportCableInstallation |  |  |  | ExportCableInstallation
3059 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3527.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3060 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3528 | MooredSubInstallation
3061 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3528 | SemiSubStorageInstallation
3062 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3529.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3063 |  | Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 3529.7804 | ExportCableInstallation |  |  |  | ExportCableInstallation
3064 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3530.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3065 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3532.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3066 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3534.5 | MooredSubInstallation
3067 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 153 | 191250 | ACTION | 3534.5 | MooredSubInstallation
3068 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3534.5 | SemiSubStorageInstallation
3069 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 153 | 191250 | ACTION | 3534.5 | SemiSubStorageInstallation
3070 |  | Export Cable Installation Vessel | Transit | 8.6957 | 43478.2609 | ACTION | 3538.4761 | ExportCableInstallation
3071 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3538.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3072 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3540.5 | MooredSubInstallation | [7 empty] | 3
3073 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3540.5 | SemiSubStorageInstallation | [7 empty] | 3
3074 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3542.5 | MooredSubInstallation
3075 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3542.5 | SemiSubStorageInstallation
3076 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3543 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3077 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3545 | MooringSystemInstallation
3078 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3546.6571 | TurbineInstallation
3079 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3548.6571 | TurbineInstallation
3080 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3549 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3081 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3551.6571 | TurbineInstallation
3082 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3552.3171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3083 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3554.5 | MooredSubInstallation
3084 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3554.5 | SemiSubStorageInstallation
3085 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3557.1667 | MooredSubInstallation | [7 empty] | 3
3086 |  | Multi-Purpose Support Vessel | Delay | 192.3333 | 801388.8889 | ACTION | 3557.1667 | MooredSubInstallation | Site
3087 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3557.1667 | SemiSubStorageInstallation | [7 empty] | 3
3088 |  | Multi-Purpose Support Vessel | Delay | 192.3333 | 801388.8889 | ACTION | 3557.1667 | SemiSubStorageInstallation | Site
3089 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3558.3171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3090 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3559.1667 | MooredSubInstallation
3091 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3559.1667 | SemiSubStorageInstallation
3092 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3561.3171 | TurbineInstallation
3093 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3562.6371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3094 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3564.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3095 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3565.1667 | MooredSubInstallation
3096 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3565.1667 | SemiSubStorageInstallation
3097 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3566.5 | MooredSubInstallation
3098 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3566.5 | SemiSubStorageInstallation
3099 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3568.6371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3100 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3569 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3101 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3571 | MooringSystemInstallation
3102 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3571.6371 | TurbineInstallation
3103 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3572.6371 | TurbineInstallation
3104 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3573.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3105 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3575 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3106 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3578.5 | MooredSubInstallation
3107 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3578.5 | SemiSubStorageInstallation
3108 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3579.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3109 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3580.9571 | TurbineInstallation
3110 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3581.9571 | TurbineInstallation
3111 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3583.2771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3112 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3585.5 | MooredSubInstallation
3113 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3585.5 | SemiSubStorageInstallation
3114 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3586.7771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3115 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3587.1667 | MooredSubInstallation
3116 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3587.1667 | SemiSubStorageInstallation
3117 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3587.7771 | TurbineInstallation
3118 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3589 | MooredSubInstallation
3119 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3589 | SemiSubStorageInstallation
3120 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3589.0971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3121 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3590.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3122 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3592.5 | MooredSubInstallation
3123 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3592.5 | SemiSubStorageInstallation
3124 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3592.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3125 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3593.5971 | TurbineInstallation
3126 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3594.9171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3127 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3595 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3128 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3596 | MooredSubInstallation
3129 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3596 | SemiSubStorageInstallation
3130 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3598.4171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3131 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3599.1667 | MooredSubInstallation
3132 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3599.1667 | MooredSubInstallation | site | [6 empty] | 2
3133 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3599.1667 | SemiSubStorageInstallation
3134 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3599.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
3135 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3600.4171 | TurbineInstallation
3136 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3603.4171 | TurbineInstallation
3137 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3604.0771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3138 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3605 | MooringSystemInstallation
3139 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3610 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3140 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3610.0771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3141 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3613.0771 | TurbineInstallation
3142 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3614.3971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3143 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3615.8333 | MooredSubInstallation | [7 empty] | 3
3144 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3615.8333 | SemiSubStorageInstallation | [7 empty] | 3
3145 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3620 | MooredSubInstallation
3146 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 4.1667 | 5208.3333 | ACTION | 3620 | MooredSubInstallation
3147 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3620 | MooringSystemInstallation
3148 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3620 | SemiSubStorageInstallation
3149 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 4.1667 | 5208.3333 | ACTION | 3620 | SemiSubStorageInstallation
3150 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3620.3971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3151 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3622 | MooringSystemInstallation
3152 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3623.3971 | TurbineInstallation
3153 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3624.3971 | TurbineInstallation
3154 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3625.7171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3155 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3626 | MooredSubInstallation | [7 empty] | 3
3156 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3626 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3157 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3626 | SemiSubStorageInstallation | [7 empty] | 3
3158 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3631.7171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3159 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3632.7171 | TurbineInstallation
3160 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3633.7171 | TurbineInstallation
3161 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3635.0371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3162 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3638.5371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3163 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3639.5371 | TurbineInstallation
3164 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3640.8571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3165 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3641.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3166 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3642.6667 | MooredSubInstallation | [7 empty] | 3
3167 |  | Multi-Purpose Support Vessel | Delay | 43.5 | 181250 | ACTION | 3642.6667 | MooredSubInstallation | Site
3168 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3642.6667 | SemiSubStorageInstallation | [7 empty] | 3
3169 |  | Multi-Purpose Support Vessel | Delay | 43.5 | 181250 | ACTION | 3642.6667 | SemiSubStorageInstallation | Site
3170 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3644.3571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3171 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3644.6667 | MooredSubInstallation
3172 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3644.6667 | SemiSubStorageInstallation
3173 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3645.3571 | TurbineInstallation
3174 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3646 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3175 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3646.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3176 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3648 | MooringSystemInstallation
3177 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3650.1771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3178 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3650.6667 | MooredSubInstallation
3179 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3650.6667 | SemiSubStorageInstallation
3180 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3652 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3181 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 3656.6667 | MooredSubInstallation
3182 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 3656.6667 | SemiSubStorageInstallation
3183 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 3657.6667 | MooredSubInstallation
3184 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 3657.6667 | SemiSubStorageInstallation
3185 |  | Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | ACTION | 3659.6667 | MooredSubInstallation
3186 |  | Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | ACTION | 3659.6667 | SemiSubStorageInstallation
3187 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3664.4629 | TurbineInstallation
3188 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3667.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3189 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3668.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3190 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 3670.6667 | MooredSubInstallation
3191 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 3670.6667 | SemiSubStorageInstallation
3192 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3672 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3193 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3674 | MooringSystemInstallation
3194 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3678 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3195 |  | WTIV | Delay | 21 | 437500 | ACTION | 3689.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3196 |  | Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | ACTION | 3690.6667 | MooredSubInstallation
3197 |  | Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | ACTION | 3690.6667 | SemiSubStorageInstallation
3198 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 3691.6667 | MooredSubInstallation
3199 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 3691.6667 | SemiSubStorageInstallation
3200 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3693.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3201 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3693.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3202 |  | Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 3695.6667 | MooredSubInstallation
3203 |  | Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 3695.6667 | SemiSubStorageInstallation
3204 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3696 | MooredSubInstallation
3205 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76 | 0 | ACTION | 3696 | MooredSubInstallation
3206 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3696 | SemiSubStorageInstallation
3207 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76 | 0 | ACTION | 3696 | SemiSubStorageInstallation
3208 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 3696.6667 | MooredSubInstallation
3209 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 3696.6667 | SemiSubStorageInstallation
3210 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3697.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3211 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3698 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3212 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3698.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3213 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3700 | MooringSystemInstallation
3214 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3700.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3215 |  | Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 3700.6667 | MooredSubInstallation
3216 |  | Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 3700.6667 | SemiSubStorageInstallation
3217 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3701.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3218 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3704 | MooredSubInstallation
3219 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3704 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3220 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3704 | SemiSubStorageInstallation
3221 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3705.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3222 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 3708.6667 | MooredSubInstallation
3223 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 3708.6667 | SemiSubStorageInstallation
3224 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3709.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3225 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3713.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3226 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3715.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3227 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3716 | MooredSubInstallation
3228 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3716 | SemiSubStorageInstallation
3229 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3716.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3230 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3718.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3231 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 10 | 41666.6667 | ACTION | 3718.6667 | MooredSubInstallation
3232 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 10 | 41666.6667 | ACTION | 3718.6667 | SemiSubStorageInstallation
3233 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3719.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3234 |  | WTIV | Transit | 5 | 104166.6667 | ACTION | 3723.4629 | TurbineInstallation
3235 |  | WTIV | Delay | 1 | 20833.3333 | ACTION | 3724.4629 | TurbineInstallation
3236 |  | Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 3724.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3237 |  | Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 3727.6667 | MooredSubInstallation
3238 |  | Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 3727.6667 | SemiSubStorageInstallation
3239 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3729 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3240 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 3729.6667 | MooredSubInstallation
3241 |  | Towing Group 1 | Positioning Support | 87 | 217500 | ACTION | 3729.6667 | MooredSubInstallation | site | [6 empty] | 2
3242 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 3729.6667 | SemiSubStorageInstallation
3243 |  | Towing Group 1 | Positioning Support | 87 | 217500 | ACTION | 3729.6667 | SemiSubStorageInstallation | site | [6 empty] | 2
3244 |  | WTIV | Transit | 9.2857 | 193452.381 | ACTION | 3733.7486 | TurbineInstallation
3245 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3735.7486 | TurbineInstallation
3246 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3738.7486 | TurbineInstallation
3247 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3739 | MooringSystemInstallation
3248 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3744 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3249 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3746.3333 | MooredSubInstallation | [7 empty] | 3
3250 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3746.3333 | SemiSubStorageInstallation | [7 empty] | 3
3251 |  | WTIV | Delay | 13 | 270833.3333 | ACTION | 3751.7486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3252 |  | Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 3752 | MooredSubInstallation
3253 |  | Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 3752 | SemiSubStorageInstallation
3254 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3752.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3255 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3754 | MooringSystemInstallation
3256 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3756 | MooringSystemInstallation
3257 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3758.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3258 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3760 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3259 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3761.4086 | TurbineInstallation
3260 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3762.7286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3261 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3764 | MooredSubInstallation
3262 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3764 | SemiSubStorageInstallation
3263 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3768.7286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3264 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3771.7286 | TurbineInstallation
3265 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3772.7286 | TurbineInstallation
3266 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3774.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3267 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3775.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3268 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3776 | MooredSubInstallation
3269 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3776 | SemiSubStorageInstallation
3270 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3780 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3271 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3780.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3272 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3781.0486 | TurbineInstallation
3273 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3782 | MooringSystemInstallation
3274 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3782.0486 | TurbineInstallation
3275 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3783 | MooredSubInstallation
3276 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3783 | SemiSubStorageInstallation
3277 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3783.3686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3278 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3786 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3279 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3786.5 | MooredSubInstallation
3280 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3786.5 | SemiSubStorageInstallation
3281 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3786.8686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3282 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3787.8686 | TurbineInstallation
3283 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3789.1886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3284 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3790 | MooredSubInstallation
3285 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3790 | SemiSubStorageInstallation
3286 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3792.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3287 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3793.6886 | TurbineInstallation
3288 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3801.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3289 |  | Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 3805.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3290 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3810 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3291 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3812 | MooringSystemInstallation
3292 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3816 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3293 |  | Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 3843 | MooredSubInstallation
3294 |  | Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 3843 | SemiSubStorageInstallation
3295 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3846.5 | MooredSubInstallation
3296 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3846.5 | SemiSubStorageInstallation
3297 |  | Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 3863 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3298 |  | WTIV | Delay | 70 | 1458333.3333 | ACTION | 3863.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3299 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3864 | MooredSubInstallation
3300 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3864 | SemiSubStorageInstallation
3301 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3865.0086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3302 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3868.5086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3303 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3870.5 | MooredSubInstallation
3304 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 124.1667 | 155208.3333 | ACTION | 3870.5 | MooredSubInstallation
3305 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3870.5 | SemiSubStorageInstallation
3306 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 124.1667 | 155208.3333 | ACTION | 3870.5 | SemiSubStorageInstallation
3307 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3870.5086 | TurbineInstallation
3308 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3873.5086 | TurbineInstallation
3309 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3874.1686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3310 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3876.5 | MooredSubInstallation | [7 empty] | 3
3311 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3876.5 | SemiSubStorageInstallation | [7 empty] | 3
3312 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3878.5 | MooredSubInstallation
3313 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3878.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3314 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3878.5 | SemiSubStorageInstallation
3315 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3880.1686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3316 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3883 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3317 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3883.1686 | TurbineInstallation
3318 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3884.4886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3319 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3885 | MooringSystemInstallation
3320 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3889 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3321 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3890.4886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3322 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3890.5 | MooredSubInstallation
3323 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3890.5 | SemiSubStorageInstallation
3324 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3893.1667 | MooredSubInstallation | [7 empty] | 3
3325 |  | Multi-Purpose Support Vessel | Delay | 163.5 | 681250 | ACTION | 3893.1667 | MooredSubInstallation | Site
3326 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3893.1667 | SemiSubStorageInstallation | [7 empty] | 3
3327 |  | Multi-Purpose Support Vessel | Delay | 163.5 | 681250 | ACTION | 3893.1667 | SemiSubStorageInstallation | Site
3328 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 3893.4886 | TurbineInstallation
3329 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3894.4886 | TurbineInstallation
3330 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3895.1667 | MooredSubInstallation
3331 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3895.1667 | SemiSubStorageInstallation
3332 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 3895.8086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3333 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3901.1667 | MooredSubInstallation
3334 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3901.1667 | SemiSubStorageInstallation
3335 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 3901.8086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3336 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3902.5 | MooredSubInstallation
3337 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3902.5 | SemiSubStorageInstallation
3338 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 3902.8086 | TurbineInstallation
3339 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3903.8086 | TurbineInstallation
3340 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3904.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3341 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3905.1286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3342 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3908.6286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3343 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3909 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3344 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3909.6286 | TurbineInstallation
3345 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3910.9486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3346 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3914.4486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3347 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3914.5 | MooredSubInstallation
3348 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 3914.5 | SemiSubStorageInstallation
3349 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 3915.4486 | TurbineInstallation
3350 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 3916.7686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3351 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3919 | MooringSystemInstallation
3352 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 3920.2686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3353 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3921.5 | MooredSubInstallation
3354 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 3921.5 | SemiSubStorageInstallation
3355 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3923.1667 | MooredSubInstallation
3356 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 3923.1667 | SemiSubStorageInstallation
3357 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3924 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3358 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3925 | MooredSubInstallation
3359 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3925 | SemiSubStorageInstallation
3360 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3928.5 | MooredSubInstallation
3361 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3928.5 | SemiSubStorageInstallation
3362 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3932 | MooredSubInstallation
3363 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3932 | SemiSubStorageInstallation
3364 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3934 | MooringSystemInstallation
3365 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3934.5543 | TurbineInstallation
3366 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3935.1667 | MooredSubInstallation
3367 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3935.1667 | MooredSubInstallation | site | [6 empty] | 2
3368 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 3935.1667 | SemiSubStorageInstallation
3369 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 3935.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
3370 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3936 | MooringSystemInstallation
3371 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3938.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3372 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3940 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3373 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3942.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3374 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3946.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3375 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3948.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3376 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3949.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3377 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3951.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3378 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3951.8333 | MooredSubInstallation | [7 empty] | 3
3379 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 3951.8333 | SemiSubStorageInstallation | [7 empty] | 3
3380 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3955.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3381 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3955.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3382 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3956 | MooredSubInstallation
3383 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 4.1667 | 5208.3333 | ACTION | 3956 | MooredSubInstallation
3384 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3956 | SemiSubStorageInstallation
3385 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 4.1667 | 5208.3333 | ACTION | 3956 | SemiSubStorageInstallation
3386 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 3959.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3387 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3960 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3388 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3962 | MooredSubInstallation | [7 empty] | 3
3389 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3962 | MooringSystemInstallation
3390 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 3962 | SemiSubStorageInstallation | [7 empty] | 3
3391 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 3963.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3392 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3964.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3393 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3966 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3394 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3966.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3395 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 3967.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3396 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 3978.6667 | MooredSubInstallation | [7 empty] | 3
3397 |  | Multi-Purpose Support Vessel | Delay | 43.5 | 181250 | ACTION | 3978.6667 | MooredSubInstallation | Site
3398 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 3978.6667 | SemiSubStorageInstallation | [7 empty] | 3
3399 |  | Multi-Purpose Support Vessel | Delay | 43.5 | 181250 | ACTION | 3978.6667 | SemiSubStorageInstallation | Site
3400 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 3980.6667 | MooredSubInstallation
3401 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 3980.6667 | SemiSubStorageInstallation
3402 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 3981.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3403 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 3981.84 | TurbineInstallation
3404 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 3983.84 | TurbineInstallation
3405 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 3986 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3406 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3986.6667 | MooredSubInstallation
3407 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 3986.6667 | SemiSubStorageInstallation
3408 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3986.84 | TurbineInstallation
3409 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 3987.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3410 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3988 | MooringSystemInstallation
3411 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3992 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3412 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 3993.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3413 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 3996.5 | TurbineInstallation
3414 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 3997.82 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3415 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4003.82 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3416 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4006.82 | TurbineInstallation
3417 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4007.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3418 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4007.82 | TurbineInstallation
3419 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4008.6667 | MooredSubInstallation
3420 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4008.6667 | SemiSubStorageInstallation
3421 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4009.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3422 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4012 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3423 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4014 | MooringSystemInstallation
3424 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4015.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3425 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4016.14 | TurbineInstallation
3426 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4017.14 | TurbineInstallation
3427 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4018 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3428 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4018.46 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3429 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4020.6667 | MooredSubInstallation
3430 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4020.6667 | MooredSubInstallation | site | [6 empty] | 2
3431 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4020.6667 | SemiSubStorageInstallation
3432 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4020.6667 | SemiSubStorageInstallation | site | [6 empty] | 2
3433 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4021.96 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3434 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4022.96 | TurbineInstallation
3435 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4024.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3436 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4032 | MooredSubInstallation
3437 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76 | 0 | ACTION | 4032 | MooredSubInstallation
3438 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4032 | SemiSubStorageInstallation
3439 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76 | 0 | ACTION | 4032 | SemiSubStorageInstallation
3440 |  | WTIV | Delay | 9 | 187500 | ACTION | 4033.28 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3441 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4033.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3442 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4036.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3443 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4037.3333 | MooredSubInstallation | [7 empty] | 3
3444 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4037.3333 | SemiSubStorageInstallation | [7 empty] | 3
3445 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4037.78 | TurbineInstallation
3446 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4038 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3447 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4039.1 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3448 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4040 | MooredSubInstallation
3449 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4040 | SemiSubStorageInstallation
3450 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4042.6 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3451 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4044.6 | TurbineInstallation
3452 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4047.6 | TurbineInstallation
3453 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4048 | MooringSystemInstallation
3454 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4048.26 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3455 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4052 | MooredSubInstallation
3456 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4052 | SemiSubStorageInstallation
3457 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4053 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3458 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4054.26 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3459 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4057.26 | TurbineInstallation
3460 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4058.58 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3461 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4063 | MooringSystemInstallation
3462 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4065 | MooringSystemInstallation
3463 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4069 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3464 |  | WTIV | Delay | 13 | 270833.3333 | ACTION | 4071.58 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3465 |  | Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 4072 | MooredSubInstallation
3466 |  | Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 4072 | SemiSubStorageInstallation
3467 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4077.58 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3468 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4080.58 | TurbineInstallation
3469 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4081.58 | TurbineInstallation
3470 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4082.9 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3471 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4084 | MooredSubInstallation
3472 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4084 | SemiSubStorageInstallation
3473 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4084.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3474 |  | Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 4088 | MooredSubInstallation
3475 |  | Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 4088 | SemiSubStorageInstallation
3476 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4089 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3477 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4091 | MooringSystemInstallation
3478 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4095 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3479 |  | WTIV | Delay | 17 | 354166.6667 | ACTION | 4099.9 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3480 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4100 | MooredSubInstallation
3481 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4100 | SemiSubStorageInstallation
3482 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4105.9 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3483 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4106.9 | TurbineInstallation
3484 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4107 | MooredSubInstallation
3485 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4107 | SemiSubStorageInstallation
3486 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4107.9 | TurbineInstallation
3487 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4108 | MooredSubInstallation
3488 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4108 | SemiSubStorageInstallation
3489 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4109.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3490 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4110.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3491 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4111.5 | MooredSubInstallation
3492 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4111.5 | SemiSubStorageInstallation
3493 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4112.72 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3494 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4113.72 | TurbineInstallation
3495 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4115 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3496 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4115.04 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3497 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4117 | MooringSystemInstallation
3498 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4118.54 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3499 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4119.54 | TurbineInstallation
3500 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4120.86 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3501 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4121 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3502 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4124.36 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3503 |  | Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 4128.5 | MooredSubInstallation
3504 |  | Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 4128.5 | SemiSubStorageInstallation
3505 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4132 | MooredSubInstallation
3506 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4132 | SemiSubStorageInstallation
3507 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4135.5 | MooredSubInstallation
3508 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4135.5 | SemiSubStorageInstallation
3509 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4136.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3510 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4138.6457 | TurbineInstallation
3511 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4141 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3512 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4142.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3513 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4143 | MooringSystemInstallation
3514 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4146.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3515 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4147 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3516 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4150.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3517 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4152.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3518 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4153.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3519 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4155.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3520 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4159.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3521 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4159.5 | MooredSubInstallation
3522 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 122.1667 | 152708.3333 | ACTION | 4159.5 | MooredSubInstallation
3523 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4159.5 | SemiSubStorageInstallation
3524 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 122.1667 | 152708.3333 | ACTION | 4159.5 | SemiSubStorageInstallation
3525 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4162.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3526 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4163.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3527 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4165.5 | MooredSubInstallation | [7 empty] | 3
3528 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4165.5 | SemiSubStorageInstallation | [7 empty] | 3
3529 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4167 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3530 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4167.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3531 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4168.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3532 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4170.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3533 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4171.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3534 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4177 | MooringSystemInstallation
3535 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4182 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3536 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 4182.1667 | MooredSubInstallation | [7 empty] | 3
3537 |  | Multi-Purpose Support Vessel | Delay | 161.5 | 672916.6667 | ACTION | 4182.1667 | MooredSubInstallation | Site
3538 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 4182.1667 | SemiSubStorageInstallation | [7 empty] | 3
3539 |  | Multi-Purpose Support Vessel | Delay | 161.5 | 672916.6667 | ACTION | 4182.1667 | SemiSubStorageInstallation | Site
3540 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 4184.1667 | MooredSubInstallation
3541 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 4184.1667 | SemiSubStorageInstallation
3542 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4185.9314 | TurbineInstallation
3543 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4187.9314 | TurbineInstallation
3544 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4190.1667 | MooredSubInstallation
3545 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4190.1667 | SemiSubStorageInstallation
3546 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4190.9314 | TurbineInstallation
3547 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4191.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3548 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4192 | MooringSystemInstallation
3549 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4194 | MooringSystemInstallation
3550 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4197.5914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3551 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4198 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3552 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4200 | MooredSubInstallation
3553 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 40.5 | 0 | ACTION | 4200 | MooredSubInstallation
3554 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4200 | SemiSubStorageInstallation
3555 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 40.5 | 0 | ACTION | 4200 | SemiSubStorageInstallation
3556 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4200.5914 | TurbineInstallation
3557 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4201.9114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3558 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4207.9114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3559 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4208 | MooredSubInstallation
3560 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4208 | SemiSubStorageInstallation
3561 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4210.9114 | TurbineInstallation
3562 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4211.9114 | TurbineInstallation
3563 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4212.1667 | MooredSubInstallation
3564 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4212.1667 | SemiSubStorageInstallation
3565 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4213.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3566 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4213.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3567 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4218 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3568 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4219.2314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3569 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4220 | MooredSubInstallation
3570 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4220 | MooringSystemInstallation
3571 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4220 | SemiSubStorageInstallation
3572 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4220.2314 | TurbineInstallation
3573 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4221.2314 | TurbineInstallation
3574 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4222.5514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3575 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4224 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3576 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4224.1667 | MooredSubInstallation
3577 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4224.1667 | MooredSubInstallation | site | [6 empty] | 2
3578 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4224.1667 | SemiSubStorageInstallation
3579 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4224.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
3580 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4226.0514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3581 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4227.0514 | TurbineInstallation
3582 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4228.3714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3583 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4231.8714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3584 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4232 | MooredSubInstallation
3585 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4232 | SemiSubStorageInstallation
3586 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4232.8714 | TurbineInstallation
3587 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4234.1914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3588 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4237.6914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3589 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4239.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3590 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4239.6914 | TurbineInstallation
3591 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4240.8333 | MooredSubInstallation | [7 empty] | 3
3592 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4240.8333 | SemiSubStorageInstallation | [7 empty] | 3
3593 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4242.6914 | TurbineInstallation
3594 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4243.3514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3595 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4244 | MooredSubInstallation
3596 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4244 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3597 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4244 | SemiSubStorageInstallation
3598 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4246 | MooringSystemInstallation
3599 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4249.3514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3600 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4250 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3601 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4251 | MooredSubInstallation
3602 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4251 | SemiSubStorageInstallation
3603 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4252 | MooredSubInstallation
3604 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4252 | SemiSubStorageInstallation
3605 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4252.3514 | TurbineInstallation
3606 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4253.6714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3607 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4255.5 | MooredSubInstallation
3608 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4255.5 | SemiSubStorageInstallation
3609 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4259 | MooredSubInstallation
3610 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4259 | SemiSubStorageInstallation
3611 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4259.6714 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3612 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4262.5 | MooredSubInstallation
3613 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4262.5 | SemiSubStorageInstallation
3614 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4262.6714 | TurbineInstallation
3615 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4263.6714 | TurbineInstallation
3616 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4264.9914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3617 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4265.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3618 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4270 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3619 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4270.9914 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3620 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4271.9914 | TurbineInstallation
3621 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4272 | MooringSystemInstallation
3622 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4272.9914 | TurbineInstallation
3623 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4274.3114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3624 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4276 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3625 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4277.8114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3626 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4278.8114 | TurbineInstallation
3627 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4280.1314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3628 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4283.6314 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3629 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4284.6314 | TurbineInstallation
3630 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4285.9514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3631 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4286.5 | MooredSubInstallation
3632 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 45.6667 | 57083.3333 | ACTION | 4286.5 | MooredSubInstallation
3633 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4286.5 | SemiSubStorageInstallation
3634 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 45.6667 | 57083.3333 | ACTION | 4286.5 | SemiSubStorageInstallation
3635 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4289.4514 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3636 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4291.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3637 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4292.5 | MooredSubInstallation | [7 empty] | 3
3638 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4292.5 | SemiSubStorageInstallation | [7 empty] | 3
3639 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4296 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3640 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4303.7371 | TurbineInstallation
3641 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4306 | MooringSystemInstallation
3642 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4307.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3643 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 4309.1667 | MooredSubInstallation | [7 empty] | 3
3644 |  | Multi-Purpose Support Vessel | Delay | 85 | 354166.6667 | ACTION | 4309.1667 | MooredSubInstallation | Site
3645 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 4309.1667 | SemiSubStorageInstallation | [7 empty] | 3
3646 |  | Multi-Purpose Support Vessel | Delay | 85 | 354166.6667 | ACTION | 4309.1667 | SemiSubStorageInstallation | Site
3647 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4311 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3648 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 4311.1667 | MooredSubInstallation
3649 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 4311.1667 | SemiSubStorageInstallation
3650 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4311.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3651 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4315.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3652 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4317.1667 | MooredSubInstallation
3653 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4317.1667 | SemiSubStorageInstallation
3654 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4317.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3655 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4318.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3656 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4320.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3657 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4321 | MooringSystemInstallation
3658 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4323 | MooringSystemInstallation
3659 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4324.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3660 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4327 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3661 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4328.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3662 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4332.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3663 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4333.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3664 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4335.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3665 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4336.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3666 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4339.1667 | MooredSubInstallation
3667 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4339.1667 | SemiSubStorageInstallation
3668 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4342.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3669 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4347 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3670 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4349 | MooringSystemInstallation
3671 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4351.0229 | TurbineInstallation
3672 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4351.1667 | MooredSubInstallation
3673 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4351.1667 | MooredSubInstallation | site | [6 empty] | 2
3674 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4351.1667 | SemiSubStorageInstallation
3675 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4351.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
3676 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4353 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3677 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4353.0229 | TurbineInstallation
3678 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4356.0229 | TurbineInstallation
3679 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4356.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3680 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4362.6829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3681 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4365.6829 | TurbineInstallation
3682 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4367.0029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3683 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4367.8333 | MooredSubInstallation | [7 empty] | 3
3684 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4367.8333 | SemiSubStorageInstallation | [7 empty] | 3
3685 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4368 | MooredSubInstallation
3686 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 81.5 | 0 | ACTION | 4368 | MooredSubInstallation
3687 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4368 | SemiSubStorageInstallation
3688 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 81.5 | 0 | ACTION | 4368 | SemiSubStorageInstallation
3689 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4368.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3690 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4373 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3691 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4373.0029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3692 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4375 | MooringSystemInstallation
3693 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4376 | MooredSubInstallation
3694 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4376 | SemiSubStorageInstallation
3695 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4376.0029 | TurbineInstallation
3696 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4377.0029 | TurbineInstallation
3697 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4378.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3698 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4379 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3699 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4384.3229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3700 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4385.3229 | TurbineInstallation
3701 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4386.3229 | TurbineInstallation
3702 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4387.6429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3703 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4388 | MooredSubInstallation
3704 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4388 | SemiSubStorageInstallation
3705 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4391.1429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3706 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4392.1429 | TurbineInstallation
3707 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4393.4629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3708 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4394.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3709 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4396.9629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3710 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4397.9629 | TurbineInstallation
3711 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4399 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3712 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4399.2829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3713 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4400 | MooredSubInstallation
3714 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4400 | SemiSubStorageInstallation
3715 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4401 | MooringSystemInstallation
3716 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4402.7829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3717 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4404.7829 | TurbineInstallation
3718 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4405 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3719 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4407.7829 | TurbineInstallation
3720 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4408.4429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3721 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4412 | MooredSubInstallation
3722 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4412 | SemiSubStorageInstallation
3723 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4414.4429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3724 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4417.4429 | TurbineInstallation
3725 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4418.7629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3726 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4419 | MooredSubInstallation
3727 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4419 | SemiSubStorageInstallation
3728 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4420.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3729 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4422.5 | MooredSubInstallation
3730 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4422.5 | SemiSubStorageInstallation
3731 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4424.7629 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3732 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4425 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3733 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4426 | MooredSubInstallation
3734 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4426 | SemiSubStorageInstallation
3735 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4427.7629 | TurbineInstallation
3736 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4428.7629 | TurbineInstallation
3737 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4429.5 | MooredSubInstallation
3738 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4429.5 | SemiSubStorageInstallation
3739 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4430.0829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3740 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4435 | MooringSystemInstallation
3741 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4436.0829 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3742 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4437.0829 | TurbineInstallation
3743 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4438.0829 | TurbineInstallation
3744 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4439.4029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3745 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4440 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3746 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4442.9029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3747 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4443.9029 | TurbineInstallation
3748 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4445.2229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3749 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4448.7229 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3750 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4449.7229 | TurbineInstallation
3751 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4450 | MooringSystemInstallation
3752 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4451.0429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3753 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4452 | MooringSystemInstallation
3754 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4453.5 | MooredSubInstallation
3755 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 85.6667 | 107083.3333 | ACTION | 4453.5 | MooredSubInstallation
3756 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4453.5 | SemiSubStorageInstallation
3757 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 85.6667 | 107083.3333 | ACTION | 4453.5 | SemiSubStorageInstallation
3758 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4454.5429 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3759 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4456 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3760 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4459.5 | MooredSubInstallation | [7 empty] | 3
3761 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4459.5 | SemiSubStorageInstallation | [7 empty] | 3
3762 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4468.8286 | TurbineInstallation
3763 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4471.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3764 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4472.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3765 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4476 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3766 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 4476.1667 | MooredSubInstallation | [7 empty] | 3
3767 |  | Multi-Purpose Support Vessel | Delay | 125 | 520833.3333 | ACTION | 4476.1667 | MooredSubInstallation | Site
3768 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 4476.1667 | SemiSubStorageInstallation | [7 empty] | 3
3769 |  | Multi-Purpose Support Vessel | Delay | 125 | 520833.3333 | ACTION | 4476.1667 | SemiSubStorageInstallation | Site
3770 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4476.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3771 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4478 | MooringSystemInstallation
3772 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 4478.1667 | MooredSubInstallation
3773 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 4478.1667 | SemiSubStorageInstallation
3774 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4480.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3775 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4482 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3776 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4482.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3777 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4483.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3778 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4484.1667 | MooredSubInstallation
3779 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4484.1667 | SemiSubStorageInstallation
3780 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4485.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3781 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4489.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3782 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4493.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3783 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4497.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3784 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4497.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3785 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4498.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3786 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4500.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3787 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4501.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3788 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4502 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3789 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4504 | MooringSystemInstallation
3790 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4506.1667 | MooredSubInstallation
3791 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4506.1667 | SemiSubStorageInstallation
3792 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4508 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3793 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4516.1143 | TurbineInstallation
3794 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4518.1143 | TurbineInstallation
3795 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4518.1667 | MooredSubInstallation
3796 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4518.1667 | MooredSubInstallation | site | [6 empty] | 2
3797 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4518.1667 | SemiSubStorageInstallation
3798 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4518.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
3799 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4521.1143 | TurbineInstallation
3800 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4521.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3801 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4523.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3802 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4527.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3803 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4528 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3804 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4530 | MooringSystemInstallation
3805 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4530.7743 | TurbineInstallation
3806 |  | WTIV | Delay | 1 | 20833.3333 | ACTION | 4531.7743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3807 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4533.0943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3808 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4534 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3809 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4534.8333 | MooredSubInstallation | [7 empty] | 3
3810 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4534.8333 | SemiSubStorageInstallation | [7 empty] | 3
3811 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4536 | MooredSubInstallation
3812 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 4536 | MooredSubInstallation
3813 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4536 | SemiSubStorageInstallation
3814 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 4536 | SemiSubStorageInstallation
3815 |  | WTIV | Delay | 7 | 145833.3333 | ACTION | 4540.0943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3816 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4544 | MooredSubInstallation
3817 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4544 | SemiSubStorageInstallation
3818 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4546.0943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3819 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4549.0943 | TurbineInstallation
3820 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4549.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3821 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4550.0943 | TurbineInstallation
3822 |  | WTIV | Delay | 2 | 41666.6667 | ACTION | 4552.0943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3823 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4553.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3824 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4554 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3825 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4556 | MooredSubInstallation
3826 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4556 | SemiSubStorageInstallation
3827 |  | WTIV | Delay | 3 | 62500 | ACTION | 4556.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3828 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4557 | MooredSubInstallation
3829 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4557 | SemiSubStorageInstallation
3830 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4562.4143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3831 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4563.4143 | TurbineInstallation
3832 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4564 | MooringSystemInstallation
3833 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4564.4143 | TurbineInstallation
3834 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4565.7343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3835 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4569 | MooredSubInstallation
3836 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4569 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3837 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4569 | SemiSubStorageInstallation
3838 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4569.2343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3839 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4570.2343 | TurbineInstallation
3840 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4571.5543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3841 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4575.0543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3842 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4576.0543 | TurbineInstallation
3843 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4577.3743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3844 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4579 | MooringSystemInstallation
3845 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4580.8743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3846 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4581 | MooredSubInstallation
3847 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4581 | MooringSystemInstallation
3848 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4581 | SemiSubStorageInstallation
3849 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4582.8743 | TurbineInstallation
3850 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4585 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3851 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4585.8743 | TurbineInstallation
3852 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4586.5343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3853 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4588 | MooredSubInstallation
3854 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4588 | SemiSubStorageInstallation
3855 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4589 | MooredSubInstallation
3856 |  | Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4589 | SemiSubStorageInstallation
3857 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4592.5 | MooredSubInstallation
3858 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4592.5 | SemiSubStorageInstallation
3859 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4592.5343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3860 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4595.5343 | TurbineInstallation
3861 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4596 | MooredSubInstallation
3862 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4596 | SemiSubStorageInstallation
3863 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4596.8543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3864 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4599.5 | MooredSubInstallation
3865 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4599.5 | SemiSubStorageInstallation
3866 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4600.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3867 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4602.8543 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3868 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4605 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3869 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4605.8543 | TurbineInstallation
3870 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4606.8543 | TurbineInstallation
3871 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4607 | MooringSystemInstallation
3872 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4608.1743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3873 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4611 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3874 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4614.1743 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3875 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4615.1743 | TurbineInstallation
3876 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4616.1743 | TurbineInstallation
3877 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4617.4943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3878 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4620.9943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3879 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4621.9943 | TurbineInstallation
3880 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4623.3143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3881 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4623.5 | MooredSubInstallation
3882 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 4623.5 | MooredSubInstallation
3883 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4623.5 | SemiSubStorageInstallation
3884 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 4623.5 | SemiSubStorageInstallation
3885 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4626.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3886 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4626.8143 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3887 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4627.8143 | TurbineInstallation
3888 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4629.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3889 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4629.5 | MooredSubInstallation | [7 empty] | 3
3890 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4629.5 | SemiSubStorageInstallation | [7 empty] | 3
3891 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4631 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3892 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4633 | MooringSystemInstallation
3893 |  | WTIV | Delay | 7 | 145833.3333 | ACTION | 4636.1343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3894 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4637 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3895 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4639.6343 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3896 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4652.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3897 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4653.92 | TurbineInstallation
3898 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4657 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3899 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4657.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3900 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4659 | MooringSystemInstallation
3901 |  | Towing Group 1 | Delay | 30 | 112500 | ACTION | 4659.5 | MooredSubInstallation | [7 empty] | 3
3902 |  | Towing Group 1 | Delay | 30 | 112500 | ACTION | 4659.5 | SemiSubStorageInstallation | [7 empty] | 3
3903 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4661.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3904 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4663 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3905 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4665.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3906 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4667.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3907 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4668.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3908 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4670.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3909 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4674.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3910 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 4676.1667 | MooredSubInstallation | [7 empty] | 3
3911 |  | Multi-Purpose Support Vessel | Delay | 158 | 658333.3333 | ACTION | 4676.1667 | MooredSubInstallation | Site
3912 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 4676.1667 | SemiSubStorageInstallation | [7 empty] | 3
3913 |  | Multi-Purpose Support Vessel | Delay | 158 | 658333.3333 | ACTION | 4676.1667 | SemiSubStorageInstallation | Site
3914 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 4678.1667 | MooredSubInstallation
3915 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 4678.1667 | SemiSubStorageInstallation
3916 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4678.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3917 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4678.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3918 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4682.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3919 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4683 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3920 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4683.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3921 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4685.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3922 |  | Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 4686.1667 | MooredSubInstallation
3923 |  | Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 4686.1667 | SemiSubStorageInstallation
3924 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4686.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3925 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4692.1667 | MooredSubInstallation
3926 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4692.1667 | SemiSubStorageInstallation
3927 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4693 | MooringSystemInstallation
3928 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4698 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3929 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4701.2057 | TurbineInstallation
3930 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4703.2057 | TurbineInstallation
3931 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4704 | MooredSubInstallation
3932 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 4704 | MooredSubInstallation
3933 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4704 | SemiSubStorageInstallation
3934 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 4704 | SemiSubStorageInstallation
3935 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4706.2057 | TurbineInstallation
3936 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4706.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3937 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4708 | MooringSystemInstallation
3938 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4710 | MooringSystemInstallation
3939 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4712 | MooredSubInstallation
3940 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4712 | SemiSubStorageInstallation
3941 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4712.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3942 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4714 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3943 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4714.1667 | MooredSubInstallation
3944 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4714.1667 | SemiSubStorageInstallation
3945 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 4715.1667 | MooredSubInstallation
3946 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 4715.1667 | SemiSubStorageInstallation
3947 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4715.8657 | TurbineInstallation
3948 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 4716.1667 | MooredSubInstallation
3949 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 4716.1667 | SemiSubStorageInstallation
3950 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 4717.1667 | MooredSubInstallation
3951 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 4717.1667 | SemiSubStorageInstallation
3952 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4724 | MooredSubInstallation
3953 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4724 | SemiSubStorageInstallation
3954 |  | Multi-Purpose Support Vessel | Delay | 10 | 41666.6667 | ACTION | 4727.1667 | MooredSubInstallation
3955 |  | Multi-Purpose Support Vessel | Delay | 10 | 41666.6667 | ACTION | 4727.1667 | SemiSubStorageInstallation
3956 |  | WTIV | Delay | 12 | 250000 | ACTION | 4727.8657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3957 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 4729.1667 | MooredSubInstallation
3958 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 4729.1667 | SemiSubStorageInstallation
3959 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4729.1857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3960 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4729.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3961 |  | Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 4732.1667 | MooredSubInstallation
3962 |  | Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 4732.1667 | SemiSubStorageInstallation
3963 |  | WTIV | Delay | 3 | 62500 | ACTION | 4732.1857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3964 |  | Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 4733 | MooredSubInstallation
3965 |  | Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 4733 | SemiSubStorageInstallation
3966 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4734 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3967 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4736 | MooringSystemInstallation
3968 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4738.1857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3969 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4740 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3970 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 8 | 33333.3333 | ACTION | 4740.1667 | MooredSubInstallation
3971 |  | Towing Group 1 | Positioning Support | 64 | 160000 | ACTION | 4740.1667 | MooredSubInstallation | site | [6 empty] | 2
3972 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 8 | 33333.3333 | ACTION | 4740.1667 | SemiSubStorageInstallation
3973 |  | Towing Group 1 | Positioning Support | 64 | 160000 | ACTION | 4740.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
3974 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4741.1857 | TurbineInstallation
3975 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4742.1857 | TurbineInstallation
3976 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4743.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3977 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4745 | MooredSubInstallation
3978 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4745 | SemiSubStorageInstallation
3979 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4749.5057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3980 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4750.5057 | TurbineInstallation
3981 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4751.5057 | TurbineInstallation
3982 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4752.8257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3983 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4755.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3984 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4756.3257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3985 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4756.8333 | MooredSubInstallation | [7 empty] | 3
3986 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4756.8333 | SemiSubStorageInstallation | [7 empty] | 3
3987 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4757 | MooredSubInstallation
3988 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4757 | SemiSubStorageInstallation
3989 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4757.3257 | TurbineInstallation
3990 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4758.6457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3991 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4760 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3992 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4762 | MooringSystemInstallation
3993 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4762.1457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3994 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4763.1457 | TurbineInstallation
3995 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4764 | MooredSubInstallation
3996 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4764 | SemiSubStorageInstallation
3997 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4764.4657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
3998 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4766 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
3999 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4781.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4000 |  | Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 4788.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4001 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4793 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4002 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4795 | MooringSystemInstallation
4003 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4799 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4004 |  | WTIV | Delay | 41 | 854166.6667 | ACTION | 4805.4657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4005 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4808.9657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4006 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4810.9657 | TurbineInstallation
4007 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4813.9657 | TurbineInstallation
4008 |  | Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 4814 | MooredSubInstallation
4009 |  | Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 4814 | SemiSubStorageInstallation
4010 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4814.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4011 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4814.6257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4012 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4817.5 | MooredSubInstallation
4013 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4817.5 | SemiSubStorageInstallation
4014 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4819 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4015 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4820.6257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4016 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4821 | MooredSubInstallation
4017 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4821 | SemiSubStorageInstallation
4018 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4823.6257 | TurbineInstallation
4019 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4824.5 | MooredSubInstallation
4020 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4824.5 | SemiSubStorageInstallation
4021 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4824.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4022 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4829 | MooringSystemInstallation
4023 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4830.9457 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4024 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4833.9457 | TurbineInstallation
4025 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4834 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4026 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4834.9457 | TurbineInstallation
4027 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4836.2657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4028 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4842.2657 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4029 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4843.2657 | TurbineInstallation
4030 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4844 | MooringSystemInstallation
4031 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4844.2657 | TurbineInstallation
4032 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4845.5857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4033 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4846 | MooringSystemInstallation
4034 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4848.5 | MooredSubInstallation
4035 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 91.6667 | 114583.3333 | ACTION | 4848.5 | MooredSubInstallation
4036 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4848.5 | SemiSubStorageInstallation
4037 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 91.6667 | 114583.3333 | ACTION | 4848.5 | SemiSubStorageInstallation
4038 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4849.0857 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4039 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4850 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4040 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4850.0857 | TurbineInstallation
4041 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4851.4057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4042 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4854.5 | MooredSubInstallation | [7 empty] | 3
4043 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4854.5 | SemiSubStorageInstallation | [7 empty] | 3
4044 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4854.9057 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4045 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4855.9057 | TurbineInstallation
4046 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4857.2257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4047 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4860.7257 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4048 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4865.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4049 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4870 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4050 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 4871.1667 | MooredSubInstallation | [7 empty] | 3
4051 |  | Multi-Purpose Support Vessel | Delay | 131 | 545833.3333 | ACTION | 4871.1667 | MooredSubInstallation | Site
4052 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 4871.1667 | SemiSubStorageInstallation | [7 empty] | 3
4053 |  | Multi-Purpose Support Vessel | Delay | 131 | 545833.3333 | ACTION | 4871.1667 | SemiSubStorageInstallation | Site
4054 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4872 | MooredSubInstallation
4055 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 23.5 | 0 | ACTION | 4872 | MooredSubInstallation
4056 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4872 | MooringSystemInstallation
4057 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4872 | SemiSubStorageInstallation
4058 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 23.5 | 0 | ACTION | 4872 | SemiSubStorageInstallation
4059 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 4873.1667 | MooredSubInstallation
4060 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 4873.1667 | SemiSubStorageInstallation
4061 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4875.0114 | TurbineInstallation
4062 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4876 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4063 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4879.0114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4064 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4879.1667 | MooredSubInstallation
4065 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 4879.1667 | SemiSubStorageInstallation
4066 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4880 | MooredSubInstallation
4067 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4880 | SemiSubStorageInstallation
4068 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4883.0114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4069 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4887.0114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4070 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4888.5114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4071 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4890.0114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4072 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4891.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4073 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4891.5114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4074 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4892 | MooredSubInstallation
4075 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4892 | SemiSubStorageInstallation
4076 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4895.5114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4077 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4896 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4078 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4898 | MooringSystemInstallation
4079 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 4899.5114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4080 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4901.1667 | MooredSubInstallation
4081 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 4901.1667 | SemiSubStorageInstallation
4082 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4902 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4083 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 4903.5114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4084 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4904 | MooredSubInstallation
4085 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4904 | SemiSubStorageInstallation
4086 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4905.0114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4087 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4906.5114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4088 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 4908.0114 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4089 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4913.1667 | MooredSubInstallation
4090 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4913.1667 | MooredSubInstallation | site | [6 empty] | 2
4091 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 4913.1667 | SemiSubStorageInstallation
4092 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 4913.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4093 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4916 | MooredSubInstallation
4094 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 4916 | SemiSubStorageInstallation
4095 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4917.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4096 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4922 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4097 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 4922.2971 | TurbineInstallation
4098 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4923 | MooredSubInstallation
4099 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 4923 | SemiSubStorageInstallation
4100 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4924 | MooringSystemInstallation
4101 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4924.2971 | TurbineInstallation
4102 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4927.2971 | TurbineInstallation
4103 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4927.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4104 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4928 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4105 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4929.8333 | MooredSubInstallation | [7 empty] | 3
4106 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 4929.8333 | SemiSubStorageInstallation | [7 empty] | 3
4107 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4933.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4108 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4936.9571 | TurbineInstallation
4109 |  | WTIV | Delay | 1 | 20833.3333 | ACTION | 4937.9571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4110 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4939.2771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4111 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4943.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4112 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4945.2771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4113 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4948 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4114 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 4948.2771 | TurbineInstallation
4115 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4949.2771 | TurbineInstallation
4116 |  | Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 4950 | MooredSubInstallation
4117 |  | Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 4950 | SemiSubStorageInstallation
4118 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 4950.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4119 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4953.5 | MooredSubInstallation
4120 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4953.5 | SemiSubStorageInstallation
4121 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 4956.5971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4122 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4957 | MooredSubInstallation
4123 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4957 | SemiSubStorageInstallation
4124 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 4957.5971 | TurbineInstallation
4125 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4958 | MooringSystemInstallation
4126 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4958.5971 | TurbineInstallation
4127 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4959.9171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4128 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4960.5 | MooredSubInstallation
4129 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4960.5 | SemiSubStorageInstallation
4130 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4963 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4131 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4963.4171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4132 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4964.4171 | TurbineInstallation
4133 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4965.7371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4134 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4969.2371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4135 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 4970.2371 | TurbineInstallation
4136 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 4971.5571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4137 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4973 | MooringSystemInstallation
4138 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4975 | MooringSystemInstallation
4139 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 4975.0571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4140 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 4977.0571 | TurbineInstallation
4141 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4979 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4142 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4980.0571 | TurbineInstallation
4143 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 4980.7171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4144 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4984.5 | MooredSubInstallation
4145 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 54.6667 | 68333.3333 | ACTION | 4984.5 | MooredSubInstallation
4146 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4984.5 | SemiSubStorageInstallation
4147 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 54.6667 | 68333.3333 | ACTION | 4984.5 | SemiSubStorageInstallation
4148 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4986.7171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4149 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 4989.7171 | TurbineInstallation
4150 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4990.5 | MooredSubInstallation | [7 empty] | 3
4151 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 4990.5 | SemiSubStorageInstallation | [7 empty] | 3
4152 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 4991.0371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4153 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 4994.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4154 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 4997.0371 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4155 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 4999 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4156 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 5000.0371 | TurbineInstallation
4157 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5001 | MooringSystemInstallation
4158 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5001.0371 | TurbineInstallation
4159 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 5002.3571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4160 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5005 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4161 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5007.1667 | MooredSubInstallation | [7 empty] | 3
4162 |  | Multi-Purpose Support Vessel | Delay | 94 | 391666.6667 | ACTION | 5007.1667 | MooredSubInstallation | Site
4163 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5007.1667 | SemiSubStorageInstallation | [7 empty] | 3
4164 |  | Multi-Purpose Support Vessel | Delay | 94 | 391666.6667 | ACTION | 5007.1667 | SemiSubStorageInstallation | Site
4165 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 5008.3571 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4166 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5009.1667 | MooredSubInstallation
4167 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 5009.1667 | SemiSubStorageInstallation
4168 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5009.3571 | TurbineInstallation
4169 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5010.3571 | TurbineInstallation
4170 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5011.6771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4171 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5015.1667 | MooredSubInstallation
4172 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5015.1667 | SemiSubStorageInstallation
4173 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5015.1771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4174 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5016.1771 | TurbineInstallation
4175 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5020.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4176 |  | Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 5024.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4177 |  | Multi-Purpose Support Vessel | Delay | 12 | 50000 | ACTION | 5027.1667 | MooredSubInstallation
4178 |  | Multi-Purpose Support Vessel | Delay | 12 | 50000 | ACTION | 5027.1667 | SemiSubStorageInstallation
4179 |  | WTIV | Delay | 11 | 229166.6667 | ACTION | 5027.1771 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4180 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5028.4971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4181 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5029 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4182 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5031 | MooringSystemInstallation
4183 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5031.9971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4184 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 5 | 20833.3333 | ACTION | 5032.1667 | MooredSubInstallation
4185 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 5 | 20833.3333 | ACTION | 5032.1667 | SemiSubStorageInstallation
4186 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5032.9971 | TurbineInstallation
4187 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5035 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4188 |  | Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 5039 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4189 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5040 | MooredSubInstallation
4190 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 55.5 | 0 | ACTION | 5040 | MooredSubInstallation
4191 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5040 | SemiSubStorageInstallation
4192 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 55.5 | 0 | ACTION | 5040 | SemiSubStorageInstallation
4193 |  | Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 5041.1667 | MooredSubInstallation
4194 |  | Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 5041.1667 | SemiSubStorageInstallation
4195 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 5042.1667 | MooredSubInstallation
4196 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 5042.1667 | SemiSubStorageInstallation
4197 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 5043.1667 | MooredSubInstallation
4198 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 5043.1667 | SemiSubStorageInstallation
4199 |  | WTIV | Delay | 11 | 229166.6667 | ACTION | 5043.9971 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4200 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5045.3171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4201 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5048 | MooredSubInstallation
4202 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5048 | SemiSubStorageInstallation
4203 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5048.8171 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4204 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5054.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4205 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5059 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4206 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 5059.1667 | MooredSubInstallation
4207 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 5059.1667 | SemiSubStorageInstallation
4208 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5060 | MooredSubInstallation
4209 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5060 | SemiSubStorageInstallation
4210 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5061 | MooringSystemInstallation
4211 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 5063.1029 | TurbineInstallation
4212 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5065 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4213 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5067.1029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4214 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5071.1029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4215 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5071.1667 | MooredSubInstallation
4216 |  | Towing Group 1 | Positioning Support | 64 | 160000 | ACTION | 5071.1667 | MooredSubInstallation | site | [6 empty] | 2
4217 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5071.1667 | SemiSubStorageInstallation
4218 |  | Towing Group 1 | Positioning Support | 64 | 160000 | ACTION | 5071.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4219 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5072 | MooredSubInstallation
4220 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5072 | SemiSubStorageInstallation
4221 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 5075.1029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4222 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5076.6029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4223 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5078.1029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4224 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5079.6029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4225 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5080.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4226 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5083.6029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4227 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5084 | MooredSubInstallation
4228 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5084 | SemiSubStorageInstallation
4229 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5085 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4230 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5087.6029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4231 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5087.8333 | MooredSubInstallation | [7 empty] | 3
4232 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5087.8333 | SemiSubStorageInstallation | [7 empty] | 3
4233 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5091 | MooredSubInstallation
4234 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5091 | SemiSubStorageInstallation
4235 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 5091.6029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4236 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5093.1029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4237 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5094.5 | MooredSubInstallation
4238 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5094.5 | SemiSubStorageInstallation
4239 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5094.6029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4240 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5095 | MooringSystemInstallation
4241 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5096.1029 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4242 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5098 | MooredSubInstallation
4243 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5098 | SemiSubStorageInstallation
4244 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5100 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4245 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5101.5 | MooredSubInstallation
4246 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5101.5 | SemiSubStorageInstallation
4247 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5110 | MooringSystemInstallation
4248 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 5110.3886 | TurbineInstallation
4249 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5112 | MooringSystemInstallation
4250 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 5112.3886 | TurbineInstallation
4251 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5115.3886 | TurbineInstallation
4252 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5116 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4253 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 5116.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4254 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5122.0486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4255 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5125.0486 | TurbineInstallation
4256 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5125.5 | MooredSubInstallation
4257 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 37.6667 | 47083.3333 | ACTION | 5125.5 | MooredSubInstallation
4258 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5125.5 | SemiSubStorageInstallation
4259 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 37.6667 | 47083.3333 | ACTION | 5125.5 | SemiSubStorageInstallation
4260 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 5126.3686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4261 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5131.5 | MooredSubInstallation | [7 empty] | 3
4262 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5131.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4263 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5131.5 | SemiSubStorageInstallation | [7 empty] | 3
4264 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5132.3686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4265 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 5135.3686 | TurbineInstallation
4266 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5136 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4267 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5136.3686 | TurbineInstallation
4268 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 5137.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4269 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5138 | MooringSystemInstallation
4270 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5142 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4271 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 5143.6886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4272 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5144.6886 | TurbineInstallation
4273 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5145.6886 | TurbineInstallation
4274 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5147.0086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4275 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5148.1667 | MooredSubInstallation | [7 empty] | 3
4276 |  | Multi-Purpose Support Vessel | Delay | 77 | 320833.3333 | ACTION | 5148.1667 | MooredSubInstallation | Site
4277 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5148.1667 | SemiSubStorageInstallation | [7 empty] | 3
4278 |  | Multi-Purpose Support Vessel | Delay | 77 | 320833.3333 | ACTION | 5148.1667 | SemiSubStorageInstallation | Site
4279 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5150.1667 | MooredSubInstallation
4280 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 5150.1667 | SemiSubStorageInstallation
4281 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5150.5086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4282 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5151.5086 | TurbineInstallation
4283 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5152.8286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4284 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5156.1667 | MooredSubInstallation
4285 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5156.1667 | SemiSubStorageInstallation
4286 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5156.3286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4287 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5157.3286 | TurbineInstallation
4288 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5157.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4289 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5158.6486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4290 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5162 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4291 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5162.1486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4292 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5164 | MooringSystemInstallation
4293 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 5164.1486 | TurbineInstallation
4294 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5167.1486 | TurbineInstallation
4295 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 5167.8086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4296 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5168 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4297 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5173.8086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4298 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5176.8086 | TurbineInstallation
4299 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 5178.1286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4300 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5178.1667 | MooredSubInstallation
4301 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5178.1667 | SemiSubStorageInstallation
4302 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5183.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4303 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5184.1286 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4304 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 5187.1286 | TurbineInstallation
4305 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5188 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4306 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5188.1286 | TurbineInstallation
4307 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 5189.4486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4308 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5190 | MooringSystemInstallation
4309 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5190.1667 | MooredSubInstallation
4310 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5190.1667 | MooredSubInstallation | site | [6 empty] | 2
4311 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5190.1667 | SemiSubStorageInstallation
4312 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5190.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4313 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5194 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4314 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 5195.4486 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4315 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5196.4486 | TurbineInstallation
4316 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5197.4486 | TurbineInstallation
4317 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5198.7686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4318 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5202.2686 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4319 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5203.2686 | TurbineInstallation
4320 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5204.5886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4321 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5206.8333 | MooredSubInstallation | [7 empty] | 3
4322 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5206.8333 | SemiSubStorageInstallation | [7 empty] | 3
4323 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5208 | MooredSubInstallation
4324 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5208 | MooredSubInstallation
4325 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5208 | SemiSubStorageInstallation
4326 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5208 | SemiSubStorageInstallation
4327 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5208.0886 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4328 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5209.0886 | TurbineInstallation
4329 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5209.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4330 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5210.4086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4331 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5213.9086 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4332 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5214 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4333 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5216 | MooredSubInstallation
4334 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5216 | SemiSubStorageInstallation
4335 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5224 | MooringSystemInstallation
4336 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5228 | MooredSubInstallation
4337 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5228 | SemiSubStorageInstallation
4338 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 5228.1943 | TurbineInstallation
4339 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5229 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4340 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5232.1943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4341 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5236.1943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4342 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5239 | MooringSystemInstallation
4343 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5240 | MooredSubInstallation
4344 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5240 | SemiSubStorageInstallation
4345 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 5240.1943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4346 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5241 | MooringSystemInstallation
4347 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5241.6943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4348 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5243.1943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4349 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5244.6943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4350 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5245 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4351 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5248.6943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4352 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5252 | MooredSubInstallation
4353 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5252 | SemiSubStorageInstallation
4354 |  | WTIV | Fasten Tower Section | 4 | 83333.3333 | ACTION | 5252.6943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4355 |  | WTIV | Fasten Nacelle | 4 | 83333.3333 | ACTION | 5256.6943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4356 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5258.1943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4357 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5259 | MooredSubInstallation
4358 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5259 | SemiSubStorageInstallation
4359 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5259.6943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4360 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5260.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4361 |  | WTIV | Fasten Blade | 1.5 | 31250 | ACTION | 5261.1943 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4362 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5262.5 | MooredSubInstallation
4363 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5262.5 | SemiSubStorageInstallation
4364 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5265 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4365 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5266 | MooredSubInstallation
4366 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5266 | SemiSubStorageInstallation
4367 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5267 | MooringSystemInstallation
4368 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5269.5 | MooredSubInstallation
4369 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5269.5 | SemiSubStorageInstallation
4370 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5271 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4371 |  | WTIV | Transit | 14.2857 | 297619.0476 | ACTION | 5275.48 | TurbineInstallation
4372 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 5277.48 | TurbineInstallation
4373 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5280.48 | TurbineInstallation
4374 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 5281.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4375 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5286.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4376 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5287.14 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4377 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5290.14 | TurbineInstallation
4378 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5291 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4379 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 5291.46 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4380 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5293 | MooringSystemInstallation
4381 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5293.5 | MooredSubInstallation
4382 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 86.6667 | 108333.3333 | ACTION | 5293.5 | MooredSubInstallation
4383 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5293.5 | SemiSubStorageInstallation
4384 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 86.6667 | 108333.3333 | ACTION | 5293.5 | SemiSubStorageInstallation
4385 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5297 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4386 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5297.46 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4387 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5299.5 | MooredSubInstallation | [7 empty] | 3
4388 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5299.5 | SemiSubStorageInstallation | [7 empty] | 3
4389 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 5300.46 | TurbineInstallation
4390 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5301.46 | TurbineInstallation
4391 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 5302.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4392 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 5308.78 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4393 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5309.78 | TurbineInstallation
4394 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5310.78 | TurbineInstallation
4395 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5312.1 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4396 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5312.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4397 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5315.6 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4398 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5316.1667 | MooredSubInstallation | [7 empty] | 3
4399 |  | Multi-Purpose Support Vessel | Delay | 126 | 525000 | ACTION | 5316.1667 | MooredSubInstallation | Site
4400 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5316.1667 | SemiSubStorageInstallation | [7 empty] | 3
4401 |  | Multi-Purpose Support Vessel | Delay | 126 | 525000 | ACTION | 5316.1667 | SemiSubStorageInstallation | Site
4402 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5316.6 | TurbineInstallation
4403 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5317 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4404 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5317.92 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4405 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5318.1667 | MooredSubInstallation
4406 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 5318.1667 | SemiSubStorageInstallation
4407 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5319 | MooringSystemInstallation
4408 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5321.42 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4409 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5322.42 | TurbineInstallation
4410 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5323 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4411 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5323.74 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4412 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5324.1667 | MooredSubInstallation
4413 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5324.1667 | SemiSubStorageInstallation
4414 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5327.24 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4415 |  | WTIV | Position Onsite | 2 | 41666.6667 | ACTION | 5329.24 | TurbineInstallation
4416 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5332.24 | TurbineInstallation
4417 |  | WTIV | Lift Tower Section | 0.66 | 13750 | ACTION | 5332.9 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4418 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5338.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4419 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5338.9 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4420 |  | WTIV | Release Tower Section | 3 | 62500 | ACTION | 5341.9 | TurbineInstallation
4421 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5343 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4422 |  | WTIV | Lift Tower Section | 1.32 | 27500 | ACTION | 5343.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4423 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 21 | 87500 | ACTION | 5345.1667 | MooredSubInstallation
4424 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 21 | 87500 | ACTION | 5345.1667 | SemiSubStorageInstallation
4425 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 5351.1667 | MooredSubInstallation
4426 |  | Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 5351.1667 | SemiSubStorageInstallation
4427 |  | WTIV | Delay | 8 | 166666.6667 | ACTION | 5351.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4428 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 5352.1667 | MooredSubInstallation
4429 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 5352.1667 | SemiSubStorageInstallation
4430 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5353 | MooringSystemInstallation
4431 |  | WTIV | Attach Tower Section | 6 | 125000 | ACTION | 5357.22 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4432 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5358 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4433 |  | WTIV | Release Nacelle | 3 | 62500 | ACTION | 5360.22 | TurbineInstallation
4434 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5361.22 | TurbineInstallation
4435 |  | WTIV | Lift Nacelle | 1.32 | 27500 | ACTION | 5362.54 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4436 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5364.1667 | MooredSubInstallation
4437 |  | Towing Group 1 | Positioning Support | 48 | 120000 | ACTION | 5364.1667 | MooredSubInstallation | site | [6 empty] | 2
4438 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5364.1667 | SemiSubStorageInstallation
4439 |  | Towing Group 1 | Positioning Support | 48 | 120000 | ACTION | 5364.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4440 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5368 | MooringSystemInstallation
4441 |  | WTIV | Attach Nacelle | 6 | 125000 | ACTION | 5368.54 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4442 |  | WTIV | Reequip | 1 | 20833.3333 | ACTION | 5369.54 | TurbineInstallation
4443 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5370 | MooringSystemInstallation
4444 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5370.54 | TurbineInstallation
4445 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5371.86 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4446 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5374 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4447 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5375.36 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4448 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5376 | MooredSubInstallation
4449 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5376 | MooredSubInstallation
4450 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5376 | SemiSubStorageInstallation
4451 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5376 | SemiSubStorageInstallation
4452 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5376.36 | TurbineInstallation
4453 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5377.68 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4454 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5380.8333 | MooredSubInstallation | [7 empty] | 3
4455 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5380.8333 | SemiSubStorageInstallation | [7 empty] | 3
4456 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5381.18 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4457 |  | WTIV | Release Blade | 1 | 20833.3333 | ACTION | 5382.18 | TurbineInstallation
4458 |  | WTIV | Lift Blade | 1.32 | 27500 | ACTION | 5383.5 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4459 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5384 | MooredSubInstallation
4460 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5384 | SemiSubStorageInstallation
4461 |  | WTIV | Attach Blade | 3.5 | 72916.6667 | ACTION | 5387 | TurbineInstallation |  | 900 | 132 | TurbineInstallation
4462 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5389.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4463 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5394 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4464 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5396 | MooredSubInstallation
4465 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5396 | MooringSystemInstallation
4466 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5396 | SemiSubStorageInstallation
4467 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5400 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4468 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5408 | MooredSubInstallation
4469 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5408 | SemiSubStorageInstallation
4470 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5415.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4471 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5420 | MooredSubInstallation
4472 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5420 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4473 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5420 | SemiSubStorageInstallation
4474 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5422 | MooringSystemInstallation
4475 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5426 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4476 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5427 | MooredSubInstallation
4477 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5427 | SemiSubStorageInstallation
4478 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5430.5 | MooredSubInstallation
4479 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5430.5 | SemiSubStorageInstallation
4480 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5434 | MooredSubInstallation
4481 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5434 | SemiSubStorageInstallation
4482 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5441.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4483 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5446 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4484 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5448 | MooringSystemInstallation
4485 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5452 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4486 |  | Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 5456 | MooredSubInstallation
4487 |  | Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 5456 | SemiSubStorageInstallation
4488 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5459.5 | MooredSubInstallation
4489 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5459.5 | SemiSubStorageInstallation
4490 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5467.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4491 |  | Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 5470.5 | MooredSubInstallation
4492 |  | Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 5470.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4493 |  | Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 5470.5 | SemiSubStorageInstallation
4494 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5475 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4495 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5485 | MooringSystemInstallation
4496 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5490 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4497 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5494.5 | MooredSubInstallation
4498 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 113.6667 | 142083.3333 | ACTION | 5494.5 | MooredSubInstallation
4499 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5494.5 | SemiSubStorageInstallation
4500 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 113.6667 | 142083.3333 | ACTION | 5494.5 | SemiSubStorageInstallation
4501 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5500 | MooringSystemInstallation
4502 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5500.5 | MooredSubInstallation | [7 empty] | 3
4503 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5500.5 | SemiSubStorageInstallation | [7 empty] | 3
4504 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5502 | MooringSystemInstallation
4505 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5506 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4506 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5517.1667 | MooredSubInstallation | [7 empty] | 3
4507 |  | Multi-Purpose Support Vessel | Delay | 153 | 637500 | ACTION | 5517.1667 | MooredSubInstallation | Site
4508 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5517.1667 | SemiSubStorageInstallation | [7 empty] | 3
4509 |  | Multi-Purpose Support Vessel | Delay | 153 | 637500 | ACTION | 5517.1667 | SemiSubStorageInstallation | Site
4510 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5519.1667 | MooredSubInstallation
4511 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 5519.1667 | SemiSubStorageInstallation
4512 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5521.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4513 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5525.1667 | MooredSubInstallation
4514 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5525.1667 | SemiSubStorageInstallation
4515 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5526 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4516 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5528 | MooringSystemInstallation
4517 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5532 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4518 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5544 | MooredSubInstallation
4519 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 49.5 | 0 | ACTION | 5544 | MooredSubInstallation
4520 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5544 | SemiSubStorageInstallation
4521 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 49.5 | 0 | ACTION | 5544 | SemiSubStorageInstallation
4522 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5547.1667 | MooredSubInstallation
4523 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5547.1667 | SemiSubStorageInstallation
4524 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5547.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4525 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5552 | MooredSubInstallation
4526 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5552 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4527 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5552 | SemiSubStorageInstallation
4528 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5554 | MooringSystemInstallation
4529 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5558 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4530 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5559.1667 | MooredSubInstallation
4531 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5559.1667 | MooredSubInstallation | site | [6 empty] | 2
4532 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5559.1667 | SemiSubStorageInstallation
4533 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5559.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4534 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5564 | MooredSubInstallation
4535 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5564 | SemiSubStorageInstallation
4536 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5573.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4537 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5575.8333 | MooredSubInstallation | [7 empty] | 3
4538 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5575.8333 | SemiSubStorageInstallation | [7 empty] | 3
4539 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5576 | MooredSubInstallation
4540 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5576 | SemiSubStorageInstallation
4541 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5578 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4542 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5580 | MooringSystemInstallation
4543 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5584 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4544 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5588 | MooredSubInstallation
4545 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5588 | SemiSubStorageInstallation
4546 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5595 | MooredSubInstallation
4547 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5595 | SemiSubStorageInstallation
4548 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5598.5 | MooredSubInstallation
4549 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5598.5 | SemiSubStorageInstallation
4550 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5599.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4551 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5602 | MooredSubInstallation
4552 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5602 | SemiSubStorageInstallation
4553 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5604 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4554 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5605.5 | MooredSubInstallation
4555 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5605.5 | SemiSubStorageInstallation
4556 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5614 | MooringSystemInstallation
4557 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5619 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4558 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5629 | MooringSystemInstallation
4559 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5629.5 | MooredSubInstallation
4560 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 53.6667 | 67083.3333 | ACTION | 5629.5 | MooredSubInstallation
4561 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5629.5 | SemiSubStorageInstallation
4562 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 53.6667 | 67083.3333 | ACTION | 5629.5 | SemiSubStorageInstallation
4563 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5631 | MooringSystemInstallation
4564 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5635 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4565 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5635.5 | MooredSubInstallation | [7 empty] | 3
4566 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5635.5 | SemiSubStorageInstallation | [7 empty] | 3
4567 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5650.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4568 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5652.1667 | MooredSubInstallation | [7 empty] | 3
4569 |  | Multi-Purpose Support Vessel | Delay | 93 | 387500 | ACTION | 5652.1667 | MooredSubInstallation | Site
4570 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5652.1667 | SemiSubStorageInstallation | [7 empty] | 3
4571 |  | Multi-Purpose Support Vessel | Delay | 93 | 387500 | ACTION | 5652.1667 | SemiSubStorageInstallation | Site
4572 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5654.1667 | MooredSubInstallation
4573 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 5654.1667 | SemiSubStorageInstallation
4574 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5655 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4575 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5657 | MooringSystemInstallation
4576 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5660.1667 | MooredSubInstallation
4577 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5660.1667 | SemiSubStorageInstallation
4578 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5661 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4579 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5676.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4580 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5681 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4581 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5682.1667 | MooredSubInstallation
4582 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5682.1667 | SemiSubStorageInstallation
4583 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5683 | MooringSystemInstallation
4584 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5687 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4585 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5694.1667 | MooredSubInstallation
4586 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5694.1667 | MooredSubInstallation | site | [6 empty] | 2
4587 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5694.1667 | SemiSubStorageInstallation
4588 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5694.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4589 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5702.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4590 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5707 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4591 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5709 | MooringSystemInstallation
4592 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5710.8333 | MooredSubInstallation | [7 empty] | 3
4593 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5710.8333 | SemiSubStorageInstallation | [7 empty] | 3
4594 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5712 | MooredSubInstallation
4595 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5712 | MooredSubInstallation
4596 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5712 | SemiSubStorageInstallation
4597 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5712 | SemiSubStorageInstallation
4598 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5713 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4599 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5720 | MooredSubInstallation
4600 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5720 | SemiSubStorageInstallation
4601 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5728.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4602 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5732 | MooredSubInstallation
4603 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5732 | SemiSubStorageInstallation
4604 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5733 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4605 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5743 | MooringSystemInstallation
4606 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5744 | MooredSubInstallation
4607 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5744 | SemiSubStorageInstallation
4608 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5748 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4609 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5756 | MooredSubInstallation
4610 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5756 | SemiSubStorageInstallation
4611 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5758 | MooringSystemInstallation
4612 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5760 | MooringSystemInstallation
4613 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5763 | MooredSubInstallation
4614 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5763 | SemiSubStorageInstallation
4615 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5764 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4616 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5766.5 | MooredSubInstallation
4617 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5766.5 | SemiSubStorageInstallation
4618 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5770 | MooredSubInstallation
4619 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5770 | SemiSubStorageInstallation
4620 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5773.5 | MooredSubInstallation
4621 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5773.5 | SemiSubStorageInstallation
4622 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5779.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4623 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5784 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4624 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5786 | MooringSystemInstallation
4625 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5790 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4626 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5797.5 | MooredSubInstallation
4627 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 86.6667 | 108333.3333 | ACTION | 5797.5 | MooredSubInstallation
4628 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5797.5 | SemiSubStorageInstallation
4629 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 86.6667 | 108333.3333 | ACTION | 5797.5 | SemiSubStorageInstallation
4630 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5803.5 | MooredSubInstallation | [7 empty] | 3
4631 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5803.5 | SemiSubStorageInstallation | [7 empty] | 3
4632 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5805.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4633 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5810 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4634 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5812 | MooringSystemInstallation
4635 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5816 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4636 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5820.1667 | MooredSubInstallation | [7 empty] | 3
4637 |  | Multi-Purpose Support Vessel | Delay | 126 | 525000 | ACTION | 5820.1667 | MooredSubInstallation | Site
4638 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5820.1667 | SemiSubStorageInstallation | [7 empty] | 3
4639 |  | Multi-Purpose Support Vessel | Delay | 126 | 525000 | ACTION | 5820.1667 | SemiSubStorageInstallation | Site
4640 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5822.1667 | MooredSubInstallation
4641 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 5822.1667 | SemiSubStorageInstallation
4642 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5828.1667 | MooredSubInstallation
4643 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5828.1667 | SemiSubStorageInstallation
4644 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5831.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4645 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5836 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4646 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5838 | MooringSystemInstallation
4647 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5842 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4648 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5850.1667 | MooredSubInstallation
4649 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 5850.1667 | SemiSubStorageInstallation
4650 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5857.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4651 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5862 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4652 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5862.1667 | MooredSubInstallation
4653 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5862.1667 | MooredSubInstallation | site | [6 empty] | 2
4654 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 5862.1667 | SemiSubStorageInstallation
4655 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 5862.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4656 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5872 | MooringSystemInstallation
4657 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5877 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4658 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5878.8333 | MooredSubInstallation | [7 empty] | 3
4659 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 5878.8333 | SemiSubStorageInstallation | [7 empty] | 3
4660 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5880 | MooredSubInstallation
4661 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5880 | MooredSubInstallation
4662 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5880 | SemiSubStorageInstallation
4663 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5880 | SemiSubStorageInstallation
4664 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5887 | MooringSystemInstallation
4665 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5888 | MooredSubInstallation
4666 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5888 | SemiSubStorageInstallation
4667 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5889 | MooringSystemInstallation
4668 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5893 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4669 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5900 | MooredSubInstallation
4670 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5900 | SemiSubStorageInstallation
4671 |  | Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 5903 | MooredSubInstallation
4672 |  | Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 5903 | SemiSubStorageInstallation
4673 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5908.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4674 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5913 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4675 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5915 | MooredSubInstallation
4676 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5915 | MooringSystemInstallation
4677 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5915 | SemiSubStorageInstallation
4678 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5919 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4679 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5927 | MooredSubInstallation
4680 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5927 | SemiSubStorageInstallation
4681 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5934 | MooredSubInstallation
4682 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5934 | SemiSubStorageInstallation
4683 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5934.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4684 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5937.5 | MooredSubInstallation
4685 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5937.5 | SemiSubStorageInstallation
4686 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5939 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4687 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5941 | MooredSubInstallation
4688 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5941 | MooringSystemInstallation
4689 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5941 | SemiSubStorageInstallation
4690 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5944.5 | MooredSubInstallation
4691 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5944.5 | SemiSubStorageInstallation
4692 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5945 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4693 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5960.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4694 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5965 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4695 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5967 | MooringSystemInstallation
4696 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5968.5 | MooredSubInstallation
4697 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 89.6667 | 112083.3333 | ACTION | 5968.5 | MooredSubInstallation
4698 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5968.5 | SemiSubStorageInstallation
4699 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 89.6667 | 112083.3333 | ACTION | 5968.5 | SemiSubStorageInstallation
4700 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5971 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4701 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5974.5 | MooredSubInstallation | [7 empty] | 3
4702 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 5974.5 | SemiSubStorageInstallation | [7 empty] | 3
4703 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 5986.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4704 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 5991 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4705 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 5991.1667 | MooredSubInstallation | [7 empty] | 3
4706 |  | Multi-Purpose Support Vessel | Delay | 129 | 537500 | ACTION | 5991.1667 | MooredSubInstallation | Site
4707 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 5991.1667 | SemiSubStorageInstallation | [7 empty] | 3
4708 |  | Multi-Purpose Support Vessel | Delay | 129 | 537500 | ACTION | 5991.1667 | SemiSubStorageInstallation | Site
4709 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6001 | MooringSystemInstallation
4710 |  | Multi-Purpose Support Vessel | Delay | 10 | 41666.6667 | ACTION | 6001.1667 | MooredSubInstallation
4711 |  | Multi-Purpose Support Vessel | Delay | 10 | 41666.6667 | ACTION | 6001.1667 | SemiSubStorageInstallation
4712 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6003.1667 | MooredSubInstallation
4713 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 6003.1667 | SemiSubStorageInstallation
4714 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6006 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4715 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6009.1667 | MooredSubInstallation
4716 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6009.1667 | SemiSubStorageInstallation
4717 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6016 | MooringSystemInstallation
4718 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6018 | MooringSystemInstallation
4719 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6022 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4720 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6031.1667 | MooredSubInstallation
4721 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6031.1667 | SemiSubStorageInstallation
4722 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6037.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4723 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6042 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4724 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6043.1667 | MooredSubInstallation
4725 |  | Towing Group 1 | Positioning Support | 52 | 130000 | ACTION | 6043.1667 | MooredSubInstallation | site | [6 empty] | 2
4726 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6043.1667 | SemiSubStorageInstallation
4727 |  | Towing Group 1 | Positioning Support | 52 | 130000 | ACTION | 6043.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4728 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6044 | MooringSystemInstallation
4729 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6048 | MooredSubInstallation
4730 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 79.5 | 0 | ACTION | 6048 | MooredSubInstallation
4731 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6048 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4732 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6048 | SemiSubStorageInstallation
4733 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 79.5 | 0 | ACTION | 6048 | SemiSubStorageInstallation
4734 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6056 | MooredSubInstallation
4735 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6056 | SemiSubStorageInstallation
4736 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6059.8333 | MooredSubInstallation | [7 empty] | 3
4737 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6059.8333 | SemiSubStorageInstallation | [7 empty] | 3
4738 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6063.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4739 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6068 | MooredSubInstallation
4740 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6068 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4741 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6068 | SemiSubStorageInstallation
4742 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6070 | MooringSystemInstallation
4743 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6074 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4744 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6080 | MooredSubInstallation
4745 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6080 | SemiSubStorageInstallation
4746 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6089.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4747 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6092 | MooredSubInstallation
4748 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6092 | SemiSubStorageInstallation
4749 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6094 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4750 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6096 | MooringSystemInstallation
4751 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6099 | MooredSubInstallation
4752 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6099 | SemiSubStorageInstallation
4753 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6100 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4754 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6102.5 | MooredSubInstallation
4755 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6102.5 | SemiSubStorageInstallation
4756 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6106 | MooredSubInstallation
4757 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6106 | SemiSubStorageInstallation
4758 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6109.5 | MooredSubInstallation
4759 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6109.5 | SemiSubStorageInstallation
4760 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6115.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4761 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6120 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4762 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6130 | MooringSystemInstallation
4763 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6133.5 | MooredSubInstallation
4764 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 73.6667 | 92083.3333 | ACTION | 6133.5 | MooredSubInstallation
4765 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6133.5 | SemiSubStorageInstallation
4766 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 73.6667 | 92083.3333 | ACTION | 6133.5 | SemiSubStorageInstallation
4767 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6135 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4768 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6139.5 | MooredSubInstallation | [7 empty] | 3
4769 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6139.5 | SemiSubStorageInstallation | [7 empty] | 3
4770 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6145 | MooringSystemInstallation
4771 |  | Towing Group 1 | Delay | 6 | 22500 | ACTION | 6145.5 | MooredSubInstallation | [7 empty] | 3
4772 |  | Towing Group 1 | Delay | 6 | 22500 | ACTION | 6145.5 | SemiSubStorageInstallation | [7 empty] | 3
4773 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6147 | MooringSystemInstallation
4774 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6151 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4775 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 6162.1667 | MooredSubInstallation | [7 empty] | 3
4776 |  | Multi-Purpose Support Vessel | Delay | 119 | 495833.3333 | ACTION | 6162.1667 | MooredSubInstallation | Site
4777 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 6162.1667 | SemiSubStorageInstallation | [7 empty] | 3
4778 |  | Multi-Purpose Support Vessel | Delay | 119 | 495833.3333 | ACTION | 6162.1667 | SemiSubStorageInstallation | Site
4779 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6164.1667 | MooredSubInstallation
4780 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 6164.1667 | SemiSubStorageInstallation
4781 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6166.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4782 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6170.1667 | MooredSubInstallation
4783 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6170.1667 | SemiSubStorageInstallation
4784 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6171 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4785 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6173 | MooringSystemInstallation
4786 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6177 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4787 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6192.1667 | MooredSubInstallation
4788 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6192.1667 | SemiSubStorageInstallation
4789 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6192.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4790 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6197 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4791 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6199 | MooringSystemInstallation
4792 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6203 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4793 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6204.1667 | MooredSubInstallation
4794 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6204.1667 | MooredSubInstallation | site | [6 empty] | 2
4795 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6204.1667 | SemiSubStorageInstallation
4796 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6204.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4797 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6216 | MooredSubInstallation
4798 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6216 | MooredSubInstallation
4799 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6216 | SemiSubStorageInstallation
4800 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6216 | SemiSubStorageInstallation
4801 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6218.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4802 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6220.8333 | MooredSubInstallation | [7 empty] | 3
4803 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6220.8333 | SemiSubStorageInstallation | [7 empty] | 3
4804 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6223 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4805 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6224 | MooredSubInstallation
4806 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6224 | SemiSubStorageInstallation
4807 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6225 | MooringSystemInstallation
4808 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6229 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4809 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6236 | MooredSubInstallation
4810 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6236 | SemiSubStorageInstallation
4811 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6244.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4812 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6248 | MooredSubInstallation
4813 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6248 | SemiSubStorageInstallation
4814 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6249 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4815 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6259 | MooringSystemInstallation
4816 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6260 | MooredSubInstallation
4817 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6260 | SemiSubStorageInstallation
4818 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6264 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4819 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6267 | MooredSubInstallation
4820 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6267 | SemiSubStorageInstallation
4821 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6270.5 | MooredSubInstallation
4822 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6270.5 | SemiSubStorageInstallation
4823 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6274 | MooredSubInstallation
4824 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6274 | MooringSystemInstallation
4825 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6274 | SemiSubStorageInstallation
4826 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6276 | MooringSystemInstallation
4827 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6277.5 | MooredSubInstallation
4828 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6277.5 | SemiSubStorageInstallation
4829 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6280 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4830 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6295.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4831 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6300 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4832 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6301.5 | MooredSubInstallation
4833 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 80.6667 | 100833.3333 | ACTION | 6301.5 | MooredSubInstallation
4834 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6301.5 | SemiSubStorageInstallation
4835 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 80.6667 | 100833.3333 | ACTION | 6301.5 | SemiSubStorageInstallation
4836 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6302 | MooringSystemInstallation
4837 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6306 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4838 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6307.5 | MooredSubInstallation | [7 empty] | 3
4839 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6307.5 | SemiSubStorageInstallation | [7 empty] | 3
4840 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6321.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4841 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 6324.1667 | MooredSubInstallation | [7 empty] | 3
4842 |  | Multi-Purpose Support Vessel | Delay | 120 | 500000 | ACTION | 6324.1667 | MooredSubInstallation | Site
4843 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 6324.1667 | SemiSubStorageInstallation | [7 empty] | 3
4844 |  | Multi-Purpose Support Vessel | Delay | 120 | 500000 | ACTION | 6324.1667 | SemiSubStorageInstallation | Site
4845 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6326 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4846 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6326.1667 | MooredSubInstallation
4847 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 6326.1667 | SemiSubStorageInstallation
4848 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6328 | MooringSystemInstallation
4849 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6332 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4850 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6332.1667 | MooredSubInstallation
4851 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6332.1667 | SemiSubStorageInstallation
4852 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6347.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4853 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6352 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4854 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6354 | MooringSystemInstallation
4855 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6354.1667 | MooredSubInstallation
4856 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6354.1667 | SemiSubStorageInstallation
4857 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6358 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4858 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6366.1667 | MooredSubInstallation
4859 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6366.1667 | MooredSubInstallation | site | [6 empty] | 2
4860 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6366.1667 | SemiSubStorageInstallation
4861 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6366.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4862 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6373.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4863 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6378 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4864 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6382.8333 | MooredSubInstallation | [7 empty] | 3
4865 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6382.8333 | SemiSubStorageInstallation | [7 empty] | 3
4866 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6384 | MooredSubInstallation
4867 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6384 | MooredSubInstallation
4868 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6384 | SemiSubStorageInstallation
4869 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6384 | SemiSubStorageInstallation
4870 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6388 | MooringSystemInstallation
4871 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6392 | MooredSubInstallation
4872 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6392 | SemiSubStorageInstallation
4873 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6393 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4874 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6403 | MooringSystemInstallation
4875 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6404 | MooredSubInstallation
4876 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6404 | SemiSubStorageInstallation
4877 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6405 | MooringSystemInstallation
4878 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6409 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4879 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6416 | MooredSubInstallation
4880 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6416 | SemiSubStorageInstallation
4881 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6424.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4882 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6428 | MooredSubInstallation
4883 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6428 | SemiSubStorageInstallation
4884 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6429 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4885 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6431 | MooringSystemInstallation
4886 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6435 | MooredSubInstallation
4887 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6435 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4888 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6435 | SemiSubStorageInstallation
4889 |  | Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 6437 | MooredSubInstallation
4890 |  | Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 6437 | SemiSubStorageInstallation
4891 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6440.5 | MooredSubInstallation
4892 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6440.5 | SemiSubStorageInstallation
4893 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6444 | MooredSubInstallation
4894 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6444 | SemiSubStorageInstallation
4895 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6447.5 | MooredSubInstallation
4896 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6447.5 | SemiSubStorageInstallation
4897 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6450.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4898 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6455 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4899 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6457 | MooringSystemInstallation
4900 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6461 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4901 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6471.5 | MooredSubInstallation
4902 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 6471.5 | MooredSubInstallation
4903 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6471.5 | SemiSubStorageInstallation
4904 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 6471.5 | SemiSubStorageInstallation
4905 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6476.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4906 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6477.5 | MooredSubInstallation | [7 empty] | 3
4907 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6477.5 | SemiSubStorageInstallation | [7 empty] | 3
4908 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6481 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4909 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6483 | MooringSystemInstallation
4910 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6487 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4911 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 6494.1667 | MooredSubInstallation | [7 empty] | 3
4912 |  | Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 6494.1667 | MooredSubInstallation | Site
4913 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 6494.1667 | SemiSubStorageInstallation | [7 empty] | 3
4914 |  | Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 6494.1667 | SemiSubStorageInstallation | Site
4915 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6496.1667 | MooredSubInstallation
4916 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 6496.1667 | SemiSubStorageInstallation
4917 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6502.1667 | MooredSubInstallation
4918 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6502.1667 | SemiSubStorageInstallation
4919 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6502.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4920 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6507 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4921 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6517 | MooringSystemInstallation
4922 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6522 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4923 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6524.1667 | MooredSubInstallation
4924 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6524.1667 | SemiSubStorageInstallation
4925 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6532 | MooringSystemInstallation
4926 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6534 | MooringSystemInstallation
4927 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6536.1667 | MooredSubInstallation
4928 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6536.1667 | MooredSubInstallation | site | [6 empty] | 2
4929 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6536.1667 | SemiSubStorageInstallation
4930 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6536.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4931 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6538 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4932 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6552 | MooredSubInstallation
4933 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 6552 | MooredSubInstallation
4934 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6552 | SemiSubStorageInstallation
4935 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 6552 | SemiSubStorageInstallation
4936 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6552.8333 | MooredSubInstallation | [7 empty] | 3
4937 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6552.8333 | SemiSubStorageInstallation | [7 empty] | 3
4938 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6553.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4939 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6558 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4940 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6560 | MooredSubInstallation
4941 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6560 | MooringSystemInstallation
4942 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6560 | SemiSubStorageInstallation
4943 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6564 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4944 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6572 | MooredSubInstallation
4945 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6572 | SemiSubStorageInstallation
4946 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6579.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4947 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6584 | MooredSubInstallation
4948 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6584 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4949 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6584 | SemiSubStorageInstallation
4950 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6586 | MooringSystemInstallation
4951 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6590 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4952 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6596 | MooredSubInstallation
4953 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6596 | SemiSubStorageInstallation
4954 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6603 | MooredSubInstallation
4955 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6603 | SemiSubStorageInstallation
4956 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6605.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4957 |  | Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6607 | MooredSubInstallation
4958 |  | Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6607 | SemiSubStorageInstallation
4959 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6610 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4960 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6610.5 | MooredSubInstallation
4961 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6610.5 | SemiSubStorageInstallation
4962 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6612 | MooringSystemInstallation
4963 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6614 | MooredSubInstallation
4964 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6614 | SemiSubStorageInstallation
4965 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6616 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4966 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6617.5 | MooredSubInstallation
4967 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6617.5 | SemiSubStorageInstallation
4968 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6631.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4969 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6636 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4970 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6641.5 | MooredSubInstallation
4971 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 6641.5 | MooredSubInstallation
4972 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6641.5 | SemiSubStorageInstallation
4973 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 6641.5 | SemiSubStorageInstallation
4974 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6646 | MooringSystemInstallation
4975 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6647.5 | MooredSubInstallation | [7 empty] | 3
4976 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6647.5 | SemiSubStorageInstallation | [7 empty] | 3
4977 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6651 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4978 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6661 | MooringSystemInstallation
4979 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6663 | MooringSystemInstallation
4980 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 6664.1667 | MooredSubInstallation | [7 empty] | 3
4981 |  | Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 6664.1667 | MooredSubInstallation | Site
4982 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 6664.1667 | SemiSubStorageInstallation | [7 empty] | 3
4983 |  | Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 6664.1667 | SemiSubStorageInstallation | Site
4984 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6666.1667 | MooredSubInstallation
4985 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 6666.1667 | SemiSubStorageInstallation
4986 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6667 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4987 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6672.1667 | MooredSubInstallation
4988 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6672.1667 | SemiSubStorageInstallation
4989 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6682.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4990 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6687 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4991 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6689 | MooringSystemInstallation
4992 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6693 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
4993 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6694.1667 | MooredSubInstallation
4994 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6694.1667 | SemiSubStorageInstallation
4995 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6706.1667 | MooredSubInstallation
4996 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6706.1667 | MooredSubInstallation | site | [6 empty] | 2
4997 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6706.1667 | SemiSubStorageInstallation
4998 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6706.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
4999 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6708.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5000 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6713 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5001 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6715 | MooringSystemInstallation
5002 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6719 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5003 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6720 | MooredSubInstallation
5004 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 78.5 | 0 | ACTION | 6720 | MooredSubInstallation
5005 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6720 | SemiSubStorageInstallation
5006 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 78.5 | 0 | ACTION | 6720 | SemiSubStorageInstallation
5007 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6722.8333 | MooredSubInstallation | [7 empty] | 3
5008 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6722.8333 | SemiSubStorageInstallation | [7 empty] | 3
5009 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6728 | MooredSubInstallation
5010 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6728 | SemiSubStorageInstallation
5011 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6734.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5012 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6739 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5013 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6740 | MooredSubInstallation
5014 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6740 | SemiSubStorageInstallation
5015 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6741 | MooringSystemInstallation
5016 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6745 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5017 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6752 | MooredSubInstallation
5018 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6752 | SemiSubStorageInstallation
5019 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6760.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5020 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6764 | MooredSubInstallation
5021 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6764 | SemiSubStorageInstallation
5022 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6765 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5023 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6771 | MooredSubInstallation
5024 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6771 | SemiSubStorageInstallation
5025 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6774.5 | MooredSubInstallation
5026 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6774.5 | SemiSubStorageInstallation
5027 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6775 | MooringSystemInstallation
5028 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6778 | MooredSubInstallation
5029 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6778 | SemiSubStorageInstallation
5030 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6780 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5031 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6781.5 | MooredSubInstallation
5032 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6781.5 | SemiSubStorageInstallation
5033 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6790 | MooringSystemInstallation
5034 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6792 | MooringSystemInstallation
5035 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6796 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5036 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6805.5 | MooredSubInstallation
5037 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 82.6667 | 103333.3333 | ACTION | 6805.5 | MooredSubInstallation
5038 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6805.5 | SemiSubStorageInstallation
5039 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 82.6667 | 103333.3333 | ACTION | 6805.5 | SemiSubStorageInstallation
5040 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6811.5 | MooredSubInstallation | [7 empty] | 3
5041 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6811.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5042 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6811.5 | SemiSubStorageInstallation | [7 empty] | 3
5043 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6816 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5044 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6818 | MooringSystemInstallation
5045 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6822 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5046 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 6828.1667 | MooredSubInstallation | [7 empty] | 3
5047 |  | Multi-Purpose Support Vessel | Delay | 122 | 508333.3333 | ACTION | 6828.1667 | MooredSubInstallation | Site
5048 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 6828.1667 | SemiSubStorageInstallation | [7 empty] | 3
5049 |  | Multi-Purpose Support Vessel | Delay | 122 | 508333.3333 | ACTION | 6828.1667 | SemiSubStorageInstallation | Site
5050 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6830.1667 | MooredSubInstallation
5051 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 6830.1667 | SemiSubStorageInstallation
5052 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6836.1667 | MooredSubInstallation
5053 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6836.1667 | SemiSubStorageInstallation
5054 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6837.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5055 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6842 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5056 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6844 | MooringSystemInstallation
5057 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6848 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5058 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6858.1667 | MooredSubInstallation
5059 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 6858.1667 | SemiSubStorageInstallation
5060 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6863.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5061 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6868 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5062 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6870 | MooringSystemInstallation
5063 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6870.1667 | MooredSubInstallation
5064 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6870.1667 | MooredSubInstallation | site | [6 empty] | 2
5065 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 6870.1667 | SemiSubStorageInstallation
5066 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 6870.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5067 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6874 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5068 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6886.8333 | MooredSubInstallation | [7 empty] | 3
5069 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 6886.8333 | SemiSubStorageInstallation | [7 empty] | 3
5070 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6888 | MooredSubInstallation
5071 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6888 | MooredSubInstallation
5072 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6888 | SemiSubStorageInstallation
5073 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6888 | SemiSubStorageInstallation
5074 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6889.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5075 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6894 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5076 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6896 | MooredSubInstallation
5077 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6896 | SemiSubStorageInstallation
5078 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6904 | MooringSystemInstallation
5079 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6908 | MooredSubInstallation
5080 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6908 | SemiSubStorageInstallation
5081 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6909 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5082 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6919 | MooringSystemInstallation
5083 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6920 | MooredSubInstallation
5084 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6920 | SemiSubStorageInstallation
5085 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6921 | MooringSystemInstallation
5086 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6925 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5087 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6932 | MooredSubInstallation
5088 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6932 | SemiSubStorageInstallation
5089 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6939 | MooredSubInstallation
5090 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6939 | SemiSubStorageInstallation
5091 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6940.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5092 |  | Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 6941 | MooredSubInstallation
5093 |  | Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 6941 | SemiSubStorageInstallation
5094 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6944.5 | MooredSubInstallation
5095 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6944.5 | SemiSubStorageInstallation
5096 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6945 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5097 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6947 | MooringSystemInstallation
5098 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6948 | MooredSubInstallation
5099 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6948 | SemiSubStorageInstallation
5100 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6951 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5101 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6951.5 | MooredSubInstallation
5102 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6951.5 | SemiSubStorageInstallation
5103 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6966.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5104 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6971 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5105 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6973 | MooringSystemInstallation
5106 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6975.5 | MooredSubInstallation
5107 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 6975.5 | MooredSubInstallation
5108 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6975.5 | SemiSubStorageInstallation
5109 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 88.6667 | 110833.3333 | ACTION | 6975.5 | SemiSubStorageInstallation
5110 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6977 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5111 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6981.5 | MooredSubInstallation | [7 empty] | 3
5112 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 6981.5 | SemiSubStorageInstallation | [7 empty] | 3
5113 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 6992.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5114 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 6997 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5115 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 6998.1667 | MooredSubInstallation | [7 empty] | 3
5116 |  | Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 6998.1667 | MooredSubInstallation | Site
5117 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 6998.1667 | SemiSubStorageInstallation | [7 empty] | 3
5118 |  | Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 6998.1667 | SemiSubStorageInstallation | Site
5119 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6999 | MooringSystemInstallation
5120 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7000.1667 | MooredSubInstallation
5121 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 7000.1667 | SemiSubStorageInstallation
5122 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7003 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5123 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7006.1667 | MooredSubInstallation
5124 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7006.1667 | SemiSubStorageInstallation
5125 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 7018.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5126 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 7023 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5127 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7028.1667 | MooredSubInstallation
5128 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7028.1667 | SemiSubStorageInstallation
5129 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 7033 | MooringSystemInstallation
5130 |  | Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7038 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5131 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7040.1667 | MooredSubInstallation
5132 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7040.1667 | MooredSubInstallation | site | [6 empty] | 2
5133 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7040.1667 | SemiSubStorageInstallation
5134 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7040.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5135 |  | Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 7048 | MooringSystemInstallation
5136 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7050 | MooringSystemInstallation
5137 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7054 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5138 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7056 | MooredSubInstallation
5139 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 7056 | MooredSubInstallation
5140 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7056 | SemiSubStorageInstallation
5141 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 7056 | SemiSubStorageInstallation
5142 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7056.8333 | MooredSubInstallation | [7 empty] | 3
5143 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7056.8333 | SemiSubStorageInstallation | [7 empty] | 3
5144 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7064 | MooredSubInstallation
5145 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7064 | SemiSubStorageInstallation
5146 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 7069.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5147 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 7074 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5148 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7076 | MooredSubInstallation
5149 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7076 | MooringSystemInstallation
5150 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7076 | SemiSubStorageInstallation
5151 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7080 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5152 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7088 | MooredSubInstallation
5153 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7088 | SemiSubStorageInstallation
5154 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 7095.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5155 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7100 | MooredSubInstallation
5156 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 7100 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5157 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7100 | SemiSubStorageInstallation
5158 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7102 | MooringSystemInstallation
5159 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7106 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5160 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7107 | MooredSubInstallation
5161 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7107 | SemiSubStorageInstallation
5162 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7110.5 | MooredSubInstallation
5163 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7110.5 | SemiSubStorageInstallation
5164 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7114 | MooredSubInstallation
5165 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7114 | SemiSubStorageInstallation
5166 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7117.5 | MooredSubInstallation
5167 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7117.5 | SemiSubStorageInstallation
5168 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 7121.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5169 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 7126 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5170 |  | Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7128 | MooringSystemInstallation
5171 |  | Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7132 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5172 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7141.5 | MooredSubInstallation
5173 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 84.6667 | 105833.3333 | ACTION | 7141.5 | MooredSubInstallation
5174 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7141.5 | SemiSubStorageInstallation
5175 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 84.6667 | 105833.3333 | ACTION | 7141.5 | SemiSubStorageInstallation
5176 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7147.5 | MooredSubInstallation | [7 empty] | 3
5177 |  | Mooring System Installation Vessel | Install Suction Pile Anchor | 15.5 | 64583.3333 | ACTION | 7147.5 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5178 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7147.5 | SemiSubStorageInstallation | [7 empty] | 3
5179 |  | Mooring System Installation Vessel | Install Mooring Line | 4.5 | 18750 | ACTION | 7152 | MooringSystemInstallation |  |  |  | MooringSystemInstallation
5180 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 7164.1667 | MooredSubInstallation | [7 empty] | 3
5181 |  | Multi-Purpose Support Vessel | Delay | 124 | 516666.6667 | ACTION | 7164.1667 | MooredSubInstallation | Site
5182 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 7164.1667 | SemiSubStorageInstallation | [7 empty] | 3
5183 |  | Multi-Purpose Support Vessel | Delay | 124 | 516666.6667 | ACTION | 7164.1667 | SemiSubStorageInstallation | Site
5184 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7166.1667 | MooredSubInstallation
5185 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 7166.1667 | SemiSubStorageInstallation
5186 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7172.1667 | MooredSubInstallation
5187 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7172.1667 | SemiSubStorageInstallation
5188 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7194.1667 | MooredSubInstallation
5189 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7194.1667 | SemiSubStorageInstallation
5190 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7206.1667 | MooredSubInstallation
5191 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7206.1667 | MooredSubInstallation | site | [6 empty] | 2
5192 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7206.1667 | SemiSubStorageInstallation
5193 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7206.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5194 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7222.8333 | MooredSubInstallation | [7 empty] | 3
5195 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7222.8333 | SemiSubStorageInstallation | [7 empty] | 3
5196 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7224 | MooredSubInstallation
5197 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7224 | MooredSubInstallation
5198 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7224 | SemiSubStorageInstallation
5199 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7224 | SemiSubStorageInstallation
5200 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7232 | MooredSubInstallation
5201 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7232 | SemiSubStorageInstallation
5202 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7244 | MooredSubInstallation
5203 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7244 | SemiSubStorageInstallation
5204 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7256 | MooredSubInstallation
5205 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7256 | SemiSubStorageInstallation
5206 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7268 | MooredSubInstallation
5207 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7268 | SemiSubStorageInstallation
5208 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7275 | MooredSubInstallation
5209 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7275 | SemiSubStorageInstallation
5210 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7278.5 | MooredSubInstallation
5211 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7278.5 | SemiSubStorageInstallation
5212 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7282 | MooredSubInstallation
5213 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7282 | SemiSubStorageInstallation
5214 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7285.5 | MooredSubInstallation
5215 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7285.5 | SemiSubStorageInstallation
5216 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7309.5 | MooredSubInstallation
5217 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 86.6667 | 108333.3333 | ACTION | 7309.5 | MooredSubInstallation
5218 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7309.5 | SemiSubStorageInstallation
5219 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 86.6667 | 108333.3333 | ACTION | 7309.5 | SemiSubStorageInstallation
5220 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7315.5 | MooredSubInstallation | [7 empty] | 3
5221 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7315.5 | SemiSubStorageInstallation | [7 empty] | 3
5222 |  | Towing Group 1 | Delay | 50 | 187500 | ACTION | 7365.5 | MooredSubInstallation | [7 empty] | 3
5223 |  | Towing Group 1 | Delay | 50 | 187500 | ACTION | 7365.5 | SemiSubStorageInstallation | [7 empty] | 3
5224 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 7382.1667 | MooredSubInstallation | [7 empty] | 3
5225 |  | Multi-Purpose Support Vessel | Delay | 176 | 733333.3333 | ACTION | 7382.1667 | MooredSubInstallation | Site
5226 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 7382.1667 | SemiSubStorageInstallation | [7 empty] | 3
5227 |  | Multi-Purpose Support Vessel | Delay | 176 | 733333.3333 | ACTION | 7382.1667 | SemiSubStorageInstallation | Site
5228 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7384.1667 | MooredSubInstallation
5229 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 7384.1667 | SemiSubStorageInstallation
5230 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7390.1667 | MooredSubInstallation
5231 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7390.1667 | SemiSubStorageInstallation
5232 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7392 | MooredSubInstallation
5233 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7392 | MooredSubInstallation
5234 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7392 | SemiSubStorageInstallation
5235 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7392 | SemiSubStorageInstallation
5236 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7400 | MooredSubInstallation
5237 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7400 | SemiSubStorageInstallation
5238 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7412 | MooredSubInstallation
5239 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7412 | SemiSubStorageInstallation
5240 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7412.1667 | MooredSubInstallation
5241 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7412.1667 | SemiSubStorageInstallation
5242 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7424 | MooredSubInstallation
5243 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7424 | SemiSubStorageInstallation
5244 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7424.1667 | MooredSubInstallation
5245 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7424.1667 | MooredSubInstallation | site | [6 empty] | 2
5246 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7424.1667 | SemiSubStorageInstallation
5247 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7424.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5248 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7436 | MooredSubInstallation
5249 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7436 | SemiSubStorageInstallation
5250 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7440.8333 | MooredSubInstallation | [7 empty] | 3
5251 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7440.8333 | SemiSubStorageInstallation | [7 empty] | 3
5252 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7443 | MooredSubInstallation
5253 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7443 | SemiSubStorageInstallation
5254 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7446.5 | MooredSubInstallation
5255 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7446.5 | SemiSubStorageInstallation
5256 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7450 | MooredSubInstallation
5257 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7450 | SemiSubStorageInstallation
5258 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7453.5 | MooredSubInstallation
5259 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7453.5 | SemiSubStorageInstallation
5260 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7477.5 | MooredSubInstallation
5261 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 36.6667 | 45833.3333 | ACTION | 7477.5 | MooredSubInstallation
5262 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7477.5 | SemiSubStorageInstallation
5263 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 36.6667 | 45833.3333 | ACTION | 7477.5 | SemiSubStorageInstallation
5264 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7483.5 | MooredSubInstallation | [7 empty] | 3
5265 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7483.5 | SemiSubStorageInstallation | [7 empty] | 3
5266 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 7500.1667 | MooredSubInstallation | [7 empty] | 3
5267 |  | Multi-Purpose Support Vessel | Delay | 76 | 316666.6667 | ACTION | 7500.1667 | MooredSubInstallation | Site
5268 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 7500.1667 | SemiSubStorageInstallation | [7 empty] | 3
5269 |  | Multi-Purpose Support Vessel | Delay | 76 | 316666.6667 | ACTION | 7500.1667 | SemiSubStorageInstallation | Site
5270 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7502.1667 | MooredSubInstallation
5271 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 7502.1667 | SemiSubStorageInstallation
5272 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7508.1667 | MooredSubInstallation
5273 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7508.1667 | SemiSubStorageInstallation
5274 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7530.1667 | MooredSubInstallation
5275 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7530.1667 | SemiSubStorageInstallation
5276 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7542.1667 | MooredSubInstallation
5277 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7542.1667 | MooredSubInstallation | site | [6 empty] | 2
5278 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7542.1667 | SemiSubStorageInstallation
5279 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7542.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5280 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7558.8333 | MooredSubInstallation | [7 empty] | 3
5281 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7558.8333 | SemiSubStorageInstallation | [7 empty] | 3
5282 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7560 | MooredSubInstallation
5283 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7560 | MooredSubInstallation
5284 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7560 | SemiSubStorageInstallation
5285 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7560 | SemiSubStorageInstallation
5286 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7568 | MooredSubInstallation
5287 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7568 | SemiSubStorageInstallation
5288 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7580 | MooredSubInstallation
5289 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7580 | SemiSubStorageInstallation
5290 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7592 | MooredSubInstallation
5291 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7592 | SemiSubStorageInstallation
5292 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7604 | MooredSubInstallation
5293 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7604 | SemiSubStorageInstallation
5294 |  | Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 7637 | MooredSubInstallation
5295 |  | Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 7637 | SemiSubStorageInstallation
5296 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7644 | MooredSubInstallation
5297 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7644 | SemiSubStorageInstallation
5298 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7647.5 | MooredSubInstallation
5299 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7647.5 | SemiSubStorageInstallation
5300 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7651 | MooredSubInstallation
5301 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7651 | SemiSubStorageInstallation
5302 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7654.5 | MooredSubInstallation
5303 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7654.5 | SemiSubStorageInstallation
5304 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7678.5 | MooredSubInstallation
5305 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 119.6667 | 149583.3333 | ACTION | 7678.5 | MooredSubInstallation
5306 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7678.5 | SemiSubStorageInstallation
5307 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 119.6667 | 149583.3333 | ACTION | 7678.5 | SemiSubStorageInstallation
5308 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7684.5 | MooredSubInstallation | [7 empty] | 3
5309 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7684.5 | SemiSubStorageInstallation | [7 empty] | 3
5310 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 7701.1667 | MooredSubInstallation | [7 empty] | 3
5311 |  | Multi-Purpose Support Vessel | Delay | 159 | 662500 | ACTION | 7701.1667 | MooredSubInstallation | Site
5312 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 7701.1667 | SemiSubStorageInstallation | [7 empty] | 3
5313 |  | Multi-Purpose Support Vessel | Delay | 159 | 662500 | ACTION | 7701.1667 | SemiSubStorageInstallation | Site
5314 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7703.1667 | MooredSubInstallation
5315 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 7703.1667 | SemiSubStorageInstallation
5316 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7709.1667 | MooredSubInstallation
5317 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7709.1667 | SemiSubStorageInstallation
5318 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7728 | MooredSubInstallation
5319 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 49.5 | 0 | ACTION | 7728 | MooredSubInstallation
5320 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7728 | SemiSubStorageInstallation
5321 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 49.5 | 0 | ACTION | 7728 | SemiSubStorageInstallation
5322 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7731.1667 | MooredSubInstallation
5323 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7731.1667 | SemiSubStorageInstallation
5324 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7736 | MooredSubInstallation
5325 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7736 | SemiSubStorageInstallation
5326 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7743.1667 | MooredSubInstallation
5327 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7743.1667 | MooredSubInstallation | site | [6 empty] | 2
5328 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7743.1667 | SemiSubStorageInstallation
5329 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7743.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5330 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7748 | MooredSubInstallation
5331 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7748 | SemiSubStorageInstallation
5332 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7759.8333 | MooredSubInstallation | [7 empty] | 3
5333 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7759.8333 | SemiSubStorageInstallation | [7 empty] | 3
5334 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7760 | MooredSubInstallation
5335 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7760 | SemiSubStorageInstallation
5336 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7772 | MooredSubInstallation
5337 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7772 | SemiSubStorageInstallation
5338 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7779 | MooredSubInstallation
5339 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7779 | SemiSubStorageInstallation
5340 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7782.5 | MooredSubInstallation
5341 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7782.5 | SemiSubStorageInstallation
5342 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7786 | MooredSubInstallation
5343 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7786 | SemiSubStorageInstallation
5344 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7789.5 | MooredSubInstallation
5345 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7789.5 | SemiSubStorageInstallation
5346 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7813.5 | MooredSubInstallation
5347 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 53.6667 | 67083.3333 | ACTION | 7813.5 | MooredSubInstallation
5348 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7813.5 | SemiSubStorageInstallation
5349 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 53.6667 | 67083.3333 | ACTION | 7813.5 | SemiSubStorageInstallation
5350 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7819.5 | MooredSubInstallation | [7 empty] | 3
5351 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 7819.5 | SemiSubStorageInstallation | [7 empty] | 3
5352 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 7836.1667 | MooredSubInstallation | [7 empty] | 3
5353 |  | Multi-Purpose Support Vessel | Delay | 93 | 387500 | ACTION | 7836.1667 | MooredSubInstallation | Site
5354 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 7836.1667 | SemiSubStorageInstallation | [7 empty] | 3
5355 |  | Multi-Purpose Support Vessel | Delay | 93 | 387500 | ACTION | 7836.1667 | SemiSubStorageInstallation | Site
5356 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7838.1667 | MooredSubInstallation
5357 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 7838.1667 | SemiSubStorageInstallation
5358 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7844.1667 | MooredSubInstallation
5359 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7844.1667 | SemiSubStorageInstallation
5360 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7866.1667 | MooredSubInstallation
5361 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 7866.1667 | SemiSubStorageInstallation
5362 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7878.1667 | MooredSubInstallation
5363 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7878.1667 | MooredSubInstallation | site | [6 empty] | 2
5364 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 7878.1667 | SemiSubStorageInstallation
5365 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 7878.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5366 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7894.8333 | MooredSubInstallation | [7 empty] | 3
5367 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 7894.8333 | SemiSubStorageInstallation | [7 empty] | 3
5368 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7896 | MooredSubInstallation
5369 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7896 | MooredSubInstallation
5370 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7896 | SemiSubStorageInstallation
5371 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7896 | SemiSubStorageInstallation
5372 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7904 | MooredSubInstallation
5373 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7904 | SemiSubStorageInstallation
5374 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7916 | MooredSubInstallation
5375 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7916 | SemiSubStorageInstallation
5376 |  | Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 7930 | MooredSubInstallation
5377 |  | Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 7930 | SemiSubStorageInstallation
5378 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7942 | MooredSubInstallation
5379 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7942 | SemiSubStorageInstallation
5380 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7954 | MooredSubInstallation
5381 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7954 | SemiSubStorageInstallation
5382 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7961 | MooredSubInstallation
5383 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7961 | SemiSubStorageInstallation
5384 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7964.5 | MooredSubInstallation
5385 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7964.5 | SemiSubStorageInstallation
5386 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7968 | MooredSubInstallation
5387 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7968 | SemiSubStorageInstallation
5388 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7971.5 | MooredSubInstallation
5389 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7971.5 | SemiSubStorageInstallation
5390 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7995.5 | MooredSubInstallation
5391 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 100.6667 | 125833.3333 | ACTION | 7995.5 | MooredSubInstallation
5392 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7995.5 | SemiSubStorageInstallation
5393 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 100.6667 | 125833.3333 | ACTION | 7995.5 | SemiSubStorageInstallation
5394 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8001.5 | MooredSubInstallation | [7 empty] | 3
5395 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8001.5 | SemiSubStorageInstallation | [7 empty] | 3
5396 |  | Towing Group 1 | Delay | 19 | 71250 | ACTION | 8020.5 | MooredSubInstallation | [7 empty] | 3
5397 |  | Towing Group 1 | Delay | 19 | 71250 | ACTION | 8020.5 | SemiSubStorageInstallation | [7 empty] | 3
5398 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 8037.1667 | MooredSubInstallation | [7 empty] | 3
5399 |  | Multi-Purpose Support Vessel | Delay | 159 | 662500 | ACTION | 8037.1667 | MooredSubInstallation | Site
5400 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 8037.1667 | SemiSubStorageInstallation | [7 empty] | 3
5401 |  | Multi-Purpose Support Vessel | Delay | 159 | 662500 | ACTION | 8037.1667 | SemiSubStorageInstallation | Site
5402 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8039.1667 | MooredSubInstallation
5403 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 8039.1667 | SemiSubStorageInstallation
5404 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8045.1667 | MooredSubInstallation
5405 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8045.1667 | SemiSubStorageInstallation
5406 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8064 | MooredSubInstallation
5407 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 68.5 | 0 | ACTION | 8064 | MooredSubInstallation
5408 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8064 | SemiSubStorageInstallation
5409 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 68.5 | 0 | ACTION | 8064 | SemiSubStorageInstallation
5410 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 8067.1667 | MooredSubInstallation
5411 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 8067.1667 | SemiSubStorageInstallation
5412 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8072 | MooredSubInstallation
5413 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8072 | SemiSubStorageInstallation
5414 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 8079.1667 | MooredSubInstallation
5415 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 8079.1667 | MooredSubInstallation | site | [6 empty] | 2
5416 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 8079.1667 | SemiSubStorageInstallation
5417 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 8079.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5418 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8084 | MooredSubInstallation
5419 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8084 | SemiSubStorageInstallation
5420 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8095.8333 | MooredSubInstallation | [7 empty] | 3
5421 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8095.8333 | SemiSubStorageInstallation | [7 empty] | 3
5422 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8096 | MooredSubInstallation
5423 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8096 | SemiSubStorageInstallation
5424 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8108 | MooredSubInstallation
5425 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8108 | SemiSubStorageInstallation
5426 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8115 | MooredSubInstallation
5427 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8115 | SemiSubStorageInstallation
5428 |  | Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 8142 | MooredSubInstallation
5429 |  | Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 8142 | SemiSubStorageInstallation
5430 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8145.5 | MooredSubInstallation
5431 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8145.5 | SemiSubStorageInstallation
5432 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8149 | MooredSubInstallation
5433 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8149 | SemiSubStorageInstallation
5434 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8152.5 | MooredSubInstallation
5435 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8152.5 | SemiSubStorageInstallation
5436 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8176.5 | MooredSubInstallation
5437 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 80.6667 | 100833.3333 | ACTION | 8176.5 | MooredSubInstallation
5438 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8176.5 | SemiSubStorageInstallation
5439 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 80.6667 | 100833.3333 | ACTION | 8176.5 | SemiSubStorageInstallation
5440 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8182.5 | MooredSubInstallation | [7 empty] | 3
5441 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8182.5 | SemiSubStorageInstallation | [7 empty] | 3
5442 |  | Towing Group 1 | Delay | 38 | 142500 | ACTION | 8220.5 | MooredSubInstallation | [7 empty] | 3
5443 |  | Towing Group 1 | Delay | 38 | 142500 | ACTION | 8220.5 | SemiSubStorageInstallation | [7 empty] | 3
5444 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8232 | MooredSubInstallation
5445 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 55.5 | 0 | ACTION | 8232 | MooredSubInstallation
5446 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8232 | SemiSubStorageInstallation
5447 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 55.5 | 0 | ACTION | 8232 | SemiSubStorageInstallation
5448 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 8237.1667 | MooredSubInstallation | [7 empty] | 3
5449 |  | Multi-Purpose Support Vessel | Delay | 158 | 658333.3333 | ACTION | 8237.1667 | MooredSubInstallation | Site
5450 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 8237.1667 | SemiSubStorageInstallation | [7 empty] | 3
5451 |  | Multi-Purpose Support Vessel | Delay | 158 | 658333.3333 | ACTION | 8237.1667 | SemiSubStorageInstallation | Site
5452 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8239.1667 | MooredSubInstallation
5453 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 8239.1667 | SemiSubStorageInstallation
5454 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8240 | MooredSubInstallation
5455 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8240 | SemiSubStorageInstallation
5456 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8245.1667 | MooredSubInstallation
5457 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8245.1667 | SemiSubStorageInstallation
5458 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 8246.1667 | MooredSubInstallation
5459 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 8246.1667 | SemiSubStorageInstallation
5460 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8252 | MooredSubInstallation
5461 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8252 | SemiSubStorageInstallation
5462 |  | Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 8289 | MooredSubInstallation
5463 |  | Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 8289 | SemiSubStorageInstallation
5464 |  | Multi-Purpose Support Vessel | Delay | 47 | 195833.3333 | ACTION | 8293.1667 | MooredSubInstallation
5465 |  | Multi-Purpose Support Vessel | Delay | 47 | 195833.3333 | ACTION | 8293.1667 | SemiSubStorageInstallation
5466 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8301 | MooredSubInstallation
5467 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8301 | SemiSubStorageInstallation
5468 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8313 | MooredSubInstallation
5469 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8313 | SemiSubStorageInstallation
5470 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 21 | 87500 | ACTION | 8314.1667 | MooredSubInstallation
5471 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 21 | 87500 | ACTION | 8314.1667 | SemiSubStorageInstallation
5472 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8320 | MooredSubInstallation
5473 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8320 | SemiSubStorageInstallation
5474 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 11 | 45833.3333 | ACTION | 8325.1667 | MooredSubInstallation
5475 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 11 | 45833.3333 | ACTION | 8325.1667 | SemiSubStorageInstallation
5476 |  | Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 8328.1667 | MooredSubInstallation
5477 |  | Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 8328.1667 | SemiSubStorageInstallation
5478 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 8329.1667 | MooredSubInstallation
5479 |  | Towing Group 1 | Positioning Support | 92 | 230000 | ACTION | 8329.1667 | MooredSubInstallation | site | [6 empty] | 2
5480 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 8329.1667 | SemiSubStorageInstallation
5481 |  | Towing Group 1 | Positioning Support | 92 | 230000 | ACTION | 8329.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5482 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8345.8333 | MooredSubInstallation | [7 empty] | 3
5483 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8345.8333 | SemiSubStorageInstallation | [7 empty] | 3
5484 |  | Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 8365 | MooredSubInstallation
5485 |  | Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 8365 | SemiSubStorageInstallation
5486 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8368.5 | MooredSubInstallation
5487 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8368.5 | SemiSubStorageInstallation
5488 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8372 | MooredSubInstallation
5489 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8372 | SemiSubStorageInstallation
5490 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8375.5 | MooredSubInstallation
5491 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8375.5 | SemiSubStorageInstallation
5492 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8399.5 | MooredSubInstallation
5493 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 53.6667 | 67083.3333 | ACTION | 8399.5 | MooredSubInstallation
5494 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8399.5 | SemiSubStorageInstallation
5495 |  | Towing Group 1 | Delay: No Completed Assemblies Available | 53.6667 | 67083.3333 | ACTION | 8399.5 | SemiSubStorageInstallation
5496 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8400 | MooredSubInstallation
5497 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 0.5 | 0 | ACTION | 8400 | MooredSubInstallation
5498 |  | Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8400 | SemiSubStorageInstallation
5499 |  | Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 0.5 | 0 | ACTION | 8400 | SemiSubStorageInstallation
5500 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8405.5 | MooredSubInstallation | [7 empty] | 3
5501 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8405.5 | SemiSubStorageInstallation | [7 empty] | 3
5502 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8408 | MooredSubInstallation
5503 |  | Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8408 | SemiSubStorageInstallation
5504 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8420 | MooredSubInstallation
5505 |  | Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8420 | SemiSubStorageInstallation
5506 |  | Towing Group 1 | Delay | 20 | 75000 | ACTION | 8425.5 | MooredSubInstallation | [7 empty] | 3
5507 |  | Towing Group 1 | Delay | 20 | 75000 | ACTION | 8425.5 | SemiSubStorageInstallation | [7 empty] | 3
5508 |  | Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8426 | MooredSubInstallation
5509 |  | Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8426 | SemiSubStorageInstallation
5510 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8438 | MooredSubInstallation
5511 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8438 | SemiSubStorageInstallation
5512 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 8442.1667 | MooredSubInstallation | [7 empty] | 3
5513 |  | Multi-Purpose Support Vessel | Delay | 113 | 470833.3333 | ACTION | 8442.1667 | MooredSubInstallation | Site
5514 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 8442.1667 | SemiSubStorageInstallation | [7 empty] | 3
5515 |  | Multi-Purpose Support Vessel | Delay | 113 | 470833.3333 | ACTION | 8442.1667 | SemiSubStorageInstallation | Site
5516 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8444.1667 | MooredSubInstallation
5517 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 8444.1667 | SemiSubStorageInstallation
5518 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8450 | MooredSubInstallation
5519 |  | Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8450 | SemiSubStorageInstallation
5520 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8450.1667 | MooredSubInstallation
5521 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8450.1667 | SemiSubStorageInstallation
5522 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 8451.1667 | MooredSubInstallation
5523 |  | Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 8451.1667 | SemiSubStorageInstallation
5524 |  | Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 8452 | MooredSubInstallation
5525 |  | Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 8452 | SemiSubStorageInstallation
5526 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8459 | MooredSubInstallation
5527 |  | Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8459 | SemiSubStorageInstallation
5528 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8462.5 | MooredSubInstallation
5529 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8462.5 | SemiSubStorageInstallation
5530 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8466 | MooredSubInstallation
5531 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8466 | SemiSubStorageInstallation
5532 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8469.5 | MooredSubInstallation
5533 |  | Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8469.5 | SemiSubStorageInstallation
5534 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 8473.1667 | MooredSubInstallation
5535 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 8473.1667 | SemiSubStorageInstallation
5536 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 8485.1667 | MooredSubInstallation
5537 |  | Towing Group 1 | Positioning Support | 43 | 107500 | ACTION | 8485.1667 | MooredSubInstallation | site | [6 empty] | 2
5538 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 8485.1667 | SemiSubStorageInstallation
5539 |  | Towing Group 1 | Positioning Support | 43 | 107500 | ACTION | 8485.1667 | SemiSubStorageInstallation | site | [6 empty] | 2
5540 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8493.5 | MooredSubInstallation
5541 |  | Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8493.5 | SemiSubStorageInstallation
5542 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8501.8333 | MooredSubInstallation | [7 empty] | 3
5543 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8501.8333 | SemiSubStorageInstallation | [7 empty] | 3
5544 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8507.8333 | MooredSubInstallation | [7 empty] | 3
5545 |  | Towing Group 1 | Ballast to Towing Draft | 6 | 22500 | ACTION | 8507.8333 | SemiSubStorageInstallation | [7 empty] | 3
5546 |  | Towing Group 1 | Tow Substructure | 16.6667 | 62500 | ACTION | 8524.5 | MooredSubInstallation | [7 empty] | 3
5547 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 8524.5 | MooredSubInstallation | Site
5548 |  | Towing Group 1 | Tow substructure | 16.6667 | 62500 | ACTION | 8524.5 | SemiSubStorageInstallation | [7 empty] | 3
5549 |  | Multi-Purpose Support Vessel | Delay | 39.3333 | 163888.8889 | ACTION | 8524.5 | SemiSubStorageInstallation | Site
5550 |  | Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8526.5 | MooredSubInstallation
5551 |  | Multi-Purpose Support Vessel | Position substructure | 2 | 8333.3333 | ACTION | 8526.5 | SemiSubStorageInstallation
5552 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8532.5 | MooredSubInstallation
5553 |  | Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8532.5 | SemiSubStorageInstallation
5554 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 8554.5 | MooredSubInstallation
5555 |  | Multi-Purpose Support Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 8554.5 | SemiSubStorageInstallation
5556 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 8566.5 | MooredSubInstallation
5557 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 8566.5 | MooredSubInstallation | site | [6 empty] | 2
5558 |  | Multi-Purpose Support Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 8566.5 | SemiSubStorageInstallation
5559 |  | Towing Group 1 | Positioning Support | 42 | 105000 | ACTION | 8566.5 | SemiSubStorageInstallation | site | [6 empty] | 2
5560 |  | Multi-Purpose Support Vessel | Transit | 10 | 41666.6667 | ACTION | 8576.5 | MooredSubInstallation
5561 |  | Multi-Purpose Support Vessel | Transit | 10 | 41666.6667 | ACTION | 8576.5 | SemiSubStorageInstallation
5562 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8583.1667 | MooredSubInstallation | [7 empty] | 3
5563 |  | Towing Group 1 | Transit | 16.6667 | 62500 | ACTION | 8583.1667 | SemiSubStorageInstallation | [7 empty] | 3